## Sheet1
Assumptions:
-Bare minimum is ability to search for a product, add it to a cart, and checkout + basic account management
-No loss of existing website functionality.
|  | Upside | Downnside | Steps to mitigate downside?
Functionality | Scope change | Estimated impact on launch date - reduction in programming time etc. | Touchpoints: Impact of scope change on current design & specs? Complicates programming? Impact on total UX?
Shop widget | Postpone entirely | N/A
| Simplify (how?) | N/A -it's 99% done?
-Search results | Postpone entirely | N/A
| Simplify (how?): Simplify YMAC | ? | ?
-Prod Desc | Postpone entirely | N/A
| Simplify (how?): | ? | ?
Active Cart | Postpone entirely | N/A
| Simplify (how?): | ? | ?
Saved Carts | Postpone entirely | N/A (b/c this would be akin to not being able to retrieve quotes online)
| Simplify (how?): | ? | ?
Saved Items | Postpone entirely | N/A (b/c this would be akin to not being able to retrieve quotes online)
| Simplify (how?): | ? | ?
Past orders | Postpone entirely | N/A (b/c 'order tracking' exists on current site)?
| Simplify (how?): | ?
Checkout | Postpone entirely | N/A
| Simplify (how?): Bundling shipments | ?
Shared Carts | Postpone entirely | -4 weeks | Would have to remove icons from cart. Loss of major "carrot" for existing users to learn new interface.
| Simplify (how?): | ? | ?
Shared items | Postpone entirely | -4 weeks | Would have to remove icons from cart & results. Loss of major "carrot" for existing users to learn new interface.
| Simplify (how?): | ? | ?
My acct/Prefs | Postpone entirely | ? | ?
| Simplify (how?): | ? | ?
Narrative thread | Postpone entirely | -10 weeks | ?
| Simplify (how?): | ? | ?
Predictive ordering | Postpone entirely | -4 weeks | ?
| Simplify (how?): Eliminate any dynamic logic | -3 weeks | ?
CE functionality | Postpone entirely | ? | ?
| Simplify (how?): | ? | ?
Analytics | Postpone entirely | ? | ?
| Simplify (how?): | ? | ?