## Sheet1
Assumptions: Bare minimum is ability to search for a product, add it to a cart checkout and manage account
No loss of existing website functionality.
|  | Upside | Downnside | Steps to mitigate downside?
Functionality | Scope change | Estimated impact on launch date - reduction in programming time etc. | Touchpoints: Impact of scope change on current design & specs? Complicates programming? Impact on total UX?
Shop widget | Postpone entirely | N/A
| Simplify (how?) | N/A -it's 99% done
Search results | Postpone entirely | N/A
| Simplify (how?): Simplify YMAC | ? | ?
Prod Desc | Postpone entirely | N/A
| Simplify (how?): | ? | ?
Active Cart | Postpone entirely | N/A
| Simplify (how?): | ? | ?
Saved Carts | Postpone entirely | ? | Leaves a hole in the tab structure and…
| Simplify (how?): | ? | ?
Saved Items | Postpone entirely | ? | Leaves a hole in the tab structure and…
| Simplify (how?): | ? | ?
Past orders | Postpone entirely | N/A (b/c 'order tracking' exists on current site?
| Simplify (how?): | ?
Checkout | Postpone entirely | N/A
| Simplify (how?): Bundling shipments | ?
Shared Carts | Postpone entirely | -4 weeks | Would have to remove icons from cart. Loss of major "carrot" for existing users to learn new interface.
| Simplify (how?): | ? | ?
Shared items | Postpone entirely | -4 weeks | Would have to remove icons from cart & results
| Simplify (how?): | ? | ?
My acct/Prefs | Postpone entirely | ? | ?
| Simplify (how?): | ? | ?
Narrative thread | Postpone entirely | -10 weeks | ?
| Simplify (how?): | ? | ?
Predictive ordering | Postpone entirely | -4 weeks | ?
| Simplify (how?): Eliminate any dynamic logic | -3 weeks | ?