## Summary
Task | Design | Avante | UI | AV Rework | UI Rework
Shop | 3 | 4 | 4 | 3 | 3 | 4 | no macchi; cliff's stock ranges; mkplc ranges; database cleanup; ui big fixes; zip code validation
Results | 3.5 | 5 | 4 | 4 | 3 | 6 | removed 10 days (for MOD pricing).
Create Config | 1 | 3 | 0 | 1 | 0 | 1 | product line creation and test
Create Quote | 5 | 8 | 0 | 3 | 0 | 4 | lots to figure out as of yet
Availability | 2 | 3 | 2 | 1 | 0 | 2 | need clarification on what actually happens
Freight | 1 | 1 | 1 | 1 | 1 | 1 | pretty much done
Price Breaks | 1 | 2 | 2 | 1 | 1 | 1 | no issues
Extended Desc | 1 | 1 | 1 | 1 | 1 | 2 | make sure design satisfies marketing reqs
Save Tags | 0 | 0 | 0 | 1 | 1 | 2 | no issues
Predictive Ordering | 3 | 4 | 2 | 2 | 2 | 2 | incomplete design
Shared Item | 0.8 | 0 | 4 | 1 | 2 | 3 | no issues
Active Cart | 11.9 | 15.1 | 18.5 | 4.53 | 5.55 | 3 | Details on its own worksheet.
Quick Add | 0 | 0 | 0 | 0 | 0 | 0 | included in Active Cart
Shared Cart | 2.3 | 3.9 | 4.1 | 1.17 | 1.23 | 2
Save Items | 0.2 | 0 | 1.8 | 2 | 0.54 | 2
Order History | 2 | 2 | 3.2 | 0.6 | 0.96 | 2
Saved Carts | 3.5 | 3 | 3 | 0.9 | 0.9 | 2
Data Conversions | 5 | 4.5 | 0 | 1.35 | 0 | 4
Check Out | 9 | 15 | 9.5 | 4 | 2 | 5
My Account | 3 | 4 | 6 | 2 | 2 | 3
Item Search | 1 | 1 | 1 | 1 | 1 | 1
Notifications | 3 | 4 | 4 | 2 | 2 | 2
Exp/Twit/??? | 5 | 4 | 4 | 2 | 2 | 2
CE Web Integration | 6 | 10 | 10 | 4 | 4 | 4
Creating Mult Orders | 6 | 14 | 3 | 4 | 4 | 10
Mktg/Fat Content | 8 | 4 | 8 | 3 | 3 | 3
Pre Login Func | 2 | 3 | 1 | 2 | 2 | 3
Changing Quotes | 5 | 4 | 4 | 2 | 2 | 2 | Exp vs unexp/unconverted; reprice/new price; increment config; overlay saveditem
Converting Quotes | 4 | 5 | 0 | 2 | 0 | 2 | If c/e 'orders' on web and email goes to queue-no changes
Qut/Ord Ackn Forms | 3 | 3 | 3 | 1 | 0 | 1 | No change to form layouts. Continue to use for NS quotes/orders & sample orders. Link from web to Avante for faxed ackn. Link from Avante to Web to re-send Order Ackn after changes. Add checkout shipping upcharges. Investigate handling Master order numbers on optio forms.
Shipment Bundling | 8 | 4 | 5 | 2 | 2 | 3 | this hasn't been included in other numbers
Shipping Upcharges | 2 | 3 | 0 | 1 | 0 | 1 | Inside Deliv,tailgate,liftgate and Export Pallet Charges
Avante Rpts | 1 | 2 | 0 | 1 | 0 | 1 | Due to configuration criteria changes/part# changes
Ashad Conversion | 5 | 7 | 0 | 2 | 0 | 2 | Conversion of existing config records to new prod line-purge unconverted configs
Misc Avante Changes | 4 | 8 | 0 | 2 | 0 | 2 | Incomplete List: QUO4000-only NS, Request Sys-new types/direction, New FOB Cd 'CPU', Shipping Notifications
Wind/Sheeting Gusset | 0 | 2 | 2 | 1 | 1 | 1 | Adding A-wind/B-wind & Slit gusset/Slit Center-diff UI handling. Wind question has been removed
Stock Dimension Ranges | 0 | 3 | 0 | 1 | 0 |  | Per Cliff's Spreadsheet (Judy will make pgm changes). 'Can this be a MOD item' rules (dimensions/materials, etc)
MOD Pricing | 2 | 9 | 0 | 2 | 0 | 1 | Add'l logic for Marketplace + 7 days remaining for Custom Items
Atlanta Production | 1 | 3 | 0 | 1 | 0 | 1 | Design Hrs assume that David writes specs for mfg facility assignment & BS/SW Rule changes
#Days | 124.2 | 171.5 | 111.1 | 71.55 | 50.18 | 93
#Resources | 2 | 2.4 | 1.6 | 2.4 | 1.6 | Various
#Weeks | 12.518 | 14.3897 | 13.9855 | 6.0605 | 6.3705 | Ongonig
Complete Date | 2026-11-01 15:01 | 2026-11-14 17:28 | 2026-11-11 21:34 | 2026-12-27 03:38 | 2026-12-26 11:48 | Pre-live
Pgmg 1 Complete | 2026-11-14 17:28
Pgmg 2 Complete | 2026-12-27 03:38
Formulas:
Design = TODAY()+([Design, row above]*7)
Avante = TODAY()+([Avante, row above]*7)
UI = TODAY()+([UI, row above]*7)
AV Rework = [Avante]+([AV Rework, row above]*7)
UI Rework = [UI]+([UI Rework, row above]*7)

## Active Cart
Task | Design | Avante | UI | QA/Test | Avante Rework | UI Rework
MOD item Descriptions | 1 | 1 | 0.5
Freight Dropdown | 0.1 | 0 | 0.3
Line Repricing | 1.5 | 0.4 | 0.6
Total Items | 0 | 0.3 | 0
Edit Qty | 0.3 | 0.2 | 0.8
Plate Upload / Display | 2 | 1 | 2.5
Repricing Clock | 0.2 | 0 | 0.3
Disabling Lines | 0.5 | 0 | 0.1
Replacing MOD items in Cart with new MOD items | 1.2 | 1.5 | 2
Delete Cart Function | 0 | 0 | 0
Special CE Handling | 1.75 | 3 | 3
Pricebreak display | 0.75 | 2 | 3
Quick Add | 0 | 0 | 0
Returning Items for Cart display | 0.7 | 3 | 0.4
Saving & Naming the Cart | 0.4 | 0.2 | 0.5
Validating Cart Names, CPU, & Zip Code | 0.5 | 0.5 | 1.5
MOD items in Carts | 1 | 2 | 3
| 11.9 | 15.1 | 18.5 | 3 | 4.53 | 5.55
Overall Rework Factor | 0.3

## Share Cart
Task | Design | Avante | UI | QA/Test | Avante Rework | UI Rework
Build and Link to popup | 0.1 | 0 | 0.4
Build Top interface for To, CC, & Subject | 0.1 |  | 0.1
Handle logo swapping for customer sharing | 0.2 | 0.2 | 0.5 |  |  |  | These numbers assume this has been essentially worked out for share items.
Return Data for MOD Items | 0.3 | 1.5 | 0.4
Build Price break display for Non customer sharing | 0.2 | 0.7 | 0.6
Build Price break drawer for markups. | 0.2 | 0.6 | 2
Saving Shared Cart Event | 1.2 | 0.9 | 0.1
| 2.3 | 3.9 | 4.1 | 2 | 1.17 | 1.23
Overall Rework Factor | 0.3

## Save Items
Task | Design | Avante | UI | QA/Test | Avante Rework | UI Rework
Save the items to the database. | 0.2 | 0 | 0
Return the Saved items | 0 | 0 | 1
Return Filtering tags. | 0 | 0 | 0.5
Finish Popup | 0 | 0 | 0.3
| 0.2 | 0 | 1.8 | 2 | 2 | 0.54
Overall Rework Factor | 0.3

## Order History
Task | Design | Avante | UI | QA/Test | Avante Rework | UI Rework
Modify results to handle master orders | 0.5 | 1 | 0.2
Complete Summary Popup | 1.5 | 1 | 3
| 2 | 2 | 3.2 | 2 | 0.6 | 0.96
Overall Rework Factor | 0.3

## Saved Carts
Task | Design | Avante | UI | QA/Test | Avante Rework | UI Rework
Activating a saved cart | 1 | 0.5 | 1
Handling working with someone else's cart | 1.5 | 1 | 1
MOD items in Carts | 1 | 1.5 | 1
| 3.5 | 3 | 3 | 2 | 0.9 | 0.9
Overall Rework Factor | 0.3

## Checkout
Task | Design | Avante | UI | QA/Test | Avante Rework | UI Rework
Activating a saved cart | 1 | 0.5 | 1
Handling working with someone else's cart | 1.5 | 1 | 1
MOD items in Carts | 1 | 1.5 | 1
| 3.5 | 3 | 3 | 2 | 0.9 | 0.9
Overall Rework Factor | 0.3

## Data Conversions
Task | Design | Avante | UI | QA/Test | Avante Rework | UI Rework
Catalog Codes | 1 | 1
Quote Conversions to Saved Items | 3 | 2
Web Fields for Stock Items | 1 | 1.5
| 5 | 4.5 | 0 | 4 | 1.35 | 0
Overall Rework Factor | 0.3

## ShipUpchgs
Investigate options of how we can print shipping upcharges not included in pricing on forms:
- No detail/show below subtotal
- Show detail (ie, liftgate, export pallet) and amount

## Defs
Avante Programmers: Wayne, Joe, Janice @ 80% | 2.4
UI Programmers: Ed, Sal @ 80% | 1.6
Technical Designers: John, Judy @ 75% ; Jim, Cathy @ 25% | 2
QA/Test: Susan, Steve, Jim, Owen, Cathy, CE, Mktg

## AvanteRpts
Investigate what Avante Reports/Processes are using configurator files to extract data.
I am looking for a list of processes that will require changes when the BAGS/SHEETING/FURN, etc
product lines are combined into a single MOD product line. This means that criteria numbers
may change:
- Search IIPROCESS/BP/LDLIB/AVBP looking for CFQNA<13,x> extractions
- Search IIPROCESS/BP/LDLIB/AVBP looking for CFORDER<13,x> extractions
- Search IIPROCESS/BP/LDLIB/AVBP looking for CFBLDHDR<10,x> extractions

## Misc Avante
Investigate what changes will be needed for the new FOB CODE "CPU". I believe CPU (customer pickup)
should follow the rules for COL/3PB in that they have no freight implications. Be sure to check the
freight quote/freight$ calculation programs to make sure that CPU will not go through this logic.
Investigate what should happen with CPU credit card orders -- should they be handled like PPD?
Investigate how 'shipping notifications' could be sent to customers notifying them that their shipment
has been made:
- Timing - should this be done when updating Avante? What if shipment hasn’t left building yet?
- What email address to use?
- What if customer doesn't accept emails?
- Should notifications be sent for all shipments? CPU's?
Investigate/writeup design to only allow NS Made/Buy quotes to be entered via QUO4000. Is there an
easy way to disable the other selections BAGS/SHEETING/TUBING/FURN from the screens? Or should
we bypass the screens entirely and only allow NS as an item number in this screen?