## Summary
Task | Status | Design | Avante | UI | AV Rework | UI Rework | Ongoing QA
ShopWidget | In Progress | 3.5 | 14.5 | 7.5 | 4.35 | 2.25 | 6.6 | no macchi; database cleanup; ui bug fixes;
Create Config |  | 1 | 3 | 0 | 1 | 0 | 1 | product line creation and test
Availability |  | 2 | 3 | 2 | 1 | 0 | 2 | need clarification on what actually happens
Freight |  | 1 | 1 | 1 | 1 | 1 | 1 | pretty much done
Price Breaks |  | 1 | 2 | 2 | 1 | 1 | 1 | no issues
Extended Desc |  | 1 | 1 | 1 | 1 | 1 | 2 | make sure design satisfies marketing reqs
Save Tags |  | 0 | 0 | 0 | 1 | 1 | 2 | no issues
Predictive Ordering | TBD | 3 | 3 | 2 | 2 | 2 | 2 | incomplete design
Shared Item |  | 0.8 | 0 | 2 | 1 | 2 | 3 | no issues
Active Cart |  | 11.9 | 15.1 | 18 | 4.53 | 5.4 | 3 | Details on its own worksheet.
Quick Add |  | 0 | 0 | 0 | 0 | 0 | 0 | included in Active Cart
Shared Cart |  | 2.3 | 3.9 | 4.1 | 1.17 | 1.23 | 2
Save Items |  | 0.2 | 0 | 1.8 | 2 | 0.54 | 2
Order History |  | 2 | 2 | 3.2 | 0.6 | 0.96 | 2
Saved Carts |  | 3.5 | 3 | 3 | 0.9 | 0.9 | 2
Data Conversions |  | 5 | 4.5 | 0 | 1.35 | 0 | 4
Check Out |  | 9 | 15 | 9.5 | 4 | 2 | 5
My Account |  | 3 | 4 | 6 | 2 | 2 | 3
Item Search |  | 1 | 1 | 1 | 1 | 1 | 1
Notifications |  | 3 | 4 | 4 | 2 | 2 | 2
Exp/Twit/??? |  | 5 | 4 | 4 | 2 | 2 | 2
CE Web Integration |  | 6 | 10 | 10 | 4 | 4 | 4
Creating Mult Orders |  | 6 | 14 | 3 | 4 | 4 | 10
Mktg/Fat Content |  | 8 | 4 | 8 | 3 | 3 | 3
Pre Login Func |  | 2 | 3 | 1 | 2 | 2 | 3
Changing Quotes |  | 5 | 4 | 4 | 2 | 2 | 2 | Exp vs unexp/unconverted; reprice/new price; increment config; overlay saveditem
Converting Quotes |  | 4 | 5 | 0 | 2 | 0 | 2 | If c/e 'orders' on web and email goes to queue-no changes
Qut/Ord Ackn Forms |  | 3 | 3 | 3 | 1 | 0 | 1 | No change to form layouts. Continue to use for NS quotes/orders & sample orders. Link from web to Avante for faxed ackn. Link from Avante to Web to re-send Order Ackn after changes. Add checkout shipping upcharges. Investigate handling Master order numbers on optio forms.
Shipment Bundling |  | 8 | 4 | 5 | 2 | 2 | 3 | this hasn't been included in other numbers
Shipping Upcharges |  | 2 | 3 | 0 | 1 | 0 | 1 | Inside Deliv,tailgate,liftgate and Export Pallet Charges
Avante Rpts |  | 1 | 2 | 0 | 1 | 0 | 1 | Due to configuration criteria changes/part# changes
Ashad Conversion |  | 5 | 7 | 0 | 2 | 0 | 2 | Conversion of existing config records to new prod line-purge unconverted configs
Misc Avante Changes |  | 4 | 8 | 0 | 2 | 0 | 2 | Incomplete List: QUO4000-only NS, Request Sys-new types/direction, New FOB Cd 'CPU', Shipping Notifications
Wind/Sheeting Gusset |  | 0 | 2 | 2 | 1 | 1 | 1 | Adding A-wind/B-wind & Slit gusset/Slit Center-diff UI handling. Wind question has been removed
MOD Pricing |  | 2 | 9 | 0 | 2 | 0 | 1 | Add'l logic for Marketplace + 7 days remaining for Custom Items
Atlanta Production |  | 1 | 3 | 0 | 1 | 0 | 1 | Design Hrs assume that David writes specs for mfg facility assignment & BS/SW Rule changes
#Days |  | 116.2 | 165 | 108.1 | 64.9 | 46.28 | 85.6
#Resources |  | 2 | 2.4 | 1.6 | 2.4 | 1.6 | Various
#Weeks |  | 11.718 | 13.848 | 13.6105 | 5.5063 | 5.883 | Ongonig
Complete Date |  | 2013-10-13 00:37 | 2013-10-27 22:28 | 2013-10-26 06:34 | 2013-12-05 11:32 | 2013-12-06 10:54 | Pre-live
Pgmg 1 Complete |  | 2013-10-27 22:28
Pgmg 2 Complete |  | 2013-12-06 10:54 | 2013-10-26 | 2013-10-21 | 2013-12-07 | 2013-12-05
Formulas:
Design = TODAY()+([Design, row above]*7)
Avante = TODAY()+([Avante, row above]*7)
UI = TODAY()+([UI, row above]*7)
AV Rework = [Avante]+([AV Rework, row above]*7)
UI Rework = [UI]+([UI Rework, row above]*7)

## ShopWidget
Task | Design |  |  | Avante |  |  | UI |  |  | Rework |  | QA | Status/Notes
| Days | Rem | Resp | Days | Rem | Resp | Days | Rem | Resp | Avante | UI
Status as of 7/22/13
Implementation of MOD items |  |  |  | 5 | 5 | JC | 1 | 1 | ED |  |  |  | Waiting for Avante programming to complete - Can I make a MOD and Range Changes (Stock and Market Place)
Quick Find Item | 0.5 | 0.5 | JBM | 0.5 | 0.5 | ?? | 0.5 | 0.5 | ED |  |  |  | Waiting for Preferences design - zip code logic - how should it work
Group Validations | [6 empty] | 1 | 1 | ED |  |  |  | Ed - #3 on list
Availability | 1 | 1 | JBM | 2 | 2 | WC | 5 | 5 | ED |  |  |  | Ed - #3 on list, PopUp, Sustitutions - quesiton on return from sub page, Data Validation
Create Quote | 2 | 2 | JP | 7 | 7 | JM | [6 empty] | Mostly figured out but a lot of work and testing left to do.
Total Days | 3.5 | 3.5 |  | 14.5 | 14.5 |  | 7.5 | 7.5 |  | 4.35 | 2.25 | 6.6
Overall Rework Factor | 0.3
Overall QA Factor | 0.3

## Active Cart
Task | Design | Avante | UI | QA/Test | Avante Rework | UI Rework
MOD item Descriptions | 1 | 1 | 0.5
Freight Dropdown | 0.1 | 0 | 0.3
Line Repricing | 1.5 | 0.4 | 0.6
Total Items | 0 | 0.3 | 0
Edit Qty | 0.3 | 0.2 | 0.8
Plate Upload / Display | 2 | 1 | 2.5
Repricing Clock | 0.2 | 0 | 0.3
Disabling Lines | 0.5 | 0 | 0.1
Replacing MOD items in Cart with new MOD items | 1.2 | 1.5 | 1.5
Delete Cart Function | 0 | 0 | 0
Special CE Handling | 1.75 | 3 | 3
Pricebreak display | 0.75 | 2 | 3
Quick Add | 0 | 0 | 0
Returning Items for Cart display | 0.7 | 3 | 0.4
Saving & Naming the Cart | 0.4 | 0.2 | 0.5
Validating Cart Names, CPU, & Zip Code | 0.5 | 0.5 | 1.5
MOD items in Carts | 1 | 2 | 3
| 11.9 | 15.1 | 18 | 3 | 4.53 | 5.4
Overall Rework Factor | 0.3

## Share Cart
Task | Design | Avante | UI | QA/Test | Avante Rework | UI Rework
Build and Link to popup | 0.1 | 0 | 0.4
Build Top interface for To, CC, & Subject | 0.1 |  | 0.1
Handle logo swapping for customer sharing | 0.2 | 0.2 | 0.5 |  |  |  | These numbers assume this has been essentially worked out for share items.
Return Data for MOD Items | 0.3 | 1.5 | 0.4
Build Price break display for Non customer sharing | 0.2 | 0.7 | 0.6
Build Price break drawer for markups. | 0.2 | 0.6 | 2
Saving Shared Cart Event | 1.2 | 0.9 | 0.1
| 2.3 | 3.9 | 4.1 | 2 | 1.17 | 1.23
Overall Rework Factor | 0.3

## Save Items
Task | Design | Avante | UI | QA/Test | Avante Rework | UI Rework
Save the items to the database. | 0.2 | 0 | 0
Return the Saved items | 0 | 0 | 1
Return Filtering tags. | 0 | 0 | 0.5
Finish Popup | 0 | 0 | 0.3
| 0.2 | 0 | 1.8 | 2 | 2 | 0.54
Overall Rework Factor | 0.3

## Order History
Task | Design | Avante | UI | QA/Test | Avante Rework | UI Rework
Modify results to handle master orders | 0.5 | 1 | 0.2
Complete Summary Popup | 1.5 | 1 | 3
| 2 | 2 | 3.2 | 2 | 0.6 | 0.96
Overall Rework Factor | 0.3

## Saved Carts
Task | Design | Avante | UI | QA/Test | Avante Rework | UI Rework
Activating a saved cart | 1 | 0.5 | 1
Handling working with someone else's cart | 1.5 | 1 | 1
MOD items in Carts | 1 | 1.5 | 1
| 3.5 | 3 | 3 | 2 | 0.9 | 0.9
Overall Rework Factor | 0.3

## Checkout
Task | Design | Avante | UI | QA/Test | Avante Rework | UI Rework
Activating a saved cart | 1 | 0.5 | 1
Handling working with someone else's cart | 1.5 | 1 | 1
MOD items in Carts | 1 | 1.5 | 1
| 3.5 | 3 | 3 | 2 | 0.9 | 0.9
Overall Rework Factor | 0.3

## Data Conversions
Task | Design | Avante | UI | QA/Test | Avante Rework | UI Rework
Catalog Codes | 1 | 1
Quote Conversions to Saved Items | 3 | 2
Web Fields for Stock Items | 1 | 1.5
| 5 | 4.5 | 0 | 4 | 1.35 | 0
Overall Rework Factor | 0.3

## ShipUpchgs
Investigate options of how we can print shipping upcharges not included in pricing on forms:
- No detail/show below subtotal
- Show detail (ie, liftgate, export pallet) and amount

## Defs
Avante Programmers: Wayne, Joe, Janice @ 80% | 2.4
UI Programmers: Ed, Sal @ 80% | 1.6
Technical Designers: John, Judy @ 75% ; Jim, Cathy @ 25% | 2
QA/Test: Susan, Steve, Jim, Owen, Cathy, CE, Mktg

## AvanteRpts
Investigate what Avante Reports/Processes are using configurator files to extract data.
I am looking for a list of processes that will require changes when the BAGS/SHEETING/FURN, etc
product lines are combined into a single MOD product line. This means that criteria numbers
may change:
- Search IIPROCESS/BP/LDLIB/AVBP looking for CFQNA<13,x> extractions
- Search IIPROCESS/BP/LDLIB/AVBP looking for CFORDER<13,x> extractions
- Search IIPROCESS/BP/LDLIB/AVBP looking for CFBLDHDR<10,x> extractions

## Misc Avante
Investigate what changes will be needed for the new FOB CODE "CPU". I believe CPU (customer pickup)
should follow the rules for COL/3PB in that they have no freight implications. Be sure to check the
freight quote/freight$ calculation programs to make sure that CPU will not go through this logic.
Investigate what should happen with CPU credit card orders -- should they be handled like PPD?
Investigate how 'shipping notifications' could be sent to customers notifying them that their shipment
has been made:
- Timing - should this be done when updating Avante? What if shipment hasn’t left building yet?
- What email address to use?
- What if customer doesn't accept emails?
- Should notifications be sent for all shipments? CPU's?
Investigate/writeup design to only allow NS Made/Buy quotes to be entered via QUO4000. Is there an
easy way to disable the other selections BAGS/SHEETING/TUBING/FURN from the screens? Or should
we bypass the screens entirely and only allow NS as an item number in this screen?

## Open Questions
Originally we had a line item for Results on the Summary page. Having reviewed the Shop/Results area with Ed we combined all incomplete functions into one page called ShopWidget. Need to review with JP to be sure there is no missing functionality.