## Summary
Status as of 7/22/13
Task | Status | Design | Avante | UI | AV Rework | UI Rework | Ongoing QA
ShopWidget | In Progress | 7.7 | 31.5 | 15.1 | 12.45 | 4.53 | 16.98 | no macchi; database cleanup; ui bug fixes;
Saved Items | In Progress | 0 | 0 | 3.05 | 0 | 0.99 | 0.99
Order History | In Progress | 2 | 2 | 3.4 | 0.6 | 1.02 | 1.62
Saved Carts | In Progress | 3.5 | 3 | 2 | 0.9 | 1.05 | 1.95
Share Cart | In Progress | 2.3 | 3.9 | 4.1 | 1.17 | 1.23 | 2.4
Active Cart | In Progress | 19.9 | 19.1 | 19.2 | 5.73 | 6.9 | 12.63
Checkout | In Progress | 13.5 | 22 | 6 | 6.6 | 1.8 | 8.4
Avante | TBDesigned | 11 | 19 | 3 | 5.7 | 0.9 | 6.6
Data Conversions | INPROG | 10 | 11.5 | 0 | 3.45 | 0 | 3.45
Predictive Ordering | TBDesigned | 3 | 3 | 2 | 2 | 2 | 2 | incomplete design
My Account |  | 3 | 4 | 6 | 2 | 2 | 3 | JP
Exp/Twit/??? |  | 5 | 4 | 4 | 2 | 2 | 2 | JP
Pre Login Func |  | 2 | 3 | 1 | 2 | 2 | 3 | JP
Mktg/Fat Content |  | 8 | 4 | 8 | 3 | 3 | 3 | JP
Availability |  | 2 | 3 | 2 | 1 | 0 | 2 | need clarification on what actually happens
Freight |  | 1 | 1 | 1 | 1 | 1 | 1 | pretty much done
Price Breaks |  | 1 | 2 | 2 | 1 | 1 | 1 | no issues
Extended Desc |  | 1 | 1 | 1 | 1 | 1 | 2 | make sure design satisfies marketing reqs
Shared Item |  | 0.8 | 0 | 2 | 1 | 2 | 3 | no issues
Quick Add |  | 0 | 0 | 0 | 0 | 0 | 0 | included in Active Cart
Check Out |  | 9 | 15 | 9.5 | 4 | 2 | 5 | JP
Item Search |  | 1 | 1 | 1 | 1 | 1 | 1 | JP
Notifications |  | 3 | 4 | 4 | 2 | 2 | 2 | JP
CE Web Integration |  | 6 | 10 | 10 | 4 | 4 | 4 | ASK IF CE REQUEST SYSTEM IS INCLUDED IN THESE NUMBERS
#Days |  | 115.7 | 167 | 109.35 | 63.6 | 43.42 | 89.02
#Resources |  | 2 | 2.4 | 1.6 | 2.4 | 1.6 | Various
#Weeks |  | 11.668 | 14.0147 | 13.7667 | 5.398 | 5.5255 | Ongonig
Complete Date |  | 2013-10-26 16:13 | 2013-11-12 02:28 | 2013-11-10 08:49 | 2013-12-19 21:20 | 2013-12-19 01:06 | Pre-live
Dates as of Prev Week |  | 2013-10-23 | 2013-11-07 | 2013-11-04 | 2013-12-14 | 2013-12-13
Formulas:
Design = TODAY()+([Design, row above]*7)
Avante = TODAY()+([Avante, row above]*7)
UI = TODAY()+([UI, row above]*7)
AV Rework = [Avante]+([AV Rework, row above]*7)
UI Rework = [UI]+([UI Rework, row above]*7)

## ShopWidget
Task | Design |  |  | Avante |  |  | UI |  |  | Rework |  | QA |  | Status/Notes
| Days | Rem | Resp | Days | Rem | Resp | Days | Rem | Resp | Avante | UI
Status as of 7/22/13
Can We Make a Mod |  | 0 | JA | 5 | 0 | JC | 1 | 1 | ED |  |  |  |  | Waiting for Avante programming to complete - Can I make a MOD and Range Changes (Stock and Market Place)
Tableize Range Values |  | 0 | JA | 2 | 1 | JC
Quick Find Item | 0.5 | 0.5 | JBM | 0.5 | 0.5 | ?? | 0.5 | 0.5 | ED |  |  |  |  | Waiting for Preferences design - zip code logic - how should it work
Group Validations | [6 empty] | 1 | 1 | ED |  |  |  |  | Ed - #3 on list
Availability | 1 | 1 | JBM | 2 | 2 | WC | 5 | 5 | ED |  |  |  |  | Ed - #3 on list, PopUp, Sustitutions - quesiton on return from sub page, Data Validation
Create Quote-question/answer xref | 2 | 0 | JP | 1 | 0 | JM
Create Quote-"non" input answers | 0 | 0 | JP | 6 | 5 | JM | [7 empty] | ** added 4 days to create new common variables on 8/1
Create Quote-final update | 1 | 0 | JBM | 5 | 5 | JM | [7 empty] | Mostly there, some final design work needed.
MOD Item Pricing and Price Breaks |  |  | JA | 7 | 5 | WC
Marketplace Domestic Pricing |  |  | JP | 2 | 2 | WC
Marketplace Import Pricing |  |  | JP | 2 | 2 | WC
Share-Subject line expiration date | [6 empty] | 0.1 | 0.1 | SM
Save-Add location work | [6 empty] | 0.5 | 0.5 | SM
Save-Add my part number logic | [6 empty] | 0.5 | 0.5 | SM |  |  |  |  | waiting for technical design
Save-Save items to the database | 0.2 | 0.2 | JP |  |  | ??
Sheeting Gusset Type |  |  |  | 2 | 2 | JC | 2 | 2 | ED |  |  |  |  | Adding Slit gusset/Slit Center-diff UI handling. Wind question has been removed
Atlanta Production | 1 | 1 | JA | 3 | 3 | ?? | [6 empty] | ** | Design Hrs assume that David writes specs for mfg facility assignment & BS/SW Rule changes
Changing Existing Quotes | 5 | 5 | JA/JP | 4 | 4 | ?? | 4 | 4 | ?? |  |  |  | ** | Exp vs unexp/unconverted; reprice/new price; increment config; overlay saveditem
Zip Code Validation in Avante | 0 | 0 | JA/JP | 0 | 0 |  | 0.5 | 0.5 | [5 empty] | Hook up zip code validation
Total Days | 10.7 | 7.7 |  | 41.5 | 31.5 |  | 15.1 | 15.1 |  | 12.45 | 4.53 | 16.98 |  | ** Not Started - Needs Design and Programming - Hrs Estimated without Design
Overall Rework Factor | 0.3
Overall QA Factor | 0.3

## Saved Items
Task | Design |  |  | Avante |  |  | UI |  |  | Rework |  | QA |  | Status/Notes
| Days | Rem | Resp | Days | Rem | Resp | Days | Rem | Resp | Avante | UI
Status as of 7/22/13
Return the Saved items | 0 | 0 |  | 0 | 0 |  | 0.5 | 0.5 | SM
Return Filtering tags -location and product | 0 | 0 |  | 0 | 0 |  | 0.5 | 0.25 | SM
Finish Popup - html | 0 | 0 |  | 0 | 0 |  | 0.3 | 0.3 | SM
Filtering Functionality | [6 empty] | 1 | 1 | SM
Finish Grid | [6 empty] | 1 | 1 | SM
Returning Saved Item to Shop Widget |  |  | ?? |  |  | ?? |  |  | SM |  |  |  | **
Total Days | 0 | 0 |  | 0 | 0 |  | 3.3 | 3.05 |  | 0 | 0.99 | 0.99 |  | ** Not Started - Needs Design and Programming - Hrs Estimated without Design
Overall Rework Factor | 0.3
Overall QA Factor | 0.3

## Order History
Task | Design |  |  | Avante |  |  | UI |  |  | Rework |  | QA | Status/Notes
| Days | Rem | Resp | Days | Rem | Resp | Days | Rem | Resp | Avante | UI
Status as of 7/22/13
Modify results to handle master orders | 0.5 | 0.5 |  | 1 | 1 |  | 0.2 | 0.2
Complete Summary Popup | 1.5 | 1.5 |  | 1 | 1 |  | 3 | 3
Complete Tracking Popup for all Carriers | [6 empty] | 0.2 | 0.2 | SM
Total Days | 2 | 2 |  | 2 | 2 |  | 3.4 | 3.4 |  | 0.6 | 1.02 | 1.62 | ** Not Started - Needs Design and Programming - Hrs Estimated without Design
Overall Rework Factor | 0.3
Overall QA Factor | 0.3

## Saved Carts
Task | Design |  |  | Avante |  |  | UI |  |  | Rework |  | QA |  | Status/Notes
| Days | Rem | Resp | Days | Rem | Resp | Days | Rem | Resp | Avante | UI
Status as of 7/22/13
Activating a saved cart | 1 | 1 |  | 0.5 | 0.5 |  | 1 | 0 | ED
Handling working with someone else's cart | 1.5 | 1.5 |  | 1 | 1 |  | 1 | 1 |  |  |  |  | ** | Preferences
MOD items in Carts | 1 | 1 |  | 1.5 | 1.5 |  | 1 | 1 |  |  |  |  | **
Deleting Saved Carts | [6 empty] | 0.5 | 0 | [5 empty] | Can carts be deleted by anyone other than the user
Total Days | 3.5 | 3.5 |  | 3 | 3 |  | 3.5 | 2 |  | 0.9 | 1.05 | 1.95 |  | ** Not Started - Needs Design and Programming - Hrs Estimated without Design
Overall Rework Factor | 0.3
Overall QA Factor | 0.3

## Share Cart
Task | Design |  |  | Avante |  |  | UI |  |  | Rework |  | QA | Status/Notes
| Days | Rem | Resp | Days | Rem | Resp | Days | Rem | Resp | Avante | UI
Status as of 7/22/13
Build and Link to popup | 0.1 | 0.1 |  | 0 | 0 |  | 0.4 | 0.4 | ED
Build Top interface for To, CC, & Subject | 0.1 | 0.1 |  |  |  |  | 0.1 | 0.1 | ED
Handle logo swapping for customer sharing | 0.2 | 0.2 |  | 0.2 | 0.2 |  | 0.5 | 0.5 | ED |  |  |  | These numbers assume this has been essentially worked out for share items.
Return Data for MOD Items | 0.3 | 0.3 |  | 1.5 | 1.5 |  | 0.4 | 0.4 | ED
Build Price break display for Non customer sharing | 0.2 | 0.2 |  | 0.7 | 0.7 |  | 0.6 | 0.6 | ED
Build Price break drawer for markups. | 0.2 | 0.2 |  | 0.6 | 0.6 |  | 2 | 2 | ED
Saving Shared Cart Event | 1.2 | 1.2 |  | 0.9 | 0.9 |  | 0.1 | 0.1 | ED
Total Days | 2.3 | 2.3 |  | 3.9 | 3.9 |  | 4.1 | 4.1 |  | 1.17 | 1.23 | 2.4 | ** Not Started - Needs Design and Programming - Hrs Estimated without Design
Overall Rework Factor | 0.3
Overall QA Factor | 0.3

## Active Cart
Task | Design |  |  | Avante |  |  | UI |  |  | Rework |  | QA |  | Status/Notes
| Days | Rem | Resp | Days | Rem | Resp | Days | Rem | Resp | Avante | UI
Status as of 7/22/13
MOD item Descriptions | 1 | 1 |  | 1 | 1 |  | 0.5 | 0.5 | ED
Freight Dropdown | 0.1 | 0.1 |  | 0 | 0 |  | 0.3 | 0.3 | ED
Line Repricing | 1.5 | 1.5 |  | 0.4 | 0.4 |  | 0.6 | 0.6 | ED
Total Items | 0 | 0 |  | 0.3 | 0.3 |  | 0 | 0 | ED
Edit Qty | 0.3 | 0.3 |  | 0.2 | 0.2 |  | 0.8 | 0 | ED
Plate Upload / Display | 2 | 2 |  | 1 | 1 |  | 2.5 | 2.5 | ED
Repricing Clock | 0.2 | 0.2 |  | 0 | 0 |  | 0.3 | 0.3 | ED
Disabling Lines | 0.5 | 0.5 |  | 0 | 0 |  | 0.1 | 0.1 | ED
Replacing MOD items in Cart with new MOD items | 1.2 | 1.2 |  | 1.5 | 1.5 |  | 1.5 | 1.5 | ED
Delete Item Function | 0 | 0 |  | 0 | 0 |  | 0 | 0 | ED
Special CE Handling | 1.75 | 1.75 |  | 3 | 3 |  | 3 | 3 | ED
Pricebreak display | 0.75 | 0.75 |  | 2 | 2 |  | 3 | 1 | ED
Quick Add | 0 | 0 |  | 0 | 0 |  | 0 | 0 | ED
Returning Items for Cart display | 0.7 | 0.7 |  | 3 | 3 |  | 0.4 | 0.4 | ED
Saving & Naming the Cart | 0.4 | 0.4 |  | 0.2 | 0.2 |  | 0.5 | 0.5 | ED
Validating Cart Names, CPU, & Zip Code | 0.5 | 0.5 |  | 0.5 | 0.5 |  | 1.5 | 0.5 | ED |  |  |  |  | *waiting for rpc
MOD items in Carts | 1 | 1 |  | 2 | 2 |  | 3 | 3 | ED
Sharing Carts |  |  | ?? |  |  | ?? |  |  | ?? |  |  |  | **
Shipment Bundling | 8 | 8 |  | 4 | 4 |  | 5 | 5 |  |  |  |  | ** | this hasn't been included in other numbers
Total Days | 19.9 | 19.9 |  | 19.1 | 19.1 |  | 23 | 19.2 |  | 5.73 | 6.9 | 12.63 |  | ** Not Started - Needs Design and Programming - Hrs Estimated without Design
Overall Rework Factor | 0.3
Overall QA Factor | 0.3

## Checkout
Task | Design |  |  | Avante |  |  | UI |  |  | Rework |  | QA |  | Status/Notes
| Days | Rem | Resp | Days | Rem | Resp | Days | Rem | Resp | Avante | UI
Status as of 7/22/13
Activating a saved cart | 1 | 1 |  | 0.5 | 0.5 |  | 1 | 1
Handling working with someone else's cart | 1.5 | 1.5 |  | 1 | 1 |  | 1 | 1
MOD items in Carts | 1 | 1 |  | 1.5 | 1.5 |  | 1 | 1
Converting Quotes to Sales Orders | 4 | 4 | JA | 5 | 5 | ?? | [6 empty] | **
Creating Master/Sub Orders | 6 | 6 |  | 14 | 14 |  | 3 | 3 |  |  |  |  | ** | creating multiple orders
Total Days | 13.5 | 13.5 |  | 22 | 22 |  | 6 | 6 |  | 6.6 | 1.8 | 8.4 |  | ** Not Started - Needs Design and Programming - Hrs Estimated without Design
Overall Rework Factor | 0.3
Overall QA Factor | 0.3

## Avante
Task | Design |  |  | Avante |  |  | UI |  |  | Rework |  | QA |  | Status/Notes
| Days | Rem | Resp | Days | Rem | Resp | Days | Rem | Resp | Avante | UI
Status as of 7/22/13
Create MOD Configuration | 1 | 1 | JA | 3 | 3 | JA
Quote and Ack Forms | 3 | 3 | JA/JP | 3 | 3 | ?? | 3 | 3 | ?? |  |  |  | ** | No change to form layouts. Continue to use for NS quotes/orders & sample orders. Link from web to Avante for faxed ackn. Link from Avante to Web to re-send Order Ackn after changes. Add checkout shipping upcharges, - determine if we should show details or No Detail/show below subtotal. Investigate handling Master order numbers on optio forms.
Shipping Upcharges | 2 | 2 | JA | 3 | 3 | ?? | [6 empty] | ** | Inside Deliv,tailgate,liftgate and Export Pallet Charges -
Avante Rpts | 1 | 1 | JA | 2 | 2 | ?? | [6 empty] | ** | ***Due to configuration criteria changes/part# changes
Misc Avante Changes | 4 | 4 | JA | 8 | 8 | ?? | [6 empty] | ** | Incomplete List: ***QUO4000-only NS, ***New FOB Cd 'CPU', *** Shipping Notifications
CE Request System Interface |  |  | ?? |  |  | ?? |  |  | ?? |  |  |  | ** | Request Sys-new types/direction, multiple requests creation for bundling and multiple sessions
Total Days | 11 | 11 |  | 19 | 19 |  | 3 | 3 |  | 5.7 | 0.9 | 6.6 |  | ** Not Started - Needs Design and Programming - Hrs Estimated without Design
Overall Rework Factor | 0.3
Overall QA Factor | 0.3
***Investigate what Avante Reports/Processes are using configurator files to extract data.
I am looking for a list of processes that will require changes when the BAGS/SHEETING/FURN, etc
product lines are combined into a single MOD product line. This means that criteria numbers
may change:
- Search IIPROCESS/BP/LDLIB/AVBP looking for CFQNA<13,x> extractions
- Search IIPROCESS/BP/LDLIB/AVBP looking for CFORDER<13,x> extractions
- Search IIPROCESS/BP/LDLIB/AVBP looking for CFBLDHDR<10,x> extractions
***Investigate/writeup design to only allow NS Made/Buy quotes to be entered via QUO4000. Is there an
easy way to disable the other selections BAGS/SHEETING/TUBING/FURN from the screens? Or should
we bypass the screens entirely and only allow NS as an item number in this screen?
***Investigate how 'shipping notifications' could be sent to customers notifying them that their shipment
has been made:
- Timing - should this be done when updating Avante? What if shipment hasn’t left building yet?
- What email address to use?
- What if customer doesn't accept emails?
- Should notifications be sent for all shipments? CPU's?
Investigate what changes will be needed for the new FOB CODE "CPU". I believe CPU (customer pickup)
should follow the rules for COL/3PB in that they have no freight implications. Be sure to check the
freight quote/freight$ calculation programs to make sure that CPU will not go through this logic.
Investigate what should happen with CPU credit card orders -- should they be handled like PPD?

## Data Conversions
Task | Design |  |  | Avante |  |  | UI |  |  | Rework |  | QA |  | Status/Notes
| Days | Rem | Resp | Days | Rem | Resp | Days | Rem | Resp | Avante | UI
Status as of 7/22/13
Catalog Codes | 1 | 1 | JP | 1 | 1
Quote Conversions to Saved Items | 3 | 3 | JP | 2 | 2
Web Fields for Stock Items | 1 | 1 | JP | 1.5 | 1.5
Ashad Conversion | 5 | 5 | JA | 7 | 7 | ?? | 0 | 0 | N/A |  |  |  | ** | Conversion of existing config records to new prod line-purge unconverted configs
Total Days | 10 | 10 |  | 11.5 | 11.5 |  | 0 | 0 |  | 3.45 | 0 | 3.45 |  | ** Not Started - Needs Design and Programming - Hrs Estimated without Design
Overall Rework Factor | 0.3
Overall QA Factor | 0.3

## Open Questions
Originally we had a line item for Results on the Summary page. Having reviewed the Shop/Results area with Ed we combined all incomplete functions into one page called ShopWidget. Need to review with JP to be sure there is no missing functionality.

## Defs
Avante Programmers: Wayne, Joe, Janice @ 80% | 2.4
UI Programmers: Ed, Sal @ 80% | 1.6
Technical Designers: John, Judy @ 75% ; Jim, Cathy @ 25% | 2
QA/Test: Susan, Steve, Jim, Owen, Cathy, CE, Mktg