## Summary
Status as of 8/22/13
Task | Status | Design | Avante | UI | AV Rework | UI Rework | Ongoing QA
ShopWidget | In Progress | 15 | 16 | 35.6 | 19.35 | 11.43 | 30.78 | no macchi; database cleanup; ui bug fixes;
Saved Items | In Progress | 6 | 3.3 | 2.5 | 0.99 | 2.19 | 3.18
Order History | In Progress | 2 | 2 | 3.4 | 0.6 | 1.02 | 1.62
Saved Carts | In Progress | 1.5 | 1.8 | 1.3 | 0.54 | 0.84 | 1.38
Share Cart | In Progress | 4.3 | 4.4 | 6.6 | 1.32 | 1.98 | 3.3
Active Cart | In Progress | 11.6 | 23.1 | 19.1 | 6.93 | 8.25 | 15.18
Checkout | In Progress | 20.5 | 25.5 | 10 | 7.65 | 3 | 10.65
My Account | TBDesigned | 10 | 10 | 10 | 3 | 3 | 6
Avante | TBDesigned | 11 | 19 | 3 | 5.7 | 0.9 | 6.6
Data Conversions | TBDesigned | 10 | 11.5 | 0 | 3.45 | 0 | 3.45
Twitter Feed on page |  | 0 | 0 | 1 | 0 | 0 | 0 | "The Experience" not in first launch. Numbers are for twitter feed on page.
Pre Login Func |  | 0 | 0 | 0 | 0 | 0 | 0 | This functionality should be in the numbers of the pertinent sections
Mktg/Fat Content |  | 8 | 4 | 8 | 3 | 3 | 3 | These numbers are COMPLETE guesses. This line is to represent the "front page" information from the existing site.
CE Web Integration | TBDesigned | 16 | 16 | 17 | 4.8 | 5.1 | 9.9
Predictive Ordering | TBDesigned | 3 | 3 | 2 | 2 | 2 | 2 | incomplete design
Shared Item |  | 2 | 0 | 0 | 0 | 0 | 0 | This is complete however, handling FAX customers is still a problem. Needs to be discussed.
Notifications |  | 3 | 4 | 4 | 2 | 2 | 2 | A sysstem needs to be designed on what to tell customers about and how to let them customize what they are told about. For example, when their order ships, when someone empties their cart.
#Days |  | 123.9 | 143.6 | 123.5 | 61.33 | 44.71 | 99.04
|  | 2 | 2.4 | 1.6 | 2.4 | 1.6 | Various
#Weeks |  | 12.488 | 12.0647 | 15.5355 | 5.2088 | 5.6867 | Ongonig
Complete Date |  | 2026-11-01 09:59 | 2026-10-29 10:52 | 2026-11-22 17:58 | 2026-12-04 21:57 | 2027-01-01 13:20 | Pre-live
Dates as of Prev Week |  | 2013-11-13 | 2013-11-08 | 2013-11-22 | 2013-12-11 | 2013-12-26
Formulas:
Design = TODAY()+([Design, row above]*7)
Avante = TODAY()+([Avante, row above]*7)
UI = TODAY()+([UI, row above]*7)
AV Rework = [Avante]+([AV Rework, row above]*7)
UI Rework = [UI]+([UI Rework, row above]*7)

## CEWeb
Task | Design |  |  | Avante |  |  | UI |  |  | Rework |  | QA | Status/Notes
| Days | Rem | Resp | Days | Rem | Resp | Days | Rem | Resp | Avante | UI
Status as of 8/22/13
Spinning off multiple requests. | 3 | 3 | JA | 6 | 6 |  | 5 | 5 |  |  |  |  | How are we going to handle multiple requests per call.
"Impersonating" a contact. | 3 | 3 | JP | 1 | 1 |  | 4 | 4 |  |  |  |  | Having the CE rep working as someone else and tracking everything correctly.
Send CE to the Web at the right time. | 4 | 4 | JA/JP | 4 | 4 |  | 0 | 0 |  |  |  |  | This means not sending to the web other times.
Multiple Sessions??? | 7 | 3 | JP/ED | 0 | 0 |  | 5 | 5 |  |  |  |  | How will CE work if we cannot use multiple web sessions. Initial investigation is done and works in IE* and above, Crome, not Firefox
NEPB? | 3 | 3 | JA | 5 | 5 |  | 3 | 3
Total Days | 20 | 16 |  | 16 | 16 |  | 17 | 17 |  | 4.8 | 5.1 | 9.9 | ** Not Started - Needs Design and Programming - Hrs Estimated without Design
Overall Rework Factor | 0.3
Overall QA Factor | 0.3

## ShopWidget
Task | Design |  |  | Avante |  |  | UI |  |  | Rework |  | QA |  | Status/Notes
| Days | Rem | Resp | Days | Rem | Resp | Days | Rem | Resp | Avante | UI
Status as of 8/22/13
Cross Browser support | 2 | 2 | JP |  |  |  | 5 | 5 | ED |  |  |  |  | IE 8, & 9 do not work well for the site. We need to get the site to work in these browsers as well.
Can We Make a Mod |  | 0 | JA | 5 | 0 | JC | 1 | 1 | SM |  |  |  |  | The results show a message about "if you give us more info we can make this item as a MOD".
Tableize Range Values |  | 0 | JA | 2 | 0 | JC | [7 empty] | Pull data validations for Dimensions from a table instead of hard coding. Included widest range for stock/MOD.
Quick Find Item | 0.5 | 0.5 | JP | 0.5 | 0.5 | JP | 0.5 | 1 | ED |  |  |  |  | The box at the top of the site where the user enters a part number and finds it based on the characteristics of that item.
Group Validations | [6 empty] | 1 | 1 | ED |  |  |  |  | Calling required field validation by group. On find and on close of a group. IF the user never goes to a field, field validation never fires so group validation is needed.
Availability | 1 | 0 | JA | 4 | 2 | JC | 5 | 5 | ED |  |  |  | E - 2 | Returning options to display to user when clicking availability date on results. Avante est. options, UI displays in popup.
Create Quote-question/answer xref | 2 | 0 | JP | 1 | 0 | JM | [7 empty] | Need to create and reference SYSTBL to find answer variable based on question id/ avante index from configurator.
Create Quote-"non" input answers | 0 | 0 | JP | 6 | 0 | JM | [7 empty] | Combined with above.
Create Quote-final update | 1 | 0 | JBM | 5 | 2 | JM | [7 empty] | Created quote for simple config. Need to implement for MOD config. Added 3 days to remaining column
Quote Review |  | 2 | JA | [9 empty] | c-2 | Make sure quote is updated in a way that interfaces to all areas of Avante correctly.
Mod Item/Quote Number Xref | 1.5 | 0 | JA/JP | 3 | 0.5 | JM | [7 empty] | A way to connect MOD item number to quote numbers. We don't want MOD items to be the exact same thing as quotes due to repricing concerns.
MOD Item Pricing and Std Price Breaks |  | 0 | JA | 7 | 0 | WC | [7 empty] | Calculate a price for a given set of criteria, and also return the standard price breaks.
Marketplace Domestic Pricing |  | 0 | JP | 2 | 1 | WC | [7 empty] | Implementing marketplace pricing is different than the MOD pricing this is accounting for that.
Marketplace Import Pricing |  | 0 | JP | 2 | 1 | WC | [7 empty] | Same as above but implementing the Import pricing for marketplace.
Create Mod Prod line/Configuration | 6 | 0 | JA | [10 empty] | Create the MOD configruation for use in the new system
MOD item result wrapper | 1 | 0 | JA/JP | 6 | 1 | JC |  | 2 | [5 empty] | This includes all the programming needed to display MOD items in the results without creating a quote.
MOD Item result handling | 1.5 | 0.5 | JP | 4 | 0 |  | 3 | 3 | ED |  |  |  | e-4 | Hooking into Avante for changes on MOD Item lines. Like packout, quantidy, and Freight Options refresh the line.
Share-Subject line expiration date | [6 empty] | 0.1 | 0.1 | SM |  |  |  |  | add exp date to subject line for MOD item
Save-Add location work | [6 empty] | 0.5 | 0.5 | SM |  |  |  |  | user notification when a tag is added. Currently it highlights the line and fades. The spec shows a bubble placed next to it. Color is orange.
Save-Add my part number logic | [6 empty] | 0.5 | 0.5 | SM |  |  |  |  | waiting for technical design - time is based on mod only
Save-Save items to the database | 0.2 | 0 | JP |  |  | ??
Sheeting Gusset Type |  |  |  | 2 | 0 | JC | 2 | 2 | SM |  |  |  |  | Adding Slit gusset/Slit Center-diff UI handling. Wind question has been removed
Atlanta Production | 1 | 1 | JA | 3 | 3 | ?? | [6 empty] | ** | Design Hrs assume that David writes specs for mfg facility assignment & BS/SW Rule changes
Changing Existing Quotes | 5 | 5 | JA/JP | 4 | 4 | JM | 4 | 4 | ?? |  |  |  | ** | Pulling up a saved item and making changes. Exp vs unexp/unconverted; reprice/new price; increment config; overlay saveditem
Zip Code Validation in Avante | 0 | 0 | JA/JP | 0 | 0 |  | 0.5 | 0.5 | ED |  |  |  |  | Hook up zip code validation
MOD Item Repricing | 4 | 1 | JA/JP | 4 | 0 | WC | 2 | 2 | [5 empty] | Reprice MOD items while honoring original Resin Prices, etc.
User defined Price Break Handling | 2 | 2 | JP | 1 | 1 | WC | 4 | 4 | [5 empty] | Handle the customer entering a custom break quantity. On Avante this is different than standard break returning.
Extended Descriptions | 3 | 0 | JP | 3 | 0 |  | 0 | 0 | [5 empty] | Need Marketing Approval for the format and the approach.
CPU handling | [6 empty] | 4 | 1 | ED |  |  |  | i-1 | Handling the user wanting to pick up orders, CPU/Ship to dropdown and passing their choice to Avante.
Performance Optimizaion | [6 empty] | 3 | 1
Freight Dropdown | 1 | 1 | JP | 0 | 0 |  | 2 | 2 | [5 empty] | Repricing when freight option changes on the line for a MOD item.
Total Days | 32.7 | 15 |  | 64.5 | 16 |  | 38.1 | 35.6 |  | 19.35 | 11.43 | 30.78 |  | ** Not Started - Needs Design and Programming - Hrs Estimated without Design
Overall Rework Factor | 0.3
Overall QA Factor | 0.3

## Saved Items
Task | Design |  |  | Avante |  |  | UI |  |  | Rework |  | QA |  | Status/Notes
| Days | Rem | Resp | Days | Rem | Resp | Days | Rem | Resp | Avante | UI
Status as of 8/22/13
Return the Saved items | 0 | 0 |  | 0 | 0 |  | 0.5 | 0 | SM
Handling MOD items in this tab | 2 | 2 | JP |  |  |  | 2 | 2 | ?? |  |  |  | C-2, I-2 | Repricing lines, and changes to initial save popup.
Return Filtering tags -location and product | 0 | 0 |  | 0 | 0 |  | 0.5 | 0 | SM
Finish Popup - html | 0 | 0 |  | 0 | 0 |  | 0.3 | 0 | SM |  |  |  |  | share history for save item
Filtering Functionality |  |  |  | 0.3 | 0.3 | JP | 1 | 0 | SM |  |  |  |  | multi tag filtering needs to be fixed
Finish Grid |  |  |  | 1 | 1 | JM | 1 | 0 | SM |  |  |  |  | delete function has to be completed on Avante side
Returning Saved Item to Shop Widget | 5 | 4 | JP | 2 | 2 |  | 2 | 0.5 | SM |  |  |  | C-4 | Using quick find logic so some code reuse should happen.
Total Days | 7 | 6 |  | 3.3 | 3.3 |  | 7.3 | 2.5 |  | 0.99 | 2.19 | 3.18 |  | ** Not Started - Needs Design and Programming - Hrs Estimated without Design
Overall Rework Factor | 0.3
Overall QA Factor | 0.3

## Order History
Task | Design |  |  | Avante |  |  | UI |  |  | Rework |  | QA | Status/Notes
| Days | Rem | Resp | Days | Rem | Resp | Days | Rem | Resp | Avante | UI
Status as of 8/22/13
Modify results to handle master orders | 0.5 | 0.5 |  | 1 | 1 |  | 0.2 | 0.2
Complete Summary Popup | 1.5 | 1.5 |  | 1 | 1 |  | 3 | 3
Complete Tracking Popup for all Carriers | [6 empty] | 0.2 | 0.2 | SM
Total Days | 2 | 2 |  | 2 | 2 |  | 3.4 | 3.4 |  | 0.6 | 1.02 | 1.62 | ** Not Started - Needs Design and Programming - Hrs Estimated without Design
Overall Rework Factor | 0.3
Overall QA Factor | 0.3

## Saved Carts
Task | Design |  |  | Avante |  |  | UI |  |  | Rework |  | QA |  | Status/Notes
| Days | Rem | Resp | Days | Rem | Resp | Days | Rem | Resp | Avante | UI
Status as of 8/22/13
Activating a saved cart | 1 | 0 |  | 0.5 | 0.5 |  | 1 | 0 | ED
Handling working with someone else's cart | 1.5 | 1.5 |  | 1 | 1 |  | 1 | 1 | ED |  |  |  | ** | Preferences
Share count in Results |  |  |  | 0.3 | 0.3 | ?? | 0.3 | 0.3 | ED
Deleting Saved Carts | [6 empty] | 0.5 | 0 | ED |  |  |  |  | Can carts be deleted by anyone other than the user
Total Days | 2.5 | 1.5 |  | 1.8 | 1.8 |  | 2.8 | 1.3 |  | 0.54 | 0.84 | 1.38 |  | ** Not Started - Needs Design and Programming - Hrs Estimated without Design
Overall Rework Factor | 0.3
Overall QA Factor | 0.3

## Share Cart
Task | Design |  |  | Avante |  |  | UI |  |  | Rework |  | QA | Status/Notes
| Days | Rem | Resp | Days | Rem | Resp | Days | Rem | Resp | Avante | UI
Status as of 8/22/13
Build and Link to popup | 0.1 | 0.1 |  | 0 | 0 |  | 0.4 | 0.4 | ED
Build Top interface for To, CC, & Subject | 0.1 | 0.1 |  |  |  |  | 0.1 | 0.1 | ED
Handle logo swapping for customer sharing | 0.2 | 0.2 |  | 0.2 | 0.2 |  | 0.5 | 0.5 | ED |  |  |  | These numbers assume this has been essentially worked out for share items.
Return Data for MOD Items | 0.3 | 0.3 |  | 1.5 | 1.5 |  | 0.4 | 0.4 | ED
Build Price break display for Non customer sharing | 0.2 | 0.2 |  | 0.7 | 0.7 |  | 0.6 | 0.6 | ED
Build Price break drawer for markups. | 0.2 | 0.2 |  | 0.6 | 0.6 |  | 2 | 2 | ED
Saving Shared Cart Event | 1.2 | 1.2 |  | 0.9 | 0.9 |  | 0.1 | 0.1 | ED
Redisplay Shared Cart from Saved Carts | 2 | 2 | JP | 0.5 | 0.5 |  | 2.5 | 2.5
Total Days | 4.3 | 4.3 |  | 4.4 | 4.4 |  | 6.6 | 6.6 |  | 1.32 | 1.98 | 3.3 | ** Not Started - Needs Design and Programming - Hrs Estimated without Design
Overall Rework Factor | 0.3
Overall QA Factor | 0.3

## Active Cart
Task | Design |  |  | Avante |  |  | UI |  |  | Rework |  | QA |  | Status/Notes
| Days | Rem | Resp | Days | Rem | Resp | Days | Rem | Resp | Avante | UI
Status as of 8/22/13
MOD item Descriptions | 1 | 1 |  | 1 | 1 |  | 0.5 | 0.5 | ED
Freight Dropdown | 0.1 | 0.1 |  | 0 | 0 |  | 0.3 | 0.3 | ED
Line Repricing | 1.5 | 1.5 |  | 0.4 | 0.4 |  | 0.6 | 0.6 | ED
Total Items | 0 | 0 |  | 0.3 | 0.3 |  | 0 | 0 | ED
Edit Qty | 0.3 | 0 |  | 0.2 | 0.2 |  | 0.8 | 0 | ED
Plate Upload / Display | 2 | 2 |  | 3 | 3 |  | 4 | 4 | ED
Repricing Clock | 0.2 | 0.2 |  | 0 | 0 |  | 0.3 | 0.3 | ED
Disabling Lines | 0.5 | 0.5 |  | 0 | 0 |  | 0.1 | 0.1 | ED
Replacing MOD items in Cart with new MOD items | 1.2 | 1.2 |  | 1.5 | 1.5 |  | 1.5 | 1.5 | ED
Delete Item Function | 0 | 0 |  | 0 | 0 |  | 0 | 0 | ED
Special CE Handling | 1.75 | 1.75 |  | 3 | 3 |  | 3 | 3 | ED
Pricebreak display | 0.75 | 0.75 |  | 2 | 2 |  | 3 | 1 | ED
Quick Add | 0 | 0 |  | 0 | 0 |  | 0 | 0.2 | ED |  |  |  | i-.2 | Handling enter and setting focus back to item number box after add button.
Returning Items for Cart display | 0.7 | 0.7 |  | 3 | 3 |  | 0.4 | 0.4 | ED
Saving & Naming the Cart | 0.4 | 0.4 |  | 0.2 | 0.2 |  | 0.5 | 0.5 | ED
Validating Cart Names, CPU, & Zip Code | 0.5 | 0.5 |  | 0.5 | 0.5 |  | 1.5 | 0.5 | ED |  |  |  |  | *waiting for rpc
MOD items in Carts | 1 | 1 |  | 2 | 2 |  | 3 | 3 | ED
Sharing Carts | 2 | 0 | JP | 2 | 2 | ?? | 3 | 3 | ED |  |  |  | 2013-08-15 | **
New Cart with Prompts | 2 | 0 | JP | 2 | 2 |  | 3 | 0 | ED |  |  |  | 2013-08-15
Delete Cart with Prompts | 2 | 0 | JP | 2 | 2 |  | 2 | 0.2 | ED |  |  |  | 2013-08-15
Total Days | 17.9 | 11.6 |  | 23.1 | 23.1 |  | 27.5 | 19.1 |  | 6.93 | 8.25 | 15.18 |  | ** Not Started - Needs Design and Programming - Hrs Estimated without Design
Overall Rework Factor | 0.3
Overall QA Factor | 0.3

## Checkout
Task | Design |  |  | Avante |  |  | UI |  |  | Rework |  | QA |  | Status/Notes
| Days | Rem | Resp | Days | Rem | Resp | Days | Rem | Resp | Avante | UI
Status as of 8/22/13
Handling working with someone else's cart | 1.5 | 1.5 |  | 1 | 1 |  | 1 | 1
MOD items in Carts | 1 | 1 |  | 1.5 | 1.5 |  | 1 | 1
Converting Quotes to Sales Orders | 4 | 4 | JA | 5 | 5 | ?? | [6 empty] | **
Creating Master/Sub Orders | 6 | 6 |  | 14 | 14 |  | 3 | 3 |  |  |  |  | ** | creating multiple orders
Shipment Bundling | 8 | 8 |  | 4 | 4 |  | 5 | 5 |  |  |  |  | ** | this hasn't been included in other numbers
Total Days | 20.5 | 20.5 |  | 25.5 | 25.5 |  | 10 | 10 |  | 7.65 | 3 | 10.65 |  | ** Not Started - Needs Design and Programming - Hrs Estimated without Design
Overall Rework Factor | 0.3
Overall QA Factor | 0.3

## Avante
Task | Design |  |  | Avante |  |  | UI |  |  | Rework |  | QA |  | Status/Notes
| Days | Rem | Resp | Days | Rem | Resp | Days | Rem | Resp | Avante | UI
Status as of 8/22/13
Create MOD Configuration | 1 | 1 | JA | 3 | 3 | JA
Quote and Ack Forms | 3 | 3 | JA/JP | 3 | 3 | ?? | 3 | 3 | ?? |  |  |  | ** | No change to form layouts. Continue to use for NS quotes/orders & sample orders. Link from web to Avante for faxed ackn. Link from Avante to Web to re-send Order Ackn after changes. Add checkout shipping upcharges, - determine if we should show details or No Detail/show below subtotal. Investigate handling Master order numbers on optio forms.
Shipping Upcharges | 2 | 2 | JA | 3 | 3 | ?? | [6 empty] | ** | Inside Deliv,tailgate,liftgate and Export Pallet Charges -
Avante Rpts | 1 | 1 | JA | 2 | 2 | ?? | [6 empty] | ** | ***Due to configuration criteria changes/part# changes
Misc Avante Changes | 4 | 4 | JA | 8 | 8 | ?? | [6 empty] | ** | Incomplete List: ***QUO4000-only NS, ***New FOB Cd 'CPU', *** Shipping Notifications
CE Request System Interface |  |  | ?? |  |  | ?? |  |  | ?? |  |  |  | ** | Request Sys-new types/direction, multiple requests creation for bundling and multiple sessions
Total Days | 11 | 11 |  | 19 | 19 |  | 3 | 3 |  | 5.7 | 0.9 | 6.6 |  | ** Not Started - Needs Design and Programming - Hrs Estimated without Design
Overall Rework Factor | 0.3
Overall QA Factor | 0.3
***Investigate what Avante Reports/Processes are using configurator files to extract data.
I am looking for a list of processes that will require changes when the BAGS/SHEETING/FURN, etc
product lines are combined into a single MOD product line. This means that criteria numbers
may change:
- Search IIPROCESS/BP/LDLIB/AVBP looking for CFQNA<13,x> extractions
- Search IIPROCESS/BP/LDLIB/AVBP looking for CFORDER<13,x> extractions
- Search IIPROCESS/BP/LDLIB/AVBP looking for CFBLDHDR<10,x> extractions
***Investigate/writeup design to only allow NS Made/Buy quotes to be entered via QUO4000. Is there an
easy way to disable the other selections BAGS/SHEETING/TUBING/FURN from the screens? Or should
we bypass the screens entirely and only allow NS as an item number in this screen?
***Investigate how 'shipping notifications' could be sent to customers notifying them that their shipment
has been made:
- Timing - should this be done when updating Avante? What if shipment hasn’t left building yet?
- What email address to use?
- What if customer doesn't accept emails?
- Should notifications be sent for all shipments? CPU's?
Investigate what changes will be needed for the new FOB CODE "CPU". I believe CPU (customer pickup)
should follow the rules for COL/3PB in that they have no freight implications. Be sure to check the
freight quote/freight$ calculation programs to make sure that CPU will not go through this logic.
Investigate what should happen with CPU credit card orders -- should they be handled like PPD?

## Data Conversions
Task | Design |  |  | Avante |  |  | UI |  |  | Rework |  | QA |  | Status/Notes
| Days | Rem | Resp | Days | Rem | Resp | Days | Rem | Resp | Avante | UI
Status as of 8/22/13
Catalog Codes | 1 | 1 | JP | 1 | 1
Quote Conversions to Saved Items | 3 | 3 | JP | 2 | 2
Web Fields for Stock Items | 1 | 1 | JP | 1.5 | 1.5
Ashad Conversion | 5 | 5 | JA | 7 | 7 | ?? | 0 | 0 | N/A |  |  |  | ** | Conversion of existing config records to new prod line-purge unconverted configs
Total Days | 10 | 10 |  | 11.5 | 11.5 |  | 0 | 0 |  | 3.45 | 0 | 3.45 |  | ** Not Started - Needs Design and Programming - Hrs Estimated without Design
Overall Rework Factor | 0.3
Overall QA Factor | 0.3

## MyAccount
Task | Design |  |  | Avante |  |  | UI |  |  | Rework |  | QA | Status/Notes
| Days | Rem | Resp | Days | Rem | Resp | Days | Rem | Resp | Avante | UI
Status as of 8/22/13
Complete This Area | 10 | 10 |  | 10 | 10 |  | 10 | 10
Total Days | 10 | 10 |  | 10 | 10 |  | 10 | 10 |  | 3 | 3 | 6 | ** Not Started - Needs Design and Programming - Hrs Estimated without Design
Overall Rework Factor | 0.3
Overall QA Factor | 0.3

## Open Questions
Originally we had a line item for Results on the Summary page. Having reviewed the Shop/Results area with Ed we combined all incomplete functions into one page called ShopWidget. Need to review with JP to be sure there is no missing functionality.

## Defs
Avante Programmers: Wayne, Joe, Janice @ 80% | 2.4
UI Programmers: Ed, Sal @ 80% | 1.6
Technical Designers: John, Judy @ 75% ; Jim, Cathy @ 25% | 2
QA/Test: Susan, Steve, Jim, Owen, Cathy, CE, Mktg