## Summary
Status as of 10.24.13
Task | Status | Design | Avante | UI | AV Rework | UI Rework | Ongoing QA
ShopWidget | In Progress | 0 | 0 | 0 | 17.49 | 8.602 | 0 | no macchi; database cleanup; ui bug fixes;
Saved Items | In Progress | 0 | 0 | 0 | 0 | 0 | 0
Order History | In Progress | 0 | 0 | 0 | 0 | 0 | 0
Saved Carts | In Progress | 0 | 0 | 0 | 0 | 0 | 0
Share Cart | In Progress | 0 | 0 | 0 | 0 | 0 | 0
Active Cart | In Progress | 0 | 0 | 0 | 0 | 0 | 0
Checkout | In Progress | 15.5 | 12.3 | 14.7 | 9.96 | 9.3 | 19.26
My Account | TBDesigned | 10 | 10 | 10 | 3 | 3 | 6
Avante | TBDesigned | 13 | 16 | 9 | 6 | 2.7 | 8.7
Data Conversions | TBDesigned | 9 | 8 | 0 | 3.45 | 0 | 3.45
Twitter Feed on page |  | 0 | 0 | 1 | 0 | 0 | 0 | "The Experience" not in first launch. Numbers are for twitter feed on page.
Pre Login Func |  | 0 | 0 | 0 | 0 | 0 | 0 | This functionality should be in the numbers of the pertinent sections
Mktg/Fat Content |  | 8 | 4 | 8 | 3 | 3 | 3 | These numbers are COMPLETE guesses. This line is to represent the "front page" information from the existing site.
CE Web Integration | TBDesigned | 16 | 16 | 17 | 4.8 | 5.1 | 9.9
Predictive Ordering | TBDesigned | 3 | 3 | 2 | 2 | 2 | 2 | incomplete design
Shared Item |  | 2 | 0 | 0 | 0 | 0 | 0 | This is complete however, handling FAX customers is still a problem. Needs to be discussed.
Notifications |  | 3 | 4 | 4 | 2 | 2 | 2 | A system needs to be designed on what to tell customers about and how to let them customize what they are told about. For example, when their order ships, when someone empties their cart.
#Days |  | 79.5 | 73.3 | 65.7 | 51.7 | 35.702 | 54.31
|  | 2 | 2.4 | 1.6 | 2.4 | 1.6 | Various
#Weeks |  | 8.048 | 6.2063 | 8.3105 | 4.4063 | 4.5607 | Ongonig
Complete Date |  | 2026-10-01 08:04 | 2026-09-18 10:40 | 2026-10-03 04:10 | 2026-10-19 06:56 | 2026-11-04 02:22 | Pre-live
Dates as of Prev Week |  | 2014-02-04 | 2014-01-21 | 2014-02-22 | 2014-02-27 | 2014-04-09
Formulas:
Design = TODAY()+([Design, row above]*7)
Avante = TODAY()+([Avante, row above]*7)
UI = TODAY()+([UI, row above]*7)
AV Rework = [Avante]+([AV Rework, row above]*7)
UI Rework = [UI]+([UI Rework, row above]*7)

## CEWeb
Task | Design |  |  | Avante |  |  | UI |  |  | Rework |  | QA | Status/Notes
| Days | Rem | Resp | Days | Rem | Resp | Days | Rem | Resp | Avante | UI
Status as of 10.24.13
Spinning off multiple requests. | 3 | 3 | JA | 6 | 6 |  | 5 | 5 |  |  |  |  | How are we going to handle multiple requests per call.
"Impersonating" a contact. | 3 | 3 | JP | 1 | 1 |  | 4 | 4 |  |  |  |  | Having the CE rep working as someone else and tracking everything correctly.
Send CE to the Web at the right time. | 4 | 4 | JA/JP | 4 | 4 |  | 0 | 0 |  |  |  |  | This means not sending to the web other times.
Multiple Sessions??? | 7 | 3 | JP/ED | 0 | 0 |  | 5 | 5 |  |  |  |  | How will CE work if we cannot use multiple web sessions. Initial investigation is done and works in IE* and above, Crome, not Firefox
NEPB? | 3 | 3 | JA | 5 | 5 |  | 3 | 3
Total Days | 20 | 16 |  | 16 | 16 |  | 17 | 17 |  | 4.8 | 5.1 | 9.9 | ** Not Started - Needs Design and Programming - Hrs Estimated without Design
Overall Rework Factor | 0.3
Overall QA Factor | 0.3

## ShopWidget
Task | Design |  |  | Avante |  |  | UI |  |  | Rework |  | QA | Status/Notes
| Days | Rem | Resp | Days | Rem | Resp | Days | Rem | Resp | Avante | UI
Status as of 10.24.13
Total Days | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | ** Not Started - Needs Design and Programming - Hrs Estimated without Design
Overall Rework Factor | 0.22
Overall QA Factor | 0.3

## Saved Items
Task | Design |  |  | Avante |  |  | UI |  |  | Rework |  | QA | Status/Notes
| Days | Rem | Resp | Days | Rem | Resp | Days | Rem | Resp | Avante | UI
Status as of 10.24.13
Total Days | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | ** Not Started - Needs Design and Programming - Hrs Estimated without Design
Overall Rework Factor | 0.3
Overall QA Factor | 0.3

## Order History
Task | Design |  |  | Avante |  |  | UI |  |  | Rework |  | QA | Status/Notes
| Days | Rem | Resp | Days | Rem | Resp | Days | Rem | Resp | Avante | UI
Status as of 10.24.13
Total Days | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | ** Not Started - Needs Design and Programming - Hrs Estimated without Design
Overall Rework Factor | 0.3
Overall QA Factor | 0.3

## Saved Carts
Task | Design |  |  | Avante |  |  | UI |  |  | Rework |  | QA | Status/Notes
| Days | Rem | Resp | Days | Rem | Resp | Days | Rem | Resp | Avante | UI
Status as of 10.24.13
Total Days | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | ** Not Started - Needs Design and Programming - Hrs Estimated without Design
Overall Rework Factor | 0.3
Overall QA Factor | 0.3

## Share Cart
Task | Design |  |  | Avante |  |  | UI |  |  | Rework |  | QA | Status/Notes
| Days | Rem | Resp | Days | Rem | Resp | Days | Rem | Resp | Avante | UI
Status as of 10.24.13
Total Days | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | ** Not Started - Needs Design and Programming - Hrs Estimated without Design
Overall Rework Factor | 0.3
Overall QA Factor | 0.3

## Active Cart
Task | Design |  |  | Avante |  |  | UI |  |  | Rework |  | QA | Status/Notes
| Days | Rem | Resp | Days | Rem | Resp | Days | Rem | Resp | Avante | UI
Status as of 10.24.13
Total Days | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | ** Not Started - Needs Design and Programming - Hrs Estimated without Design
Overall Rework Factor | 0.3
Overall QA Factor | 0.3
| 17.7 |  |  | 23.6 |  |  | 30.5

## Checkout
Task | Design |  |  | Avante |  |  | UI |  |  | Rework |  | QA |  | Status/Notes
| Days | Rem | Resp | Days | Rem | Resp | Days | Rem | Resp | Avante | UI
Status as of 10.24.13
Handling working with someone else's cart | 1.5 | 1.5 |  | 1 | 1 |  | 1 | 1
MOD items in Carts | 0 | 0 |  | 0 | 0 |  | 0 | 0 | [5 empty] | Duplicate line from Active Cart Sheet
Converting Quotes to Sales Orders | 4 | 0 | JA | 5 | 0.1 | ?? | [6 empty] | **
Creating Master/Sub Orders | 6 | 6 |  | 14 | 5 |  | 3 | 3 |  |  |  |  | ** | creating multiple orders
Shipment Bundling | 8 | 8 |  | 5 | 3 |  | 5 | 2.5 |  |  |  |  | ** | this hasn't been included in other numbers
Revert to standard SYS0123 |  |  |  | 2 | 0 | WC | [7 empty] | Time required to use standard Avante update routine.
Addresses - Return Customer Data |  |  |  | 1 | 0 | JP | [7 empty] | Return customers based on selection
Overall - Validate Data |  |  |  | 4 | 2 | [8 empty] | Validate address data for new ship-to location, establish fields that need to be defined, and establish validations. Addnamed parameters and update the shopping cart for each step.
Summary | [6 empty] | 3 | 1
Giving | [6 empty] | 3 | 0
Checkout - Overall-Cleanup Frame | [6 empty] | 3 | 0
Checkout - Overall-Connect Steps with line.
Checkout - Overall-Return to cart link | [6 empty] | 0.1 | 0.1
Checkout - Overall-Add order Total Panel | [6 empty] | 0.3 | 0
Checkout - Overall-Super user setup |  |  |  | 0.4 | 0.4 |  | 1 | 1
Checkout - Addresses-Build the content of the page | [6 empty] | 1 | 0
Checkout - Addresses-Handle Bill to changing | [6 empty] | 1.5 | 0
Checkout - Addresses-Add Criteria to RPC$CUSTOMER_GETBYFILTER | [7 empty] | 0
Checkout - Addresses-Handle switching shiptos |  |  |  | 0.5 | 0.5 |  | 1.5 | 0
Checkout 3 - Labeling-Build the Content of the page | [6 empty] | 1 | 1
Checkout 3 - Labeling-Enable correct Label options. | [6 empty] | 0.3 | 0.3
Checkout 3 - Labeling-Build Label Image | [6 empty] | 2 | 2
Checkout 3 - Labeling-Handle Adding Label comment | [6 empty] | 0.4 | 0.4
Checkout 3 - Labeling-Handle Third party label | [6 empty] | 0.4 | 0.4
Checkout 4 - Payment-Validate PO and Dropship PO fields. For duplication and req'd. | [6 empty] | 0.5 | 0.5
Checkout 4 - Payment-List of orders based on Duplicate PO #. |  |  |  | 0.3 | 0.3 |  | 3 | 1.5
Total Days | 19.5 | 15.5 |  | 33.2 | 12.3 |  | 31 | 14.7 |  | 9.96 | 9.3 | 19.26 |  | ** Not Started - Needs Design and Programming - Hrs Estimated without Design
Overall Rework Factor | 0.3
Overall QA Factor | 0.3

## Miscellaneous
Task | Design |  |  | Avante |  |  | UI |  |  | Rework |  | QA |  | Status/Notes
| Days | Rem | Resp | Days | Rem | Resp | Days | Rem | Resp | Avante | UI
Status as of 10.24.13
Quote and Ack Forms | 3 | 3 | JA/JP | 3 | 3 | ?? | 3 | 3 | ?? |  |  |  | ** | No change to form layouts. Continue to use for NS quotes/orders & sample orders. Link from web to Avante for faxed ackn. Link from Avante to Web to re-send Order Ackn after changes. Add checkout shipping upcharges, - determine if we should show details or No Detail/show below subtotal. Investigate handling Master order numbers on optio forms. 10/8-possible layout change for bundling detail?
Shipping Upcharges | 2 | 2 | JA | 3 | 3 | ?? | [6 empty] | ** | Inside Deliv,tailgate,liftgate and Export Pallet Charges -
Avante Config Rpts and Logic | 1 | 1 | JA | 2 | 2 | ?? | [6 empty] | ** | ***Due to configuration criteria changes/part# changes
Misc Avante Changes | 4 | 4 | JA | 8 | 8 | ?? | [6 empty] | ** | Incomplete List: ***QUO4000-only NS, ***New FOB Cd 'CPU', *** Shipping Notifications; 10/23 added c/e request system alert messages for contact/cust/sales org; 10/26-added SOP4000 master order# logic
Master Buyer Functionality | 3 | 3 |  | 4 | 0 |  | 6 | 0.5 | [5 empty] | Add any new preferecne fields and supportive data selects, etc for various Master Buyer functions.
Total Days | 13 | 13 |  | 20 | 16 |  | 9 | 3.5 |  | 6 | 2.7 | 8.7 |  | ** Not Started - Needs Design and Programming - Hrs Estimated without Design
Overall Rework Factor | 0.3
Overall QA Factor | 0.3
***Investigate what Avante Reports/Processes are using configurator files to extract data.
I am looking for a list of processes that will require changes when the BAGS/SHEETING/FURN, etc
product lines are combined into a single MOD product line. This means that criteria numbers
may change:
- Search IIPROCESS/BP/LDLIB/AVBP looking for CFQNA<13,x> extractions
- Search IIPROCESS/BP/LDLIB/AVBP looking for CFORDER<13,x> extractions
- Search IIPROCESS/BP/LDLIB/AVBP looking for CFBLDHDR<10,x> extractions
***Investigate/writeup design to only allow NS Made/Buy quotes to be entered via QUO4000. Is there an
easy way to disable the other selections BAGS/SHEETING/TUBING/FURN from the screens? Or should
we bypass the screens entirely and only allow NS as an item number in this screen?
***Investigate how 'shipping notifications' could be sent to customers notifying them that their shipment
has been made:
- Timing - should this be done when updating Avante? What if shipment hasn’t left building yet?
- What email address to use?
- What if customer doesn't accept emails?
- Should notifications be sent for all shipments? CPU's?
Investigate what changes will be needed for the new FOB CODE "CPU". I believe CPU (customer pickup)
should follow the rules for COL/3PB in that they have no freight implications. Be sure to check the
freight quote/freight$ calculation programs to make sure that CPU will not go through this logic.
Investigate what should happen with CPU credit card orders -- should they be handled like PPD?

## Data Conversions
Task | Design |  |  | Avante |  |  | UI |  |  | Rework |  | QA |  | Status/Notes
| Days | Rem | Resp | Days | Rem | Resp | Days | Rem | Resp | Avante | UI
Status as of 10.24.13
Catalog Codes | 1 | 1 | JP | 1 | 1
Quote Conversions to Saved Items | 3 | 3 | JP | 2 | 2
Web Fields for Stock Items | 1 | 1 | JP | 1.5 | 0 | WC | [7 empty] | Update all new fields to support stock searches
Ashad Conversion | 5 | 4 | JA | 7 | 5 | JC | 0 | 0 | N/A |  |  |  | ** | Conversion of existing config records to new prod line-purge unconverted configs
Total Days | 10 | 9 |  | 11.5 | 8 |  | 0 | 0 |  | 3.45 | 0 | 3.45 |  | ** Not Started - Needs Design and Programming - Hrs Estimated without Design
Overall Rework Factor | 0.3
Overall QA Factor | 0.3

## MyAccount
Task | Design |  |  | Avante |  |  | UI |  |  | Rework |  | QA | Status/Notes
| Days | Rem | Resp | Days | Rem | Resp | Days | Rem | Resp | Avante | UI
Status as of 10.24.13
Complete This Area | 10 | 10 |  | 10 | 10 |  | 10 | 10
Total Days | 10 | 10 |  | 10 | 10 |  | 10 | 10 |  | 3 | 3 | 6 | ** Not Started - Needs Design and Programming - Hrs Estimated without Design
Overall Rework Factor | 0.3
Overall QA Factor | 0.3

## Open Questions
Originally we had a line item for Results on the Summary page. Having reviewed the Shop/Results area with Ed we combined all incomplete functions into one page called ShopWidget. Need to review with JP to be sure there is no missing functionality.

## Defs
Avante Programmers: Wayne, Joe, Janice @ 80% | 2.4
UI Programmers: Ed, Sal @ 80% | 1.6
Technical Designers: John, Judy @ 75% ; Jim, Cathy @ 25% | 2
QA/Test: Susan, Steve, Jim, Owen, Cathy, CE, Mktg

## ToDo
Tab | LookUp Ref# | Date Added | Programming Task | Designer | Programmer | Status
|  |  | Bundling - Shipping and Packaging work – logic for Ship Instructions, Ship Paid By, and Ship Via |  |  | 0
|  |  | Order History Summary | John |  | 0
|  |  | Stock & MOD Price Overrides (Misc$) |  |  | 0
|  |  | Report for go-live that lists pallet info that can be entered as preferences |  |  | 0
|  |  | Order Creation -Upcharges | Judy |  | 0
|  |  | Order Creation - Special Instructions / Comments | Judy |  | 0
|  |  | Order Creation - Credit Hold - put entire master order on hold (all sub-orders) |  |  | 0
|  |  | Creation of c/e request(s) *** this logic applies to other areas of site, not just orders |  |  | 0
|  |  | Price Discrepancies - flagging in cart, different order acknowledgement, put order(s) on hold, auto-release for onhold orders |  |  | 0
|  |  | Conversion Program - for customer comments that will become preferences |  |  | 0
|  |  | Conversion Program - load master order# data for existing orders (after purging old data) |  |  | 0
|  |  | Conversion Program - Creating Saved Items from Ashads |  |  | 0
|  |  | Preference-related logic for defaults (ie, cradlepacked, no verbal p/o, no verbal order) |  |  | 0
|  |  | Atlanta Production Rules |  |  | 0
|  |  | Avante - Shipping Notifications |  |  | 0
|  |  | Avante - Invoice Form: add upcharges below subtotal |  |  | 0
|  |  | Contract Pricing - still on spreadsheet - move to Phase II? |  |  | 0
Shop Widget | 1-0 | 2013-11-25 | Avante - Changes for Rolls, Rolls Cradle packed, Rolls Boxed | Judy |  | 1
| 1-1 |  | Modify Packaging Group Description | Judy |  | 1
| 1-2 |  | Modify Packaging Default Value | Judy |  | 1
Saved Items and Checkout | 2-0 | 2013-11-25 | New customer part number logic (including cart logic hover over our part# to see customer part#) |  |  | 1
| 2-1 |  | Avante - Update Existing Mainenance Program for 2 lines of descriptions |  |  | 0
| 2-2 |  | UI - Update Checkout Label View | John | Francisco | 2
| 2-3 |  | UI - Update Saved Items View | John | Sal | 2
| 2-4 |  | UI - code retrieval of customer items from Database | John |  | 1
| 2-5 |  | UI - code save of customer items to Database | John |  | 1
| 2-6 |  | DB - RPC to return customer items to web |  |  | 0
| 2-7 |  | DB - RPC to save customer items to database |  |  | 0
| 2-8 |  | Conversion - convert MOD items to new format for custom customer part numbers |  |  | 0
| 2-9 |  | DB - Customer Item Number Search from the Shop Widget
| 2-10 |  | Avante - Modify the Customer Item Number upload for new format and to overwrite rather than delete |  |  | 0
| 2-11 |  | How to handle duplicate customer names/add customer nbr to tag xref for cust part# assignment??? |  |  | 0
Saved Items | 3-0 | 2013-11-25 | Change the saved items record key (from contact to billto customer) and effects on completed programming | John |  | 1
| 3-1 |  | DB - Create file to hold Mod Item Specification by Bill-to | John |  | 1
| 3-2 |  | DB - Modify File Structure for Contact Item information | John |  | 1
| 3-3 |  | DB - RPC$MODITEM_CREATE - Update saving of MOD items | John |  | 1
| 3-4 |  | DB - RPC$CONTACTITEM_DELETE - Delete Billto Level data as well? | John |  | 1
| 3-5 |  | DB - RPC$CONTACTITEM_GETBYFILTER - Pull information from billto level & Contact level | John |  | 1
| 3-6 |  | DB - RPC$CONTACTITEM_GETBYID - Pull Information from billto level & Contact Level | John |  | 1
| 3-7 |  | DB - RPC$CONTACTITEM_SAVE | John |  | 1
| 3-8 |  | DB - RPC$ITEMTAG_GETBYFILTER | John
| 3-9 |  | DB - RPC$ITEMTAG_GETBYFILTER2 | John
| 3-10 |  | DB - RPC$ITEMTAG_SELECT | John
| 3-11 |  | DB - RPC$QUOTEITEM_GETBYSAVEDITEM | John
| 3-12 |  | DB - RPC$SHAREDITEM_GETBYFILTER | John
| 3-13 |  | DB - RPC$SHAREDITEM_SAVE | John
| 3-14 |  | DB - RPC$SHIPMENTBUNDLING_GETBYFILTER | John
LOGIN | 4-0 |  | Delete expired carts after ‘x’ days old | John |  | 1
| 4-1 |  | Write Last Activity Date to SHOPPINGCART.USR | John
| 4-2 |  | Delete old carts upon user validation based on xxx days old | John
| 4-3 |  | Does purge of carts delete the history of sharing as well
Checkout | 5-0 |  | Duplicate P/O display in Checkout | John |  | 1
| 5-1 |  | Create Pop-up for Duplicate PO numbers | John
| 5-2 |  | Handle user response to pop-up | John
Checkout | 6-0 |  | Order Creation | Judy |  | 1
| 6-1 |  | Determine How To Create Orders from Bundles | CJJ |  | 0
| 6-2 |  | Create orders from Bundles | Judy
| 6-3 |  | Order Creation - Ship With Logic (ship with comment) | Judy |  | 1
| 6-4 |  | Order Creation - Setting FOB Code for Customer Pickup | Judy |  | 1
| 6-5 |  | ‘Must Ship Today Flag’ setting on order based on time of day and bundle ship date | Judy |  | 1
| 6-6 |  | Order source when ce enters order | Judy | Wayne | 2
| 6-7 |  | Creating a new Shipto Customer | Judy | Wayne | 2
| 6-8 |  | Write cart name to SOHDR.USR | Judy | Wayne | 2
| 6-9 |  | Move MOD ‘ashad’ comments and order shipping preference comments forward to new order | Judy |  | 5
| 6-10 |  | Pallet Type (from shipping preferences) must be added as a w/o comment for MOD Orders | Judy |  | 1
Checkout | 7-0 |  | Checkout - Labeling | John |  | 1
| 7-1 |  | Validations - customer part number required, third party, Brandit customer setup
| 7-2 |  | Udate Labeling to SHOPPINGCART.USR
| 7-3 |  | Interface with Bartender to generate label images
| 7-4 |  | Set up paging to step from label to label.
| 7-5 |  | interface with Saved items popup.
| 7-6 |  | refresh label image as needed.
| 7-7 |  | Retrieve customer part number information.
| 7-8 |  | Return Brandit information as customer object properties
| 7-9 |  | Show correct options (label type on top, check box options below, actual part numbers)
Checkout | 8-0 |  | Checkout - Addresses
| 8-1 |  | Check Create Order F2 validations - only diff is that zip code is entered, then city/state is defaulted from ZIPCODE.USR | Judy |  | 1
| 8-2 |  | Update SHOPPINGCART.USR | Judy | Wayne | 2
| 8-3 |  | Verify that ship-to zip matches cart zip (in case of zip code change) | Judy |  | 1
Checkout | 9-0 |  | Checkout - Payment
| 9-1 |  | Check Create Order F2 validations **done-only diff is CC Name s/b reqd & Exp Date shouldn't default - UI?? | Judy |  | 1
| 9-2 |  | Make sure all validations from existing website are in new website (UI?)
| 9-3 |  | Redign Payment View to new specifications
Checkout | 10-0 |  | Checkout - Giving
| 10-1 |  | Check Create Order F2 validations - *** NO GIVING SCREEN ON AVANTE SO NOT NEEDED - | Judy |  | 1
| 10-2 |  | Bypass if CE | John |  | 1
| 10-3 |  | Update SHOPPINGCART.USR | Judy | Wayne | 2
Checkout | 11-0 |  | Checkout - Bundling View
| 11-1 |  | Validations - ie ship via, fob code, shipping preferences, ship date | Judy |  | 1
| 11-2 |  | Update Bundling to SHOPPINGCART.USR | Judy |  | 1
| 11-3 |  | Validate ‘ship date’ – allow ‘x’ days in future | Judy |  | 1
Active Cart | 12-0 |  | Cart - Handle Price expiration of MOD items
| 12-1 |  | Create a view for Mod Items
| 12-2 |  | Establish the state of the view and show correct clock icon
| 12-3 |  | Disable Controls for expired items
| 12-4 |  | Create a new quote from expired quote and save new quote to SHOPPINGCART.USR and remove old
Active Cart | 13-0 |  | Cart - Repricing MOD items in the cart.
| 13-1 |  | Call repricing routine and update existing quote (qty, price break and freight option changes) | John |  | 1
| 13-2 |  | Show MOD price break pop-up for MOD items
Active Cart | 14-0 |  | Cart - Handling Zipcode changes in the Cart.
| 14-1 |  | Update availability dates for stock and mod items | John |  | 1
| 14-2 |  | Reprice the quote for MOD items (if expired it gets new quote) | John |  | 1
Remove checkout address informaton from SHOPPINGCART.USR
Remove checkout bundling informaton from SHOPPINGCART.USR
Active Cart | 15-0 |  | Cart - CE version of contact’s cart (by operator) | John |  | 1
Active Cart | 16-0 |  | Cart - New print plate logic (no checkout until approval) |  |  | 1
| 16-1 |  | Detect a printed job and show upload link
Active Cart | 17-0 |  | Cart - Changes to Items in a Cart (add, delete , quantity changes) |  |  | 1
| 17-1 |  | Remove checkout bundling informaton from SHOPPINGCART.USR
| 17-2 |  | Update availability dates for stock and mod items
Results | 18-0 |  | Marketplace - When to show MOD Result |  |  | 1
| 18-1 |  | BP WEB.MODITEM.CHECK - If 'Customer Pickup' is chosen for Ziptop, do not create a Marketplace MOD Result | Judy |  | 1
| 18-2 |  | UI - Only show MOD marketplace result if it's a better price than exact stock match. What about availability? | JJ
|  |  | Godzilla - ce quote search |  |  | 1
|  |  | c/e & sales web interface (including NEPB customer login) |  |  | 1
|  |  | c/e - multiple sessions |  |  | 1
Miscellaneous |  |  | Avante - QUO4000: remove all custom items except NS |  |  | 1
Miscellaneous |  |  | Avante - new CPU FOB code (check Clippership) |  |  | 1
Miscellaneous |  |  | Avante - SOP4000 & QUO4001 - assign master order# for sample/NS orders |  |  | 1
Miscellaneous |  |  | Avante - Sales Order Entry and Sales Order Display - searching/viewing orders using master order# |  |  | 1
Miscellaneous |  |  | Avante - report changes due to restructure of configuration (MOD) |  |  | 1
Miscellaneous |  |  | Avante - Must Ship Today Report - resort by shipment status? |  |  | 1
Miscellaneous |  |  | Avante - Label Item Description for Marketplace: format has changed to be more like other custom items |  |  | 1
|  |  | Creation of new label templates |  |  | 1
|  |  | Change .READ includes to callable programs? |  |  | 1
|  |  | Continue to Test and Bug Fix the Shop Widget |  |  | 1
|  |  | Acknowledgements - Avante vs Web and Faxing |  |  | 1
|  |  | Lock Logic - Carts, Quote Changes, etc - how will we stop multiple people from working on same cart/quote? |  |  | 1
|  |  | Completed - Widget Level 3 – null out defaults if level 3 disabled | Judy | Joe | 3
|  |  | Show Cradlepack option upon search. | John | Sal | 2
|  |  | Cart - Add MOD item to Cart | John | Ed | 2
|  |  | Results - show message when can't make MOD item |  |  | 3
|  |  | Investigate - Can we save individual prices for certain parts number for a given customer (ideally would be able point to an Override price list for certain items) |  |  | 5
|  |  | Investigate - ramifications of allocating inventory when an order goes on credit hold |  |  | 5
|  |  | Investigate - what needs to change on Avante when order# goes to 8 char (7+suffix) and w/o goes to 9 char |  |  | 5
|  |  | Investigate - automating CIA and COD as part of credit card process (per Dawn - if we happen to be in that area …) |  |  | 5
|  |  | Server Response Time |  |  | 5
|  |  | UI work (smooth out screen jumping) |  |  | 5
|  |  | Default and Validate Zip Code based on Active Cart. |  |  | 0
|  |  | Add MOD items to Cart | John | Ed | 1
|  |  | Detecting WHS descrepancy for CPU MOD items. | John |  | 0
|  |  | Cross Browser Support |  |  | 0
|  |  | Improve Banner Message Wording |  |  | 0
|  |  | Enter YMAC Rules for ALL categories | John |  | 1
Added - has 'Remake Order' been added to Re-order screen from Order History?
Added - Avante - c/e requests - add zipcode prompt to billto# lookup (for orgs with multiple billtos)
0 = Awaiting Info - can't design yet
1 = Ready to Design
2 = Ready for Program
3 = Done
5 = Investigation
shop widget |  |  | Calling required field validation by group. On find and on close of a group. IF the user never goes to a field, field validation never fires so group validation is needed.
shop widget |  |  | Substitute logic is left to be determined. |  |  | 0
shop widget |  |  | Pulling up a saved item and making changes. Exp vs unexp/unconverted; reprice/new price; increment config; overlay saveditem
shop widget | ext descriptions |  | Need Marketing Approval for the format and the approach.
order History |  |  | Modify results to handle master orders
order History |  |  | Complete Summary Popup
order History |  |  | Complete Tracking Popup for all Carriers
saved carts |  |  | Handling working with someone else's cart
saved carts |  |  | Share count in Results
Share Cart |  |  | Saving Shared Cart Event
Share Cart |  |  | Redisplay Shared Cart from Saved Carts
Performance Optimizaion
|  |  | Production Description Standarization - WHAT DO YOU WANT |  |  | 0
Active Cart |  |  | how to handle price breaks after they changed results options (freight options,packout)
MOD item Descriptions
Freight Dropdown
Total Items