## Summary
Status as of 12.2.13
Task | Status | Avante | UI | AV Rework | UI Rework | Ongoing QA
ShopWidget | In Progress | 0 | 0 | 17.49 | 8.602 | 0 | no macchi; database cleanup; ui bug fixes;
Saved Items | In Progress | 0 | 0 | 0 | 0 | 0
Order History | In Progress | 0 | 0 | 0 | 0 | 0
Saved Carts | In Progress | 0 | 0 | 0 | 0 | 0
Share Cart | In Progress | 0 | 0 | 0 | 0 | 0
Active Cart | In Progress | 0 | 0 | 0 | 0 | 0
Checkout | In Progress | 0 | 0 | 0 | 0 | 0
My Account | TBDesigned | 0 | 0 | 0 | 0 | 0
Avante | TBDesigned | 0 | 0 | 0 | 0 | 0
Data Conversions | TBDesigned | 0 | 0 | 0 | 0 | 0
Twitter Feed on page |  | 0 | 1 | 0 | 0 | 0 | "The Experience" not in first launch. Numbers are for twitter feed on page.
Pre Login Func |  | 0 | 0 | 0 | 0 | 0 | This functionality should be in the numbers of the pertinent sections
Mktg/Fat Content |  | 4 | 8 | 3 | 3 | 3 | These numbers are COMPLETE guesses. This line is to represent the "front page" information from the existing site.
CE Web Integration | TBDesigned | 0 | 0 | 0 | 0 | 0
Predictive Ordering | TBDesigned | 3 | 2 | 2 | 2 | 2 | incomplete design
Shared Item |  | 0 | 0 | 0 | 0 | 0 | This is complete however, handling FAX customers is still a problem. Needs to be discussed.
Notifications |  | 4 | 4 | 2 | 2 | 2 | A system needs to be designed on what to tell customers about and how to let them customize what they are told about. For example, when their order ships, when someone empties their cart.
#Days |  | 11 | 15 | 24.49 | 15.602 | 7
|  | 2.4 | 1.6 | 2.4 | 1.6 | Various
#Weeks |  | 1.0147 | 1.973 | 2.1388 | 2.0482 | Ongonig
Complete Date |  | 2026-08-13 02:28 | 2026-08-19 19:28 | 2026-08-28 01:47 | 2026-09-03 03:34 | Pre-live
Dates as of Prev Week |  | 2014-01-21 | 2014-02-22 | 2014-02-27 | 2014-04-09
Formulas:
Avante = TODAY()+([Avante, row above]*7)
UI = TODAY()+([UI, row above]*7)
AV Rework = [Avante]+([AV Rework, row above]*7)
UI Rework = [UI]+([UI Rework, row above]*7)

## ShopWidget
Task | Avante |  | UI |  | Rework |  | QA | Status/Notes
| Days | Rem | Days | Rem | Avante | UI
Status as of 12.2.13
Total Days | 0 | 0 | 0 | 0
Overall Rework Factor
Overall QA Factor

## Saved Items
Task | Avante |  | UI |  | Rework |  | QA | Status/Notes
| Days | Rem | Days | Rem | Avante | UI
Status as of 12.2.13
Total Days | 0 | 0 | 0 | 0
Overall Rework Factor
Overall QA Factor

## Order History
Task | Avante |  | UI |  | Rework |  | QA | Status/Notes
| Days | Rem | Days | Rem | Avante | UI
Status as of 12.2.13
Total Days | 0 | 0 | 0 | 0
Overall Rework Factor
Overall QA Factor

## Saved Carts
Task | Avante |  | UI |  | Rework |  | QA | Status/Notes
| Days | Rem | Days | Rem | Avante | UI
Status as of 12.2.13
Total Days | 0 | 0 | 0 | 0
Overall Rework Factor
Overall QA Factor

## Share Cart
Task | Avante |  | UI |  | Rework |  | QA | Status/Notes
| Days | Rem | Days | Rem | Avante | UI
Status as of 12.2.13
Total Days | 0 | 0 | 0 | 0
Overall Rework Factor
Overall QA Factor

## Active Cart
Task | Avante |  | UI |  | Rework |  | QA | Status/Notes
| Days | Rem | Days | Rem | Avante | UI
Status as of 12.2.13
Total Days | 0 | 0 | 0 | 0
Overall Rework Factor
Overall QA Factor

## Checkout
Task | Avante |  | UI |  | Rework |  | QA | Status/Notes
| Days | Rem | Days | Rem | Avante | UI
Status as of 12.2.13
Total Days | 0 | 0 | 0 | 0
Overall Rework Factor
Overall QA Factor

## CEWeb
Task | Avante |  | UI |  | Rework |  | QA | Status/Notes
| Days | Rem | Days | Rem | Avante | UI
Status as of 12.2.13
Total Days | 0 | 0 | 0 | 0
Overall Rework Factor
Overall QA Factor

## Miscellaneous
Task | Avante |  | UI |  | Rework |  | QA | Status/Notes
| Days | Rem | Days | Rem | Avante | UI
Status as of 12.2.13
Total Days | 0 | 0 | 0 | 0
Overall Rework Factor
Overall QA Factor

## Data Conversions
Task | Avante |  | UI |  | Rework |  | QA | Status/Notes
| Days | Rem | Days | Rem | Avante | UI
Status as of 12.2.13
Total Days | 0 | 0 | 0 | 0
Overall Rework Factor
Overall QA Factor

## MyAccount
Task | Avante |  | UI |  | Rework |  | QA | Status/Notes
| Days | Rem | Days | Rem | Avante | UI
Status as of 12.2.13
Total Days | 0 | 0 | 0 | 0
Overall Rework Factor
Overall QA Factor

## Note-Questions
Results | Originally we had a line item for Results on the Summary page. Having reviewed the Shop/Results area with
Ed we combined all incomplete functions into one page called ShopWidget. Need to review with JP to be
sure there is no missing functionality.
Miscellaneous | ***Investigate what Avante Reports/Processes are using configurator files to extract data.
I am looking for a list of processes that will require changes when the BAGS/SHEETING/FURN, etc
product lines are combined into a single MOD product line. This means that criteria numbers
may change:
- Search IIPROCESS/BP/LDLIB/AVBP looking for CFQNA<13,x> extractions
- Search IIPROCESS/BP/LDLIB/AVBP looking for CFORDER<13,x> extractions
- Search IIPROCESS/BP/LDLIB/AVBP looking for CFBLDHDR<10,x> extractions
Miscellaneous | ***Investigate/writeup design to only allow NS Made/Buy quotes to be entered via QUO4000. Is there an
easy way to disable the other selections BAGS/SHEETING/TUBING/FURN from the screens? Or should
we bypass the screens entirely and only allow NS as an item number in this screen?
Miscellaneous | ***Investigate how 'shipping notifications' could be sent to customers notifying them that their shipment
has been made:
- Timing - should this be done when updating Avante? What if shipment hasn’t left building yet?
- What email address to use?
- What if customer doesn't accept emails?
- Should notifications be sent for all shipments? CPU's?
Miscellaneous | Investigate what changes will be needed for the new FOB CODE "CPU". I believe CPU (customer pickup)
should follow the rules for COL/3PB in that they have no freight implications. Be sure to check the
freight quote/freight$ calculation programs to make sure that CPU will not go through this logic.
Investigate what should happen with CPU credit card orders -- should they be handled like PPD?

## Defs
Avante Programmers: Wayne, Joe, Janice @ 80% | 2.4
UI Programmers: Ed, Sal @ 80% | 1.6
Technical Designers: John, Judy @ 75% ; Jim, Cathy @ 25% | 2
QA/Test: Susan, Steve, Jim, Owen, Cathy, CE, Mktg

## ToDo
Tab | L-U Ref# | Dt Added | Status | Designer | Programming Task | DB Prg | Hrs/Days | UI Prg | Hrs/Days | DT Rcvd
Key to Reporting | 0-0 |  | 0 |  | Status'
| 0-1 |  | 0 |  | 0 = Awaiting Info - can't design yet
| 0-2 |  | 1 |  | 1 = Ready to Design
| 0-3 |  | 2 |  | 2 = Ready for Program
| 0-4 |  | 3 |  | 3 = Done
| 0-5 |  | 5 |  | 5 = Investigation
| 0-6 |  | 99 |  | 99 = Reserved for Future Use
ShopWidget | 1-0 |  | 0 |  | Avante - Changes for Rolls, Rolls Cradle packed, Rolls Boxed
| 1-1 | 2013-11-25 | 1 | Judy | Modify Packaging Group Description
| 1-2 | 2013-11-25 | 1 |  | Modify Packaging Default Value
| 1-3 |  | 99 |  | Reserved for Future Use
| 1-4 |  | 99 |  | Reserved for Future Use
| 1-5 |  | 99 |  | Reserved for Future Use
SavedItems and | 2-0 |  | 0 |  | New customer part number logic | [5 empty] | including cart logic hover over our part# to see customer part#
Checkout | 2-1 | 2013-11-25 | 0 |  | Avante - Update Existing Mainenance Program | [5 empty] | for 2 lines of descriptions
| 2-2 | 2013-11-25 | 2 | John | UI - Update Checkout Label View |  |  | Francisco | ?? | ??
| 2-3 | 2013-11-25 | 2 | John | UI - Update Saved Items View |  |  | Sal | ?? | ??
| 2-4 | 2013-11-25 | 1 | John | UI - code retrieval of customer items from Database
| 2-5 | 2013-11-25 | 1 | John | UI - code save of customer items to Database
| 2-6 | 2013-11-25 | 0 |  | DB - RPC to return customer items to web
| 2-7 | 2013-11-25 | 0 |  | DB - RPC to save customer items to database
| 2-8 | 2013-11-25 | 0 |  | Conversion - convert MOD items | [5 empty] | new format for customer item numbers (custom/MOD) and combine 3 description lines to 2
| 2-9 | 2013-11-25 | 1 |  | DB - Customer Item Number Search from the Shop Widget | [5 empty] | allow for search from shop widget by customer item number
| 2-10 | 2013-11-25 | 0 |  | Avante - Modify the Customer Item Number upload | [5 empty] | for new format and to overwrite rather than delete
| 2-11 | 2013-11-25 | 0 |  | Duplicate Customer Names | [5 empty] | How to handle duplicate customer names/add customer nbr to tag xref for cust part# assignment???
| 2-12 |  | 99 |  | Reserved for Future Use
| 2-13 |  | 99 |  | Reserved for Future Use
| 2-14 |  | 99 |  | Reserved for Future Use
Saved Items | 3-0 |  | 0 |  | Change the saved items record key (from contact to billto customer) | [5 empty] | and effects on completed programming
| 3-1 | 2013-11-25 | 1 | John | DB - Create file to hold Mod Item Specification by Bill-to
| 3-2 | 2013-11-25 | 1 | John | DB - Modify File Structure for Contact Item information
| 3-3 | 2013-11-25 | 1 | John | DB - RPC$MODITEM_CREATE - Update saving of MOD items
| 3-4 | 2013-11-25 | 1 | John | DB - RPC$CONTACTITEM_DELETE - Delete Billto Level data as well?
| 3-5 | 2013-11-25 | 1 | John | DB - RPC$CONTACTITEM_GETBYFILTER - Pull info from billto level & Contact level
| 3-6 | 2013-11-25 | 1 | John | DB - RPC$CONTACTITEM_GETBYID - Pull Info from billto level & Contact Level
| 3-7 | 2013-11-25 | 1 | John | DB - RPC$CONTACTITEM_SAVE
| 3-8 | 2013-11-25 | 1 | John | DB - RPC$ITEMTAG_GETBYFILTER
| 3-9 | 2013-11-25 | 1 | John | DB - RPC$ITEMTAG_GETBYFILTER2
| 3-10 | 2013-11-25 | 1 | John | DB - RPC$ITEMTAG_SELECT
| 3-11 | 2013-11-25 | 1 | John | DB - RPC$QUOTEITEM_GETBYSAVEDITEM
| 3-12 | 2013-11-25 | 1 | John | DB - RPC$SHAREDITEM_GETBYFILTER
| 3-13 | 2013-11-25 | 1 | John | DB - RPC$SHAREDITEM_SAVE
| 3-14 | 2013-11-25 | 1 | John | DB - RPC$SHIPMENTBUNDLING_GETBYFILTER
| 3-15 |  | 99 |  | Reserved for Future Use
| 3-16 |  | 99 |  | Reserved for Future Use
| 3-17 |  | 99 |  | Reserved for Future Use
MyAccount | 4-0 |  | 0 |  | Process at Login - Deleting Expired Carts
| 4-1 |  | 1 | John | Write Last Activity Date to SHOPPINGCART.USR
| 4-2 |  | 0 | John | Delete old carts upon user validation based on xxx days old | [5 empty] | Can carts be deleted by anyone other than the user that created them?
| 4-3 |  | 0 |  | Does purge of carts delete the history of sharing as well
| 4-4 |  | 99 |  | Reserved for Future Use
| 4-5 |  | 99 |  | Reserved for Future Use
| 4-6 |  | 99 |  | Reserved for Future Use
Checkout | 5-0 |  | 0 |  | Duplicate P/O display in Checkout
| 5-1 |  | 2 | John | Create Pop-up for Duplicate PO numbers |  |  | ?? | ?? | ??
| 5-2 |  | 1 | John | Handle user response to pop-up
| 5-3 |  | ?? | John | Validations
| 5-4 |  | 99 |  | Reserved for Future Use
| 5-5 |  | 99 |  | Reserved for Future Use
| 5-6 |  | 99 |  | Reserved for Future Use
Checkout | 6-0 |  | 0 |  | Order Creation
| 6-1 |  | 0 |  | Determine How To Create Orders from Bundles
| 6-2 |  | 0 | Judy | Create orders from Bundles
| 6-3 |  | 1 | Judy | Order Creation - Ship With Logic (ship with comment)
| 6-4 |  | 2 | Judy | Order Creation - Setting FOB Code for Customer Pickup | Wayne | 0.1 |  |  | 2013-12-02
| 6-5 |  | 2 | Judy | ‘Must Ship Today Flag’ | Wayne | 0.1 |  |  | 2013-12-02 | setting on order based on time of day and bundle ship date
| 6-6 |  | 2 | Judy | Order source when ce enters order | Wayne | ?? |  |  | ??
| 6-7 |  | 2 | Judy | Creating a new Shipto Customer | Wayne | ?? |  |  | ??
| 6-8 |  | 2 | Judy | Write cart name to SOHDR.USR | Wayne | ?? |  |  | ??
| 6-9 |  | 5 | Judy | Move MOD ‘ashad' and order shipping preference comments | [5 empty] | ‘ashad’ comments and order shipping preference comments forward to new order
| 6-10 |  | 1 | Judy | Add Pallet Type (shipping preferences) as a w/o comment for MOD Orders | [5 empty] | Pallet Type (from shipping preferences) must be added as a w/o comment for MOD Orders
| 6-11 |  | 99 |  | Reserved for Future Use
| 6-12 |  | 99 |  | Reserved for Future Use
| 6-13 |  | 99 |  | Reserved for Future Use
Checkout | 7-0 |  | 0 |  | Checkout - Labeling
| 7-1 |  | 1 |  | Validations | [5 empty] | customer part number required, third party, Brandit customer setup
| 7-2 |  | 1 |  | Udate Labeling to SHOPPINGCART.USR
| 7-3 |  | 1 |  | Interface with Bartender to Generate Label Images
| 7-4 |  | 1 |  | Set Up Paging to Step from Label to Label.
| 7-5 |  | 0 |  | Interface with Saved Items Popup.
| 7-6 |  | 1 |  | Refresh Label Image as Needed.
| 7-7 |  | 0 |  | Retrieve Customer Part Number Information.
| 7-8 |  | 1 |  | Return Brandit Information as Customer Object Properties
| 7-9 |  | 1 |  | Show Correct Options for Label Format | [5 empty] | label type on top, check box options below, actual part numbers
| 7-10 |  | 1 |  | Creation of New Label Templates
????? Own | 7-11 |  | 0 |  | Handle Adding Label Comment
????? Own | 7-12 |  | 0 |  | Build Content of the Page
????? Own | 7-13 |  | 0 |  | Build Label Image
| 7-14 |  | 99 |  | Reserved for Future Use
| 7-15 |  | 99 |  | Reserved for Future Use
| 7-16 |  | 99 |  | Reserved for Future Use
Checkout | 8-0 |  | 0 |  | Checkout - Addresses
| 8-1 |  | 1 | Judy | Check Create Order F2 validations | [5 empty] | only diff is that zip code is entered, then city/state is defaulted from ZIPCODE.USR
| 8-2 |  | 2 | Judy | Update SHOPPINGCART.USR | Wayne | ?? |  |  | ??
| 8-3 |  | 1 | Judy | Verify that ship-to zip matches cart zip (in case of zip code change)
????? Own | 8-4 |  | 0 |  | Handle changing of Ship-to
| 8-5 |  | 99 |  | Reserved for Future Use
| 8-6 |  | 99 |  | Reserved for Future Use
| 8-7 |  | 99 |  | Reserved for Future Use
Checkout | 9-0 |  | 0 |  | Checkout - Payment
| 9-1 |  | 1 | Judy | Check Create Order F2 validations | [5 empty] | **done-only diff is CC Name s/b reqd & Exp Date shouldn't default - UI??
| 9-2 |  | 1 |  | Make sure all validations from existing website are in new website (UI?)
| 9-3 |  | 1 |  | Redesign Payment View to new specifications
| 9-4 |  | 99 |  | Reserved for Future Use
| 9-5 |  | 99 |  | Reserved for Future Use
| 9-6 |  | 99 |  | Reserved for Future Use
Checkout | 10-0 |  | 0 |  | Checkout - Giving
| 10-1 |  | 3 | Judy | Check Create Order F2 validations - | ?? | ?? |  |  | ?? | *** NO GIVING SCREEN ON AVANTE SO NOT NEEDED -
| 10-2 |  | 1 | John | Bypass if CE
| 10-3 |  | 2 | Judy | Update SHOPPINGCART.USR | Wayne | ?? |  |  | ??
| 10-4 |  | 99 |  | Reserved for Future Use
| 10-5 |  | 99 |  | Reserved for Future Use
| 10-6 |  | 99 |  | Reserved for Future Use
Checkout | 11-0 |  | 0 |  | Checkout - Bundling View
| 11-1 |  | 1 | Judy | Validations - ie ship via, fob code, shipping preferences, ship date
| 11-2 |  | 1 | Judy | Update Bundling to SHOPPINGCART.USR
| 11-3 |  | 1 | Judy | Validate ‘ship date’ – allow ‘x’ days in future
| 11-4 |  | 99 |  | Reserved for Future Use
| 11-5 |  | 99 |  | Reserved for Future Use
| 11-6 |  | 99 |  | Reserved for Future Use
Active Cart | 12-0 |  | 0 |  | Cart - Handle Price expiration of MOD items
| 12-1 |  | 2 | John | Create a view for Mod Items |  |  | ?? | ?? | ??
| 12-2 |  | 1 |  | Establish the state of the view and show correct clock icon
| 12-3 |  | 1 |  | Disable Controls for expired items
| 12-4 |  | 1 |  | Creating New Quote from Expired Quote | [5 empty] | Create a new quote from expired quote and save new quote to SHOPPINGCART.USR and remove old
| 12-5 |  | 99 |  | Reserved for Future Use
| 12-6 |  | 99 |  | Reserved for Future Use
| 12-7 |  | 99 |  | Reserved for Future Use
Active Cart | 13-0 |  | 0 |  | Cart - Repricing MOD items in the cart.
| 13-1 |  | 1 | John | Call repricing routine and update existing quote | [5 empty] | qty, price break and freight option changes
| 13-2 |  | 1 |  | Show MOD price break pop-up for MOD items
| 13-3 |  | 99 |  | Reserved for Future Use
| 13-4 |  | 99 |  | Reserved for Future Use
| 13-5 |  | 99 |  | Reserved for Future Use
Active Cart | 14-0 |  | 0 |  | Cart - Handling Zipcode changes in the Cart.
| 14-1 |  | 1 | John | Update availability dates for stock and mod items
| 14-2 |  | 1 | John | Reprice the quote for MOD items (if expired it gets new quote)
| 14-3 |  | 1 |  | Remove checkout address informaton from SHOPPINGCART.USR
| 14-4 |  | 1 |  | Remove checkout bundling informaton from SHOPPINGCART.USR
| 14-5 |  | 99 |  | Reserved for Future Use
| 14-6 |  | 99 |  | Reserved for Future Use
| 14-7 |  | 99 |  | Reserved for Future Use
Active Cart | 15-0 |  | 0 |  | Cart - CE version of contact’s cart (by operator)
| 15-1 |  | 99 |  | Reserved for Future Use
| 15-2 |  | 99 |  | Reserved for Future Use
| 15-3 |  | 99 |  | Reserved for Future Use
Active Cart | 16-0 |  | 0 |  | Cart - New print plate logic (no checkout until approval)
| 16-1 |  | 1 |  | Detect a printed job and show upload link
| 16-2 |  | 99 |  | Reserved for Future Use
| 16-3 |  | 99 |  | Reserved for Future Use
| 16-4 |  | 99 |  | Reserved for Future Use
Active Cart | 17-0 |  | 0 |  | Cart - Changes to Items in a Cart (add, delete , quantity changes)
| 17-1 |  | 1 |  | Remove checkout bundling informaton from SHOPPINGCART.USR | [5 empty] | add change delete based on what is done
| 17-2 |  | 1 |  | Update availability dates for stock and mod items
| 17-3 |  | 99 |  | Reserved for Future Use
| 17-4 |  | 99 |  | Reserved for Future Use
| 17-5 |  | 99 |  | Reserved for Future Use
Results | 18-0 |  | 0 |  | Marketplace - When to show MOD Result
| 18-1 |  | 1 | Judy | BP WEB.MODITEM.CHECK - for 'Customer Pickup' if Ziptop | [5 empty] | If 'Customer Pickup' is chosen for Ziptop, do not create a Marketplace MOD Result
| 18-2 |  | 0 | John/Judy | UI - MOD vs. Stock Comparrison for marketplace result | [5 empty] | Only show MOD marketplace result if it's a better price than exact stock match. What about availability?
| 18-3 |  | 99 |  | Reserved for Future Use
| 18-4 |  | 99 |  | Reserved for Future Use
| 18-5 |  | 99 |  | Reserved for Future Use
Order History | 19-0 |  | 0 |  | Modify results to handle master orders
| 19-1 |  | 99 |  | Reserved for Future Use
| 19-2 |  | 99 |  | Reserved for Future Use
| 19-3 |  | 99 |  | Reserved for Future Use
Order History | 20-0 |  | 0 |  | Complete Summary Popup
| 20-1 |  | 99 |  | Reserved for Future Use
| 20-2 |  | 99 |  | Reserved for Future Use
| 20-3 |  | 99 |  | Reserved for Future Use
Order History | 21-0 |  | 0 |  | Complete Tracking Popup for all Carriers
| 21-1 |  | 99 |  | Reserved for Future Use
| 21-2 |  | 99 |  | Reserved for Future Use
| 21-3 |  | 99 |  | Reserved for Future Use
CEWeb | 22-0 |  | 0 |  | Spinning off multiple requests. | [5 empty] | How are we going to handle multiple requests per call.
| 22-1 |  | 99 |  | Reserved for Future Use
| 22-2 |  | 99 |  | Reserved for Future Use
| 22-3 |  | 99 |  | Reserved for Future Use
CEWeb | 23-0 |  | 0 |  | Impersonating a contact. | [5 empty] | Having the CE rep working as someone else and tracking everything correctly.
| 23-1 |  | 99 |  | Reserved for Future Use
| 23-2 |  | 99 |  | Reserved for Future Use
| 23-3 |  | 99 |  | Reserved for Future Use
CEWeb | 24-0 |  | 0 |  | Send CE to the Web at the right time. | [5 empty] | This means not sending to the web other times.
| 24-1 |  | 99 |  | Reserved for Future Use
| 24-2 |  | 99 |  | Reserved for Future Use
| 24-3 |  | 99 |  | Reserved for Future Use
CEWeb | 25-0 |  | 0 |  | Multiple Sessions??? | [5 empty] | How will CE work if we cannot use multiple web sessions. Initial investigation is done and works in IE* and above, Crome, not Firefox
| 25-1 |  | 99 |  | Reserved for Future Use
| 25-2 |  | 99 |  | Reserved for Future Use
| 25-3 |  | 99 |  | Reserved for Future Use
CEWeb | 26-0 |  | 0 |  | NEPB Customer Login | [5 empty] | How will CE process NEPB customers
| 26-1 |  | 99 |  | Reserved for Future Use
| 26-2 |  | 99 |  | Reserved for Future Use
| 26-3 |  | 99 |  | Reserved for Future Use
CEWeb | 27-0 |  | 0 |  | CE and Sales Web Interface | [5 empty] | Including NEPB customer Login
| 27-1 |  | 99 |  | Reserved for Future Use
| 27-2 |  | 99 |  | Reserved for Future Use
| 27-3 |  | 99 |  | Reserved for Future Use
CEWeb | 28-0 |  | 0 |  | CE - Multiple Sessions - making it work
| 28-1 |  | 99 |  | Reserved for Future Use
| 28-2 |  | 99 |  | Reserved for Future Use
| 28-3 |  | 99 |  | Reserved for Future Use
CEWeb | 29-0 |  | 1 |  | Godzilla - CE Quote Search
| 29-1 |  | 99 |  | Reserved for Future Use
| 29-2 |  | 99 |  | Reserved for Future Use
| 29-3 |  | 99 |  | Reserved for Future Use
Miscellaneous | 30-0 |  | 0 |  | Miscellaneous Avante Items
| 30-1 |  | 1 |  | Avante - QUO4000 | [5 empty] | remove all custom items except NS
| 30-2 |  | 1 |  | Avante - new CPU FOB code | [5 empty] | check Clippership
| 30-3 |  | 1 |  | Avante - SOP4000 & QUO4001 | [5 empty] | assign master order# for sample/NS orders
| 30-4 |  | 1 |  | Avante - Sales Order Entry and Sales Order Display | [5 empty] | searching/viewing orders using master order#
| 30-5 |  | 1 |  | Avante - MOD Configuration | [5 empty] | report changes due to restructure of configuration
| 30-6 |  | 1 |  | Avante - Must Ship Today Report | [5 empty] | resort by shipment status or must ship today flag
| 30-7 |  | 1 |  | Avante - Label Item Description for Marketplace | [5 empty] | format has changed to be more like other custom items
| 30-8 |  | 0 |  | Avante - Searches | [5 empty] | add 'zip code' prompt to the billto # search in c/e requests - for orgs with multiple bill-to's
| 30-9 |  | 1 |  | Change .READ includes to callable programs?
| 30-10 |  | 0 |  | Excel Report - Pallet Info | [5 empty] | go-live that lists pallet info that can be entered as preferences
| 30-11 |  | 0 |  | Excel Report - Customer Item Info | [5 empty] | go-live that lists customers using their item numbers so preferences can be set
| 30-12 |  | 99 |  | Reserved for Future Use
| 30-13 |  | 99 |  | Reserved for Future Use
| 30-14 |  | 99 |  | Reserved for Future Use
ShopWidget | 31-0 |  | 1 |  | Continue to Test and Bug Fix the Shop Widget
| 31-1 |  | 99 |  | Reserved for Future Use
| 31-2 |  | 99 |  | Reserved for Future Use
| 31-3 |  | 99 |  | Reserved for Future Use
ShopWidget | 32-0 |  | 0 |  | Validations
| 32-1 |  | 2 |  | Group Validations | [5 empty] | Calling required field validation by group. On find and on close of a group. IF the user never goes to a field, field validation never fires so group validation is needed.
| 32-2 |  | 99 |  | Reserved for Future Use
| 32-3 |  | 99 |  | Reserved for Future Use
| 32-4 |  | 99 |  | Reserved for Future Use
ShopWidget | 33-0 |  | 0 |  | Changing Quotes
| 33-1 |  | 1 |  | Change Existing Quotes | [5 empty] | Pulling up a saved item and making changes. Exp vs unexp/unconverted; reprice/new price; increment config and overlay saved items
| 33-2 |  | 99 |  | Reserved for Future Use
| 33-3 |  | 99 |  | Reserved for Future Use
| 33-4 |  | 99 |  | Reserved for Future Use
ShopWidget | 34-0 |  | 0 |  | Extended Descriptions
| 34-1 |  | 0 |  | Marketing notes for extended descriptions | [5 empty] | Need Marketing Approval for the format and the approach.
| 34-2 |  | 99 |  | Reserved for Future Use
| 34-3 |  | 99 |  | Reserved for Future Use
| 34-4 |  | 99 |  | Reserved for Future Use
ShopWidget | 35-0 |  | 0 |  | Atlanta Production
| 35-1 |  | 0 |  | Modify Avante Programs and Configurations | [5 empty] | Waiting for production rules from David
| 35-2 |  | 0 |  | Modify RPC programs for Rules
| 35-3 |  | 99 |  | Reserved for Future Use
| 35-4 |  | 99 |  | Reserved for Future Use
| 35-5 |  | 99 |  | Reserved for Future Use
ShopWidget | 36-0 |  | 0 |  | Level 3 Results
| 36-1 |  | 3 | Judy | Widget Level 3 | Joe |  |  |  |  | null out defaults if level 3 disabled
| 36-2 |  | 99 |  | Reserved for Future Use
| 36-3 |  | 99 |  | Reserved for Future Use
| 36-4 |  | 99 |  | Reserved for Future Use
SavedCarts | 37-0 |  | 0 |  | Results
| 37-1 |  | 1 | John | Share count on results page | [5 empty] | the count of how many user has saved.
| 37-2 |  | 99 |  | Reserved for Future Use
| 37-3 |  | 99 |  | Reserved for Future Use
| 37-4 |  | 99 |  | Reserved for Future Use
SavedCarts | 38-0 |  | 0 |  | Handling Working on Someone Else's Cart
| 38-1 |  | 0 | John | UI Changes | [5 empty] | Changes to the UI / Avante based on preferences
| 38-2 |  | 0 | Judy | Avante DB Changes
| 38-3 |  | 99 |  | Reserved for Future Use
| 38-4 |  | 99 |  | Reserved for Future Use
| 38-5 |  | 99 |  | Reserved for Future Use
ShareCart | 39-0 |  | 1 |  | Saving Shared Cart Event
| 39-1 |  | 99 |  | Reserved for Future Use
| 39-2 |  | 99 |  | Reserved for Future Use
| 39-3 |  | 99 |  | Reserved for Future Use
ShareCart | 40-0 |  | 0 |  | Redisplay Shared Cart from Saved Carts
| 40-1 |  | 99 |  | Reserved for Future Use
| 40-2 |  | 99 |  | Reserved for Future Use
| 40-3 |  | 99 |  | Reserved for Future Use
Active Cart | 41-0 |  | 0 |  | MOD Item Descriptions | [5 empty] | ??
| 41-1 |  | 99 |  | Reserved for Future Use
| 41-2 |  | 99 |  | Reserved for Future Use
| 41-3 |  | 99 |  | Reserved for Future Use
Active Cart | 42-0 |  | 0 |  | Freight Dropdown | [5 empty] | ??
| 42-1 |  | 99 |  | Reserved for Future Use
| 42-2 |  | 99 |  | Reserved for Future Use
| 42-3 |  | 99 |  | Reserved for Future Use
Active Cart | 43-0 |  | 0 |  | Total Items | [5 empty] | ??
| 43-1 |  | 99 |  | Reserved for Future Use
| 43-2 |  | 99 |  | Reserved for Future Use
| 43-3 |  | 99 |  | Reserved for Future Use
Active Cart | 44-0 |  | 0 |  | Price Break Display | [5 empty] | how to handle price breaks after they changed results options (freight options,packout)
| 44-1 |  | 99 |  | Reserved for Future Use
| 44-2 |  | 99 |  | Reserved for Future Use
| 44-3 |  | 99 |  | Reserved for Future Use
Active Cart | 45-0 |  | 0 |  | Quick Add | [5 empty] | Handling enter and setting focus back to item number box after add button
| 45-1 |  | 99 |  | Reserved for Future Use
| 45-2 |  | 99 |  | Reserved for Future Use
| 45-3 |  | 99 |  | Reserved for Future Use
Active Cart | 46-0 |  | 0 |  | Default and Validate Zip Code Based on Active Cart | [5 empty] | Handling enter and setting focus back to item number box after add button
| 46-1 |  | 99 |  | Reserved for Future Use
| 46-2 |  | 99 |  | Reserved for Future Use
| 46-3 |  | 99 |  | Reserved for Future Use
Active Cart | xx-0 |  | 2 |  | Add MOD Item to Cart |  |  | Ed |  |  | Hitting ADD must properly store MOD item in the cart
| xx-1 |  | 99 |  | Reserved for Future Use
| xx-2 |  | 99 |  | Reserved for Future Use
| xx-3 |  | 99 |  | Reserved for Future Use
Order History | xx-0 |  | 0 | John | Order History Summary |  |  | Ed
| xx-1 |  | 99 |  | Reserved for Future Use
| xx-2 |  | 99 |  | Reserved for Future Use
| xx-3 |  | 99 |  | Reserved for Future Use
Order History | xx-0 |  | 0 |  | Remake Orders - Re-Order Page |  |  | Ed |  |  | Remake order logic needs to be added
| xx-1 |  | 99 |  | Reserved for Future Use
| xx-2 |  | 99 |  | Reserved for Future Use
| xx-3 |  | 99 |  | Reserved for Future Use
????????? | xx-0 |  | 0 |  | Stock & MOD Price Overrides (Misc$) |  |  | Ed
| xx-1 |  | 99 |  | Reserved for Future Use
| xx-2 |  | 99 |  | Reserved for Future Use
| xx-3 |  | 99 |  | Reserved for Future Use
Checkout | xx-0 |  | 0 |  | Checkout - Summary
| xx-1 |  | 99 |  | Reserved for Future Use
| xx-2 |  | 99 |  | Reserved for Future Use
| xx-3 |  | 99 |  | Reserved for Future Use
Checkout | xx-0 |  | 0 |  | Handling Working with Someone Else's Cart
| xx-1 |  | 99 |  | Reserved for Future Use
| xx-2 |  | 99 |  | Reserved for Future Use
| xx-3 |  | 99 |  | Reserved for Future Use
Checkout | xx-0 |  | 0 |  | Add Order Total Panel
| xx-1 |  | 99 |  | Reserved for Future Use
| xx-2 |  | 99 |  | Reserved for Future Use
| xx-3 |  | 99 |  | Reserved for Future Use
Checkout | xx-0 |  | 0 |  | Labeling
| xx-1 |  | 0 |  | Handle Third Party Labels
| xx-2 |  | 99 |  | Reserved for Future Use
| xx-3 |  | 99 |  | Reserved for Future Use
| xx-4 |  | 99 |  | Reserved for Future Use
Checkout | xx-0 |  | 0 |  | Super User Setup
| xx-1 |  | 99 |  | Reserved for Future Use
| xx-2 |  | 99 |  | Reserved for Future Use
| xx-3 |  | 99 |  | Reserved for Future Use
Miscellaneous | xx-0 |  | 0 | Judy | Cross Browser Support | [5 empty] | Testing on Multiple Platforms / Issues with IE8
| xx-1 |  | 99 |  | Reserved for Future Use
| xx-2 |  | 99 |  | Reserved for Future Use
| xx-3 |  | 99 |  | Reserved for Future Use
Miscellaneous | xx-0 |  | 0 |  | Improve Banner Message Wording
| xx-1 |  | 99 |  | Reserved for Future Use
| xx-2 |  | 99 |  | Reserved for Future Use
| xx-3 |  | 99 |  | Reserved for Future Use
Miscellaneous | xx-0 |  | 0 | Judy | Avante Config Reports and Logic | [5 empty] | Due to configuration creiteria changes and part number changes
| xx-1 |  | 99 |  | Reserved for Future Use
| xx-2 |  | 99 |  | Reserved for Future Use
| xx-3 |  | 99 |  | Reserved for Future Use
Miscellaneous | xx-0 |  | 0 | Judy | Quote and Ack Forms | [5 empty] | No change to form layout. Continue to use for NS quote/orders & sample orders.
| xx-1 |  | 0 |  | Link From Web to Avante for Faxed Ackn
| xx-2 |  | 0 |  | Link From Avante to Web to re-send Order Ack
| xx-3 |  | 0 |  | Add checkout Shipping Upcharges | [5 empty] | Determine if we should show details or no detail - below subtotal
| xx-4 |  | 0 |  | Master Order Numbers On Optio Forms
| xx-5 | 2013-10-08 | 5 |  | Possible layout change for bundling details
| xx-6 |  | 99 |  | Reserved for Future Use
| xx-7 |  | 99 |  | Reserved for Future Use
| xx-8 |  | 99 |  | Reserved for Future Use
Miscellaneous | xx-0 |  | 0 | Judy | Acknowledgements - Avante vs Web and Faxing | [5 empty] | ???? Is this a duplicate of above
| xx-1 |  | 99 |  | Reserved for Future Use
| xx-2 |  | 99 |  | Reserved for Future Use
| xx-3 |  | 99 |  | Reserved for Future Use
Miscellaneous | xx-0 |  | 0 | Judy | Order Creation - Credit Hold - put entire master order on hold (all sub-orders)
| xx-1 |  | 99 |  | Reserved for Future Use
| xx-2 |  | 99 |  | Reserved for Future Use
| xx-3 |  | 99 |  | Reserved for Future Use
Miscellaneous | xx-0 |  | 0 | Judy | Order Creation - Special Instructions / Comments
| xx-1 |  | 99 |  | Reserved for Future Use
| xx-2 |  | 99 |  | Reserved for Future Use
| xx-3 |  | 99 |  | Reserved for Future Use
Miscellaneous | xx-0 |  | 0 |  | Order Creation Upcharges
| xx-1 |  | 99 |  | Reserved for Future Use
| xx-2 |  | 99 |  | Reserved for Future Use
| xx-3 |  | 99 |  | Reserved for Future Use
Miscellaneous | xx-0 |  | 0 |  | Creation of c/e request(s) *** this logic applies to other areas of site, not just orders
| xx-1 |  | 99 |  | Reserved for Future Use
| xx-2 |  | 99 |  | Reserved for Future Use
| xx-3 |  | 99 |  | Reserved for Future Use
Miscellaneous | xx-0 |  | 0 |  | Shipping Upcharges
| xx-1 |  | 0 |  | Avante - Invoice Form: add upcharges below subtotal | [5 empty] | Inside delivery, tailgate, liftgate and export pallets
| xx-2 |  | 99 |  | Reserved for Future Use
| xx-3 |  | 99 |  | Reserved for Future Use
| xx-4 |  | 99 |  | Reserved for Future Use
Miscellaneous | xx-0 |  | 0 |  | Production Upcharges
| xx-1 |  | 99 |  | Reserved for Future Use
| xx-2 |  | 99 |  | Reserved for Future Use
| xx-3 |  | 99 |  | Reserved for Future Use
Miscellaneous | xx-0 |  | 0 |  | Shipping Notifications
| xx-1 |  | 99 |  | Reserved for Future Use
| xx-2 |  | 99 |  | Reserved for Future Use
| xx-3 |  | 99 |  | Reserved for Future Use
Miscellaneous | xx-0 |  | 0 |  | CE Alert messages for org/cust/contact
| xx-1 |  | 99 |  | Reserved for Future Use
| xx-2 |  | 99 |  | Reserved for Future Use
| xx-3 |  | 99 |  | Reserved for Future Use
Miscellaneous | xx-0 |  | 0 |  | Master Buyer Functionality
| xx-1 |  | 0 |  | Preferences | [5 empty] | Add new fields and supportive data selects, etc. for various Master Buyer functions
| xx-2 |  | 99 |  | Reserved for Future Use
| xx-3 |  | 99 |  | Reserved for Future Use
| xx-4 |  | 99 |  | Reserved for Future Use
Miscellaneous | xx-0 |  | 0 |  | Price Discrepancies | [5 empty] | flagging in cart, different order acknowledgement, put order(s) on hold, auto-release for onhold orders
| xx-1 |  | 99 |  | Reserved for Future Use
| xx-2 |  | 99 |  | Reserved for Future Use
| xx-3 |  | 99 |  | Reserved for Future Use
Miscellaneous | xx-0 |  | 0 |  | Preference-related logic for defaults | [5 empty] | ie, cradlepacked, no verbal p/o, no verbal order
| xx-1 |  | 99 |  | Reserved for Future Use
| xx-2 |  | 99 |  | Reserved for Future Use
| xx-3 |  | 99 |  | Reserved for Future Use
Miscellaneous | xx-0 |  | 0 |  | Lock Logic - Carts, Quote Changes, etc -
| xx-1 |  | 1 |  | Locking Records - Carts, Quote Changes, etc
| xx-2 |  | 99 |  | Reserved for Future Use
| xx-3 |  | 99 |  | Reserved for Future Use
| xx-4 |  | 99 |  | Reserved for Future Use | [5 empty] | how will we stop multiple people from working on same cart/quote?
Miscellaneous | xx-0 |  | 0 |  | Conversion Programs
| xx-1 |  | 0 |  | Customer comments that will become preferences
| xx-2 |  | 0 |  | Load master order# data for existing orders (after purging old data)
| xx-3 |  | 0 |  | Creating Saved Items from Ashads
| xx-4 |  | 99 |  | Reserved for Future Use
| xx-5 |  | 99 |  | Reserved for Future Use
| xx-6 |  | 99 |  | Reserved for Future Use
Miscellaneous | xx-0 |  | 0 |  | Performance Optimization / Server Response Issues
| xx-1 |  | 5 |  | ShopWidget
| xx-2 |  | 5 |  | Server Response Time
| xx-3 |  | 99 |  | Reserved for Future Use
| xx-4 |  | 99 |  | Reserved for Future Use
| xx-5 |  | 99 |  | Reserved for Future Use
Investigate | 1999-0 |  | 0 |  | Items Requiring Further Investigation
| 1999-1 |  | 5 |  | Customer Item Number Pricing | [5 empty] | Can we save individual prices for certain parts number for a given customer (ideally would be able point to an Override price list for certain items)
| 1999-2 |  | 5 |  | Inventory Allocations | [5 empty] | Ramifications of allocating inventory when an order goes on credit hold
| 1999-3 |  | 5 |  | Order Number Size Change (8 or 9) 7+Suffix | [5 empty] | What needs to change on Avante when order# goes to 8 char (7+suffix) and w/o goes to 9 char
| 1999-4 |  | 5 |  | Automating CIA and COD in Ccard processing | [5 empty] | Automating CIA and COD as part of credit card process (per Dawn - if we happen to be in that area …)
| 1999-5 |  | 5 |  | UI work (smooth out screen jumping)
| 1999-6 |  | 5 |  | Product Description Standardization | [5 empty] | What should be displayed / printed on Web and Labels
| 1999-7 |  | 5 |  | Work Order Numbers | [5 empty] | Dawn was concerned that if multiple mod items on same order work order numbers would be for example 5000000A 5000000B etc
| 1999-8 |  | 99 |  | Reserved for Future Use
| 1999-9 |  | 99 |  | Reserved for Future Use
| 1999-10 |  | 99 |  | Reserved for Future Use
Phase II | 2000-0 |  | 0 |  | Contract Pricing Structure
| 2000-1 |  | 0 |  | Program RPC
| 2000-2 |  | 0 |  | Set up contract pricing input and access in Avante | [5 empty] | For Stock and Mod Items
| 2000-3 |  | 99 |  | Reserved for Future Use
| 2000-4 |  | 99 |  | Reserved for Future Use
| 2000-5 |  | 99 |  | Reserved for Future Use
|  |  | 2 | John | Show Cradlepack option upon search. | Sal
|  |  | 2 | John | Cart - Add MOD item to Cart | Ed
|  |  | 3 |  | Results - show message when can't make MOD item
|  |  | 1 | John | Add MOD items to Cart | Ed
|  |  | 0 | John | Detecting WHS descrepancy for CPU MOD items.
|  |  | 1 | John | Enter YMAC Rules for ALL categories
|  |  | 0 |  | Bundling - Shipping and Packaging work – logic for Ship Instructions, Ship Paid By, and Ship Via