## Summary
Status as of 1/9/14
Task | Status | Avante | UI | AV Rework | UI Rework | Ongoing QA
ShopWidget | In Progress | 0 | 0 | 0 | 0 | 0 | no macchi; database cleanup; ui bug fixes;
Saved Items | In Progress | 0 | 0 | 0 | 0 | 0
Order History | In Progress | 0 | 0 | 0 | 0 | 0
Saved Carts | In Progress | 0 | 0 | 0 | 0 | 0
Share Cart | In Progress | 0 | 0 | 0 | 0 | 0
Active Cart | In Progress | 0 | 0 | 0 | 0 | 0
Checkout | In Progress | 0 | 0 | 0 | 0 | 0
My Account | TBDesigned | 0 | 0 | 0 | 0 | 0
Avante | TBDesigned | 0 | 0 | 0 | 0 | 0
Data Conversions | TBDesigned | 0 | 0 | 0 | 0 | 0
Twitter Feed on page |  | 0 | 1 | 0 | 0 | 0 | "The Experience" not in first launch. Numbers are for twitter feed on page.
Pre Login Func |  | 0 | 0 | 0 | 0 | 0 | This functionality should be in the numbers of the pertinent sections
Mktg/Fat Content |  | 4 | 8 | 3 | 3 | 3 | These numbers are COMPLETE guesses. This line is to represent the "front page" information from the existing site.
CE Web Integration | TBDesigned | 0 | 0 | 0 | 0 | 0
Predictive Ordering | TBDesigned | 3 | 2 | 2 | 2 | 2 | incomplete design
Shared Item |  | 0 | 0 | 0 | 0 | 0 | This is complete however, handling FAX customers is still a problem. Needs to be discussed.
Notifications |  | 4 | 4 | 2 | 2 | 2 | A system needs to be designed on what to tell customers about and how to let them customize what they are told about. For example, when their order ships, when someone empties their cart.
#Days |  | 11 | 15 | 7 | 7 | 7
|  | 2.4 | 1.6 | 2.4 | 1.6 | Various
#Weeks |  | 1.0147 | 1.973 | 0.68133 | 0.973 | Ongonig
Complete Date |  | 2026-08-13 02:28 | 2026-08-19 19:28 | 2026-08-17 20:56 | 2026-08-26 14:56 | Pre-live
Dates as of Prev Week |  | 2014-01-21 | 2014-02-22 | 2014-02-27 | 2014-04-09
Formulas:
Avante = TODAY()+([Avante, row above]*7)
UI = TODAY()+([UI, row above]*7)
AV Rework = [Avante]+([AV Rework, row above]*7)
UI Rework = [UI]+([UI Rework, row above]*7)

## ShopWidget
Task Nbr | Task Description | Avante |  | UI |  | Rework |  | QA | Status/Notes
|  | Days | Rem | Days | Rem | Avante | UI
Status as of 1/9/14
1-0
| Total Days | 0 | 0 | 0 | 0
Overall Rework Factor
Overall QA Factor

## SavedItems
Task Nbr | Task Description | Avante |  | UI |  | Rework |  | QA | Status/Notes
|  | Days | Rem | Days | Rem | Avante | UI
Status as of 1/9/14
2-0
3-0
| Total Days | 0 | 0 | 0 | 0
Overall Rework Factor
Overall QA Factor

## OrderHistory
Task Nbr | Task Description | Avante |  | UI |  | Rework |  | QA | Status/Notes
|  | Days | Rem | Days | Rem | Avante | UI
Status as of 1/9/14
| Total Days | 0 | 0 | 0 | 0
Overall Rework Factor
Overall QA Factor

## SavedCarts
Task Nbr | Task Description | Avante |  | UI |  | Rework |  | QA | Status/Notes
|  | Days | Rem | Days | Rem | Avante | UI
Status as of 1/9/14
| Total Days | 0 | 0 | 0 | 0
Overall Rework Factor
Overall QA Factor

## ShareCart
Task Nbr | Task Description | Avante |  | UI |  | Rework |  | QA | Status/Notes
|  | Days | Rem | Days | Rem | Avante | UI
Status as of 1/9/14
| Total Days | 0 | 0 | 0 | 0
Overall Rework Factor
Overall QA Factor

## ActiveCart
Task Nbr | Task Description | Avante |  | UI |  | Rework |  | QA | Status/Notes
|  | Days | Rem | Days | Rem | Avante | UI
Status as of 1/9/14
| Total Days | 0 | 0 | 0 | 0
Overall Rework Factor
Overall QA Factor

## Checkout
Task Nbr | Task Description | Avante |  | UI |  | Rework |  | QA | Status/Notes
|  | Days | Rem | Days | Rem | Avante | UI
Status as of 1/9/14
| Total Days | 0 | 0 | 0 | 0
Overall Rework Factor
Overall QA Factor

## CEWeb
Task Nbr | Task Description | Avante |  | UI |  | Rework |  | QA | Status/Notes
|  | Days | Rem | Days | Rem | Avante | UI
Status as of 1/9/14
| Total Days | 0 | 0 | 0 | 0
Overall Rework Factor
Overall QA Factor

## Miscellaneous
Task Nbr | Task Description | Avante |  | UI |  | Rework |  | QA | Status/Notes
|  | Days | Rem | Days | Rem | Avante | UI
Status as of 1/9/14
| Total Days | 0 | 0 | 0 | 0
Overall Rework Factor
Overall QA Factor

## DataConversions
Task Nbr | Task Description | Avante |  | UI |  | Rework |  | QA | Status/Notes
|  | Days | Rem | Days | Rem | Avante | UI
Status as of 1/9/14
| Total Days | 0 | 0 | 0 | 0
Overall Rework Factor
Overall QA Factor

## MyAccount
Task Nbr | Task Description | Avante |  | UI |  | Rework |  | QA | Status/Notes
|  | Days | Rem | Days | Rem | Avante | UI
Status as of 1/9/14
| Total Days | 0 | 0 | 0 | 0
Overall Rework Factor
Overall QA Factor

## Note-Questions
Results | Originally we had a line item for Results on the Summary page. Having reviewed the Shop/Results area with
Ed we combined all incomplete functions into one page called ShopWidget. Need to review with JP to be
sure there is no missing functionality.
Miscellaneous | ***Investigate what Avante Reports/Processes are using configurator files to extract data.
I am looking for a list of processes that will require changes when the BAGS/SHEETING/FURN, etc
product lines are combined into a single MOD product line. This means that criteria numbers
may change:
- Search IIPROCESS/BP/LDLIB/AVBP looking for CFQNA<13,x> extractions
- Search IIPROCESS/BP/LDLIB/AVBP looking for CFORDER<13,x> extractions
- Search IIPROCESS/BP/LDLIB/AVBP looking for CFBLDHDR<10,x> extractions
Miscellaneous | ***Investigate/writeup design to only allow NS Made/Buy quotes to be entered via QUO4000. Is there an
easy way to disable the other selections BAGS/SHEETING/TUBING/FURN from the screens? Or should
we bypass the screens entirely and only allow NS as an item number in this screen?
Miscellaneous | ***Investigate how 'shipping notifications' could be sent to customers notifying them that their shipment
has been made:
- Timing - should this be done when updating Avante? What if shipment hasn’t left building yet?
- What email address to use?
- What if customer doesn't accept emails?
- Should notifications be sent for all shipments? CPU's?
Miscellaneous | Investigate what changes will be needed for the new FOB CODE "CPU". I believe CPU (customer pickup)
should follow the rules for COL/3PB in that they have no freight implications. Be sure to check the
freight quote/freight$ calculation programs to make sure that CPU will not go through this logic.
Investigate what should happen with CPU credit card orders -- should they be handled like PPD?

## Defs
Avante Programmers: Wayne, Joe, Janice @ 80% | 2.4
UI Programmers: Ed, Sal @ 80% | 1.6
Technical Designers: John, Judy @ 75% ; Jim, Cathy @ 25% | 2
QA/Test: Susan, Steve, Jim, Owen, Cathy, CE, Mktg

## ToDo
Tab | Task Nbr | Dt Added | Status | Designer | Programming Task Description | Pty | DB Pgmr | Hours | Rem | UI Pgmr | Hours | Rem |  |  | Wiki Programing Document Spec Name | Dt Assigned | St Date
Key to Reporting | 0-0 |  | 1 |  | Status'
| 0-1 |  | 0 |  | 0 = Awaiting Info - can't design yet
| 0-2 |  | 1 |  | 1 = Ready to Design
| 0-3 |  | 2 |  | 2 = Ready for Program
| 0-4 |  | 3 |  | 3 = In QA
| 0-5 |  | 4 |  | 4 = Done
| 0-6 |  | 5 |  | 5 = Investigation
| 0-7 |  | 80 |  | 80 = Bug Fixes
| 0-8 |  | 99 |  | 99 = Reserved for Future Use
ShopWidget | 1-0 |  | 4 |  | Avante - Changes for Rolls, Rolls Cradle packed, Rolls Boxed |  |  | 0 | 0 |  | 0 | 0 | Show just "Rolls" in packaging section so we can show the user Rolls Boxed and Rolls Cradlepacked in results as exact matches.
| 1-1 | 2013-11-25 | 4 | Judy | Modify Packaging Group Description |  | Joe |  | 0
| 1-2 | 2013-11-25 | 4 | Judy | Modify Packaging Default Value |  | Joe |  | 0
| 1-3 |  | 99 |  | Reserved for Future Use
SavedItems | 2-0 |  | 1 |  | New customer part number logic |  |  | 11 | 0 |  | 0 | 0 | including cart logic hover over our part# to see customer part#. Assigning customer part numbers from Saved Items Popup and calling that popup from the Labeling step of checkout, then refreshing labeling screen when they are done with that popup.
| 2-1 | 2013-11-25 | 99 |  | Reserved for Future Use
| 2-2 | 2013-11-25 | 3 | John | UI - Update Checkout Label View |  |  |  |  | Francisco
| 2-3 | 2013-11-25 | 3 | John | UI - Update Saved Items View |  |  |  |  | Sal |  |  | Interfacing that if the customer has a customer item number then bring ack that info
| 2-4 | 2013-11-25 | 3 | John | UI - code retrieval of customer items from Database |  |  |  |  | Sal |  |  | save item popup - display existing customer item number for stock or MOD
| 2-5 | 2013-11-25 | 3 | John | UI - code save of customer items to Database |  |  |  |  | Sal |  |  | saves item
| 2-6 | 2013-11-25 | 3 | John | DB - RPC to return customer items to web |  | Joe
| 2-7 | 2013-11-25 | 1 | John | DB - RPC to save customer items to database |  | John | 3 |  |  |  |  | needs to update cross ref and check to see if iems are getting written correcty
| 2-8 | 2013-11-25 | 1 | Cathy | Conversion - convert items |  | Cathy | 4 |  |  |  |  | new format for customer item numbers (custom and combine 3 description lines to 2
| 2-9 | 2013-11-25 | 99 |  | Reserved for Future Use
| 2-10 | 2013-11-25 | 3 | Cathy | Avante - Modify the Customer Item Number Upload - Part I |  | Joe | [5 empty] | change to write the new CUSTPARTXREF.USR record |  | Programming Specs - Customer Part Numbers | 2013-12-26
| 2-11 | 2013-11-25 | 3 | John | Duplicate Customer Names |  |  |  |  | Sal |  |  | We concatenated the city and state to the name for display
| 2-12 | 2013-11-25 | 3 | Cathy | Avante - Modify Existing Programs to Use CUSTPARTXRF.USR - Part II |  | Joe | [5 empty] | Format for custpart.usr will now have key for custom items to be co*cust*MODnnnn |  | Programming Specs - Customer Part Numbers | 2013-12-26
| 2-13 | 2013-11-25 | 3 | Cathy | Avante - Program to create CUSTPARTXRF.USR - Part I |  | Joe | [5 empty] | Create CUSTPARTXRF.USR for existing items |  | Programming Specs - Customer Part Numbers | 2013-12-26
| 2-14 | 2013-11-25 | 3 | Cathy | Avante - Customer Item Number Maintenance - Part I |  | Joe | [5 empty] | change to write the new CUSTPARTXREF.USR record |  | Programming Specs - Customer Part Numbers | 2013-12-26
| 2-15 | 2013-11-25 | 1 | Cathy | Avante - Customer Item Number Maintenance - Part II |  | Cathy | 2 |  |  |  |  | Modify for the MOD item from Cpartnumber key change |  | Programming Specs - Customer Part Numbers | 2013-12-26
| 2-16 | 2013-11-25 | 1 | Cathy | Avante - Customer Item Number Upload - Part II |  | Cathy | 2 |  |  |  |  | Modify for the MOD item from Cpartnumber key change |  | Programming Specs - Customer Part Numbers | 2013-12-26
| 2-17 |  | 99 |  | Reserved for Future Use
SavedItems | 3-0 |  | 3 |  | Change the saved items record key |  |  | 0 | 0 |  | 0 | 0 | From Contact to Bill-to Number --- Changing the location that the saved MOD items are stored, and changing file structure and programs to use the new structure. Including "finding" an existing MOD item from the Shop widget to pull up existing MOD items based on configuration.
| 3-1 | 2013-11-25 | 3 | John | DB - Create file to hold Mod Item Specification by Bill-to |  | Joe
| 3-2 | 2013-11-25 | 3 | John | DB - Modify File Structure for Contact Item information |  | Joe
| 3-3 | 2013-11-25 | 3 | John | DB - RPC$MODITEM_CREATE |  | Joe | [5 empty] | Update saving of MOD items
| 3-4 | 2013-11-25 | 3 | John | DB - RPC$CONTACTITEM_DELETE |  | Joe | [5 empty] | Delete Billto Level data as well?
| 3-5 | 2013-11-25 | 3 | John | DB - RPC$CONTACTITEM_GETBYFILTER |  | Joe | [5 empty] | Pull info from billto level & Contact level
| 3-6 | 2013-11-25 | 3 | John | DB - RPC$CONTACTITEM_GETBYID |  | Joe | [5 empty] | Pull Info from billto level & Contact Level
| 3-7 | 2013-11-25 | 3 | John | DB - RPC$CONTACTITEM_SAVE |  | Joe
| 3-8 | 2013-11-25 | 3 | John | DB - RPC$ITEMTAG_GETBYFILTER |  | Joe
| 3-9 | 2013-11-25 | 3 | John | DB - RPC$ITEMTAG_GETBYFILTER2 |  | Joe
| 3-10 | 2013-11-25 | 3 | John | DB - RPC$ITEMTAG_SELECT |  | Joe
| 3-11 | 2013-11-25 | 3 | John | DB - RPC$QUOTEITEM_GETBYSAVEDITEM |  | Joe
| 3-12 | 2013-11-25 | 3 | John | DB - RPC$SHAREDITEM_GETBYFILTER |  | Joe
| 3-13 | 2013-11-25 | 3 | John | DB - RPC$SHAREDITEM_SAVE |  | Joe
| 3-14 | 2013-11-25 | 3 | John | DB - RPC$SHIPMENTBUNDLING_GETBYFILTER |  | Joe
| 3-15 |  | 99 |  | Reserved for Future Use
MyAccount | 4-0 |  | 2 |  | Process at Login - Deleting Expired Carts |  |  | 3 | 0 |  | 0 | 0 | Purging "old" carts upon login based on time since last activity date. What defines "old" is a system wide setting.
| 4-1 |  | 2 | John | DB - Write Last Activity Date to SHOPPINGCART.USR |  | Joe | 1.5 | [6 empty] | https://laddawn1.atlassian.net/wiki/display/web/Functional+Spec.+-+Write+Cart+Last+Activity+Date | 2014-01-15
| 4-2 |  | 2 | John | DB - Delete old carts upon user validation based on xxx days old |  | Joe | 1.5 |  |  |  |  | Can carts be deleted by anyone other than the user that created them? |  | https://laddawn1.atlassian.net/wiki/pages/viewpage.action?pageId=27754595 | 2014-01-15
| 4-3 |  | 99 |  | Reserved for Future Use
Checkout | 5-0 |  | 3 |  | Duplicate P/O display in Checkout |  |  | 0 | 0 |  | 0 | 0 | A popup showing the other orders this PO number is used on. Called from Payment screen of checkout.
| 5-1 |  | 3 | John | Create Pop-up for Duplicate PO numbers |  |  |  |  | Sal
| 5-2 |  | 3 | John | Handle user response to pop-up |  |  |  |  | Francisco
| 5-3 |  | 99 |  | Reserved for Future Use
Checkout | 6-0 |  | 1 |  | Order Creation |  |  | 36 | 0 |  | 0 | 0 | Separating bundles to Avante orders and create a master order. Includes number assignment scheme.
| 6-1 |  | 3 | Judy | Determine How To Create Orders from Bundles
| 6-2 |  | 2 | Judy | Create orders from Bundles |  | Wayne | 24
| 6-3 |  | 2 | Judy | Order Creation - Ship With Logic (ship with comment) |  | Wayne | 2 | [7 empty] | 2013-12-30
| 6-4 |  | 3 | Judy | Order Creation - Setting FOB Code for Customer Pickup |  | Wayne | [8 empty] | 2013-12-02 | 2013-12-02
| 6-5 |  | 3 | Judy | ‘Must Ship Today Flag’ |  | Wayne | [5 empty] | setting on order based on time of day and bundle ship date |  |  | 2013-12-02 | 2013-12-02
| 6-6 |  | 3 | Judy | Order source when ce enters order |  | Wayne
| 6-7 |  | 3 | Judy | Creating a new Shipto Customer |  | Wayne
| 6-8 |  | 3 | Judy | Write cart name to SOHDR.USR |  | Wayne
| 6-9 |  | 5 | Judy | Move MOD ‘ashad' and order shipping preference comments | [7 empty] | ‘ashad’ comments and order shipping preference comments forward to new order
| 6-10 |  | 2 | Judy | Add Pallet Type as a w/o comment for MOD Orders |  | Wayne | 2 |  |  |  |  | Pallet Type (from shipping preferences) must be added as a w/o comment for MOD Orders |  |  | 2013-12-30
| 6-11 | 2013-12-19 | 2 | Judy | Add 'Backordered' or 'Ship Complete' comment to order w/backorder |  | Wayne | 4 |  |  |  |  | For ship and b/o bundles, put 'Backorder' comment on the backordered order and nothing on main order. For default bundle shipping everything in 3 days (because of b/o), put a 'ship complete' comment on the order.
| 6-12 | 2013-12-30 | 2 | Judy | Write Shipping Instruction Comments to Sales Order |  | Wayne | 4
| 6-13 | 2014-01-03 | 1 | Judy | Write w/o comment for 'no wooden slats' on Export Pallet jobs |  | Judy | 0 |  |  |  |  | comment automatically goes on work orders for export pallet jobs to NOT use untreated wooden slats
| 6-14 |  | 99 |  | Reserved for Future Use
Checkout | 7-0 |  | 1 |  | Checkout - Labeling |  |  | 10 | 0 |  | 6 | 0 | Completion of the Labeling step of checkout process.
| 7-1 |  | 3 | John | Validations |  |  |  |  | Francisco |  |  | customer part number required, third party, Brandit customer setup
| 7-2 |  | 1 | Judy | DB - Update Labeling to SHOPPINGCART.USR |  | Judy | 6 |  |  |  |  | when user hits save and continue we want to record what they said
| 7-3 |  | 3 | John | Interface with Bartender to Generate Label Images |  |  |  |  | Francisco
| 7-4 |  | 3 | John | Set Up Paging to Step from Label to Label. |  |  |  |  | Francisco
| 7-5 |  | 1 | John | Interface with Saved Items Popup. |  |  |  |  | John | 4 |  | pull up saved items popup with the correct tagging
| 7-6 |  | 3 | John | Refresh Label Image as Needed. |  |  |  |  | Francisco
| 7-7 |  | 1 | John | DB - Retrieve Customer Part Number Information. |  | John | 4 |  |  |  |  | pull customer part number and description onto the label
| 7-8 |  | 3 | John | Return Brandit Information as Customer Object Properties |  |  |  |  | Francisco
| 7-9 |  | 3 | John | Show Correct Options for Label Format |  |  |  |  | Francisco |  |  | label type on top, check box options below, actual part numbers
| 7-10 |  | 1 | CHRIS | Creation of New Label Templates
| 7-11 |  | 3 | John | Handle Adding Label Comment |  |  |  |  | Francisco
| 7-12 |  | 1 | John | UI - Retrieve Customer Part Number Information |  |  |  |  | John | 2
| 7-13 |  | 99 |  | Reserved for Future Use
Checkout | 8-0 |  | 0 |  | Checkout - Addresses |  |  | 0 | 0 |  | 16 | 0 | First step of the checkout process. Where the user selects or adds the ship to address.
| 8-1 |  | 3 | Judy | Check Create Order F2 validations | [7 empty] | only diff is that zip code is entered, then city/state is defaulted from ZIPCODE.USR
| 8-2 |  | 3 | Judy | Update SHOPPINGCART.USR |  | Wayne
| 8-3 |  | 3 | John | Verify that ship-to zip matches cart zip (in case of zip code change) |  |  |  |  | Francisco
| 8-4 |  | 0 | John | Handle changing of Ship-to | [7 empty] | changing of customer number - after getting to summary page - could have some FOB, VIA, or shipping preferences
| 8-5 |  | 1 | John | UI - Handle "TAGGED SHIPTO" |  |  |  |  | John | 16 |  | selecting customer that was just "tagged" but is not a valid customer - has no address
| 8-6 |  | 1 | Judy | DB - Handle "TAGGED SHIPTO" |  | Judy | 0 |  |  |  |  | selecting customer that was just "tagged" but is not a valid customer - has no address
| 8-7 |  | 99 |  | Reserved for Future Use
Checkout | 9-0 |  | 1 |  | Checkout - Payment |  |  | 0 | 0 |  | 5 | 0 | Checkout Payment step. Display / Validate / save.
| 9-1 |  | 3 | Judy | Check Create Order F2 validations | [7 empty] | **done-only diff is CC Name s/b reqd & Exp Date shouldn't default - UI??
| 9-2 |  | 3 | John | Make sure all validations from existing website are in new website (UI?)
| 9-3 |  | 1 | John | Redesign Payment View to new specifications |  |  |  |  | John | 5
| 9-4 |  | 99 |  | Reserved for Future Use
Checkout | 10-0 |  | 0 |  | Checkout - Giving |  |  | 6 | 0 |  | 2 | 0 | Checkout Giving Page
| 10-1 |  | 3 | Judy | Check Create Order F2 validations - | [7 empty] | *** NO GIVING SCREEN ON AVANTE SO NOT NEEDED -
| 10-2 |  | 0 | John | UI - Bypass if CE
| 10-3 |  | 3 | Judy | Update SHOPPINGCART.USR |  | Wayne
| 10-4 |  | 1 | John | UI - hook up response to the order |  |  |  |  | John | 2
| 10-5 |  | 1 | John | DB - hook up response to the order |  | John | 6
| 10-6 |  | 99 |  | Reserved for Future Use
Checkout | 11-0 |  | 0 |  | Checkout - Bundling View |  |  | 8 | 0 |  | 0 | 0 | Complete Bundling page of checkout.
| 11-1 |  | 3 | Judy | Bundling Validation - Ship Via |  | Wayne
| 11-2 |  | 3 | Judy | Bundling Validation - Freight Terms |  | Wayne
| 11-3 |  | 3 | Judy | Bundling Validation - Ship Date |  | Wayne
| 11-4 |  | 3 | Judy | Update Bundling to SHOPPINGCART.USR |  | Janice | [5 empty] | Update all bundling info to SHOPPINGCART.USR | checkout 'save' updating |  |  | 2013-12-11
| 11-5 |  | 3 | Judy | Avante-Comments Maint Screen (Ship Instr) |  | Janice | [5 empty] | Create new web sub-screen from SYS9012 | checkout shipping instructions |  |  | 2013-12-11
| 11-6 |  | 3 | Judy | DB-WEB.COMMENTS.READ (Ship Instr) |  | Janice | [5 empty] | Global prgm to read/return all data from COMMENTS.USR | checkout shipping instructions |  |  | 2013-12-11
| 11-7 |  | 3 | Judy | DB-RPC$COMMENTS_GETBYFILTER (Ship Instr |  | Janice | [5 empty] | Pass all shipping instruction comments from select list by section to UI | checkout shipping instructions |  |  | 2013-12-11
| 11-8 |  | 3 | Judy | DB-RPC$COMMENTS_GETBYID (Ship Instr |  | Janice | [5 empty] | Pass single shipping instruction comment to UI | checkout shipping instructions |  |  | 2013-12-11
| 11-9 |  | 3 | Judy | DB-Save & Continue Updating |  | Janice | [5 empty] | Update shipping instructions to SHOPPINGCART.USR | checkout shipping instructions |  |  | 2013-12-11
| 11-10 |  | 0 | John | preserve (ship via, fob, ship inst) when merging and splitting bundles | [7 empty] | Work needed to preserve (ship via, fob, ship inst) when merging and splitting bundles
| 11-11 | 2013-12-24 | 2 | Judy | DB-Shipping Instructions Enabling/Default Values & Comment Scrn Chng |  | Janice | 8 |  |  |  |  | Send Enabled/Disabled & Default Value for each comment in Shipping Instruct & Add Revenue Chg Code to Comm Scrn
| 11-12 | 2013-12-30 | 3 | John | UI Call Bundling Routines to fill screens from DB |  |  |  |  | Francisco
| 11-13 |  | 99 |  | Reserved for Future Use
ActiveCart | 12-0 |  | 3 |  | Cart - Handle Price expiration of MOD items |  |  | 0 | 0 |  | 0 | 0 | The active cart tab shows the customer what items still have "active" pricing, or pricing that will expire soon. This is about showing the customer the correct cues about their pricing on MOD items.
| 12-1 |  | 3 | John | Create a view for Mod Items |  |  |  |  | Ed
| 12-2 |  | 3 | John | Establish the state of the view and show correct clock icon |  |  |  |  | Ed
| 12-3 |  | 3 | John | Disable Controls for expired items |  |  |  |  | Ed
| 12-4 |  | 3 | John | Creating New Quote from Expired Quote |  |  |  |  | Ed |  |  | Create a new quote from expired quote and save new quote to SHOPPINGCART.USR and remove old
| 12-5 |  | 3 | Judy | DB - Mod item repricing |  | Janice
| 12-7 |  | 99 |  | Reserved for Future Use
ActiveCart | 13-0 |  | 1 |  | Cart - Repricing MOD items in the cart. |  |  | 0 | 0 |  | 0 | 0 | Changing Zip Code, CPU, QTY, Freight Option on the cart will trigger a repricing of the MOD item by calling the pricing routine with the correct flags. A subset of 17-0
| 13-1 |  | 3 | John | Call repricing routine and update existing quote |  | Janice | [5 empty] | qty, and freight option changes
| 13-2 |  | 1 | John | Show MOD price break pop-up for MOD items |  | John | 0 |  |  |  |  | they can change the price breaks from the cart - repricing line reprices price breaks
| 13-3 |  | 99 |  | Reserved for Future Use
| 13-4 |  | 99 |  | Reserved for Future Use
| 13-5 |  | 99 |  | Reserved for Future Use
ActiveCart | 14-0 |  | 1 |  | Cart - Handling Zipcode changes in the Cart. |  |  | 10 | 0 |  | 3 | 0 | The customer is allowed to change the ZIP code for which the cart is built. This change effects availability dates, primary warehouse selection and MOD pricing.
| 14-1 |  | 3 | John | Update availability dates for stock and mod items |  |  |  |  | Ed
| 14-2 |  | 3 | John | Reprice the quote for MOD items (if expired it gets new quote) |  |  |  |  | Ed
| 14-3 |  | 1 | John | DB - Remove checkout address informaton from SHOPPINGCART.USR |  | John | 5 |  |  |  |  | do we want to clear all or partial
| 14-4 |  | 1 | John | DB - Remove checkout bundling informaton from SHOPPINGCART.USR |  | John | 5
| 14-5 |  | 2 | John | UI - Handling Ship-to Zip / Pick-up Changes |  |  |  |  | Ed | 3
| 14-6 |  | 99 |  | Reserved for Future Use
ActiveCart | 15-0 |  | 0 |  | Cart - CE version of contact’s cart (by operator) |  |  | 0 | 0 |  | 0 | 0 | While the customer contact is on the website, and CE logs in as that customer, we don't want them conflicting on the same active cart. So CE will need its own version of the cart when logged in as another contact.
| 15-1 |  | 99 |  | Reserved for Future Use
| 15-2 |  | 99 |  | Reserved for Future Use
| 15-3 |  | 99 |  | Reserved for Future Use
ActiveCart | 16-0 |  | 0 |  | Cart - New print plate logic (no checkout until approval) |  |  | 0 | 0 |  | 32 | 0 | If the MOD item in the cart has a print plate assigned that we do not have the image for the customer must upload the image through the site before being allowed to start the checkout process. This is where they select the PDF on their system and upload it to Laddawn in a status of awaiting approval.
| 16-1 |  | 1 | John | Detect a printed job and show upload link |  |  |  |  | John | 32
| 16-2 |  | 0 | Judy | Plate approvals - stop checkout |  | Judy
| 16-3 |  | 0 | Judy | One Plate for Multiple Quotes |  | Judy
| 16-4 |  | 0 | Judy | Customer Supplied Plates |  | Judy | [5 empty] | do we need this or not?????
| 16-5 |  | 99 |  | Reserved for Future Use
ActiveCart | 17-0 |  | 1 |  | Cart - Changes to Items in a Cart (add, delete , quantity changes) |  |  | 1 | 0 |  | 0 | 0 | A more inclusive statement of 13-0. 13-0 was referring to only MOD items, this is referring to both stock and MOD.
| 17-1 |  | 1 | John | DB - Remove checkout bundling informaton from SHOPPINGCART.USR |  | John | 1 |  |  |  |  | add change delete based on what is done - this refers to the program in 14-4
| 17-2 |  | 1 | John | Update availability dates for stock and mod items |  |  |  |  | John |  |  | they can change the price breaks from the cart - repricing line reprices price breaks
| 17-3 |  | 99 |  | Reserved for Future Use
| 17-4 |  | 99 |  | Reserved for Future Use
| 17-5 |  | 99 |  | Reserved for Future Use
Results | 18-0 |  | 0 |  | Marketplace - When to show MOD Result |  |  | 0 | 0 |  | 0 | 0 | In some circumstances (CPU, or Mktplace Price higher than Laddawn stock) orders cannot be Marketplace orders. This is referring to the work needed to ensure that marketplace MOD items are PPD only and a better price or leadtime than the stock item found. Currently all marketplace orders must be PPD.
| 18-1 |  | 3 | Judy | BP WEB.MODITEM.CHECK - for 'Customer Pickup' if Ziptop |  | Janice | [5 empty] | If 'Customer Pickup' is chosen for Ziptop, do not create a Marketplace MOD Result
| 18-2 |  | 99 |  | Reserved for Future Use
| 18-3 |  | 99 |  | Reserved for Future Use
| 18-4 |  | 99 |  | Reserved for Future Use
OrderHistory | 19-0 |  | 0 |  | Modify results to handle master orders |  |  | 0 | 0 |  | 0 | 0 | Currently Order History brings up list of avante orders. This will need some work to be "master order aware".
| 19-1 |  | 99 |  | Reserved for Future Use
| 19-2 |  | 99 |  | Reserved for Future Use
| 19-3 |  | 99 |  | Reserved for Future Use
OrderHistory | 20-0 |  | 0 |  | Complete Summary Popup |  |  | 0 | 0 |  | 0 | 0 | When the user clicks summary in Order History tab, this is what they will see.
| 20-1 |  | 99 |  | Reserved for Future Use
| 20-2 |  | 99 |  | Reserved for Future Use
| 20-3 |  | 99 |  | Reserved for Future Use
OrderHistory | 21-0 |  | 0 |  | Complete Tracking Popup for all Carriers |  |  | 0 | 0 |  | 0 | 0 | Order history tracking popup works for carriers with online tracking tools that do not require a login. This is about how we handle these issues.
| 21-1 |  | 99 |  | Reserved for Future Use
| 21-2 |  | 99 |  | Reserved for Future Use
| 21-3 |  | 99 |  | Reserved for Future Use
CEWeb | 22-0 |  | 0 |  | Spinning off multiple requests. |  |  | 0 | 0 |  | 0 | 0 | How are we going to handle multiple requests per call. Especially in regards to handling on hold requests and routings.
| 22-1 |  | 99 |  | Reserved for Future Use
| 22-2 |  | 99 |  | Reserved for Future Use
| 22-3 |  | 99 |  | Reserved for Future Use
ShopWidget | 23-0 |  | 0 |  | Default and Validate Zip Code Based on Active Cart |  |  | 0 | 0 |  | 0 | 0 | Handling enter and setting focus back to item number box after add button
| 23-1 |  | 3 | John | UI - default zipcode from active cart if any |  |  |  |  | Ed
| 23-2 |  | 3 | John | UI - Validate the Zip Code when Adding Items |  |  |  |  | Ed
| 23-3 |  | 0 | 2014-01-09 | UI - Changes to the Pop-Up for Zip Code Discrepancies | [7 empty] | Steve to Update Wiki with what is wanted
| 23-4 |  | 99 |  | Reserved for Future Use
CEWeb | 24-0 |  | 0 |  | Send CE to the Web at the right time. |  |  | 0 | 0 |  | 0 | 0 | This means not sending to the web other times.
| 24-1 |  | 99 |  | Reserved for Future Use
| 24-2 |  | 99 |  | Reserved for Future Use
| 24-3 |  | 99 |  | Reserved for Future Use
CEWeb | 25-0 |  | 0 |  | CE & Sales Impersonating a contact. |  |  | 2 | 0 |  | 10 | 0 | How will Laddawn staff impersonate a contact on the website, and what special considerations do we need to take into account. And do CE / CR / Sales have different fields available on the site.
| 25-1 | 2013-12-30 | 3 | Judy | DB - Write Correct Operator Codes to Quotes |  | Joe | [7 empty] | Programming Spec-Add'l Quote Updating | 2013-12-31
| 25-2 | 2013-12-30 | 2 | Judy | DB - Write Correct Operator Code to Orders |  | Wayne | 2 | [6 empty] | Programming Spec-Create Order from Checkout | 2013-12-31
| 25-3 | 2013-12-30 | 1 | John | UI - Carry Port Number Throughout Session |  |  |  |  | John | 10
| 25-4 | 2014-01-14 | 0 | John | DB - Change Authentication to Check for Port Number
| 25-5 |  | 0 |  | NEPB Customer Login | [7 empty] | How will CE and Sales get on the website to build quotes and orders for NEPB customers, who have no sales contacts.
| 25-6 |  | 99 |  | Reserved for Future Use
CEWeb | 26-0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 | 0
| 26-1 |  | 99 |  | Reserved for Future Use
| 26-2 |  | 99 |  | Reserved for Future Use
| 26-3 |  | 99 |  | Reserved for Future Use
CEWeb | 28-0 |  | 5 |  | CE - Multiple Sessions - making it work |  |  | 0 | 0 |  | 0 | 0 | How will CE work if we cannot use multiple web sessions. Initial investigation is done and works in IE* and above, Chrome, not Firefox
| 28-1 |  | 99 |  | Reserved for Future Use | [7 empty] | Ask Franciso if he has knowledge on
| 28-2 |  | 99 |  | Reserved for Future Use
| 28-3 |  | 99 |  | Reserved for Future Use
CEWeb | 29-0 |  | 1 |  | Godzilla - CE Quote Search |  |  | 0 | 0 |  | 0 | 0 | When the user fills out the Shop Widget we will look for that same item in the shopping carts, recent order history, and saved items.
| 29-1 |  | 0 |  | DB - Banner for Similar Items Found | [7 empty] | Determine if there is a match in MOD.ITMMST.USR and signal hit by retuning all MOD item numbers in PART.NBR
| 29-2 |  | 0 |  | UI - Banner for Similar Items Found | [7 empty] | Display correct banner message
| 29-3 |  | 0 |  | UI - Middle tier support | [7 empty] | Determine method to return values from database to front end
29-4
| 29-5 |  | 99 |  | Reserved for Future Use
Miscellaneous | 30-0 |  | 0 | Judy | Miscellaneous Avante Items |  |  | 95 | 0 |  | 4 | 0
| 30-1 |  | 1 |  | Avante - QUO4000 | [7 empty] | remove all custom items except NS
| 30-2 |  | 2 | Judy | Avante - new CPU FOB code |  | Janice | 24 |  |  |  |  | Janice will investigate and make reqd changes to Avante programs for new FOB Code CPU - John or Cathy should check Clippership
| 30-3 |  | 1 | Judy | Avante - SOP4000 & QUO4001 |  | Judy | 4 |  |  |  |  | assign master order# for sample/NS orders - one for one - master order and an A version.
| 30-4 |  | 1 | Judy | Avante - Sales Order Entry and Sales Order Display |  | Judy | 16 |  |  |  |  | searching/viewing orders using master order# - launch screen?
| 30-5 |  | 1 | Judy | Avante - MOD Configuration Report Changes |  | Judy | 16 |  |  |  |  | report changes due to restructure of configuration
| 30-6 |  | 1 | Judy | Avante - Must Ship Today Report |  | Judy | 2 |  |  |  |  | resort by shipment status or must ship today flag
| 30-7 |  | 1 | Judy | Avante - Label Item Description for Marketplace |  | Judy | 4 |  |  |  |  | format has changed to be more like other custom items
| 30-8 |  | 1 | Judy | Avante - Searches |  | Judy | 3 |  |  |  |  | add 'zip code' prompt to the billto # search in c/e requests - for orgs with multiple bill-to's
| 30-9 |  | 1 | Judy | Excel Report - Pallet Info |  | Judy | 8 |  |  |  |  | go-live that lists pallet info that can be entered as preferences
| 30-10 |  | 1 | Cathy | Excel Report - Customer Item Info |  | Cathy | 2 |  |  |  |  | go-live that lists customers using their item numbers so preferences can be set
| 30-11 | 2014-01-09 | 1 | John | Clippership - new CPU FOB Code |  |  |  |  | John | 4 |  | Check clippership to make sure it can handle new FOB Code 'CPU'
| 30-12 | 2014-01-09 | 1 | Judy | DB - Build Label Descriptions |  | Judy | 16 |  |  |  |  | This is what Sal wrote for compliance - needs to be re-written on the back end
| 30-13 |  | 99 |  | Reserved for Future Use
| 30-14 |  | 99 |  | Reserved for Future Use
ShopWidget | 31-0 |  | 1 |  | Continue to Test and Bug Fix the Shop Widget |  |  | 0 | 0 |  | 0 | 0 | We suspect there are remaining bugs in this area that have not yet been found. This is the task of fixing them when they are found.
| 31-1 |  | 99 |  | Reserved for Future Use
| 31-2 |  | 99 |  | Reserved for Future Use
| 31-3 |  | 99 |  | Reserved for Future Use
ShopWidget | 32-0 |  | 0 |  | Validations - Group Validations |  |  | 0 | 0 |  | 25 | 0 | Group validations in the shop widget as explained on the next line.
| 32-1 |  | 1 | John | Display required Fields in Message box. |  |  |  |  | John | 1 |  | Calling required field validation by group. On find and on close of a group. IF the user never goes to a field, field validation never fires so group validation is needed.
| 32-2 |  | 1 | John | Display Marker flags by missing data. |  |  |  |  | John | 24 |  | design has red markers next to missing data
| 32-3 |  | 99 |  | Reserved for Future Use
| 32-4 |  | 99 |  | Reserved for Future Use
ShopWidget | 33-0 |  | 0 |  | Changing Quotes |  |  | 0 | 0 |  | 0 | 0 | Retrieving a saved item with its quote intact, having the website tracking whether or not it has revised a quote already in this session, and having the pricing routines return prices based on the correct information.
| 33-1 |  | 0 | John | Change Find button to Ask Modify or Create New Quote |  |  |  |  | John |  |  | Pulling up a saved item and making changes. Exp vs unexp/unconverted; reprice/new price; increment config and overlay saved items
| 33-2 |  | 0 | John | Build PopUp to Ask Question |  |  |  |  | John
| 33-3 |  | 0 | John | Preserve CONFIG.REV While Making Changes |  |  |  |  | John
| 33-4 |  | 99 |  | Reserved for Future Use
ShopWidget | 34-0 |  | 0 |  | Extended Descriptions |  |  | 0 | 0 |  | 1 | 0 | The plan is to have a routine build the extended description and specification based on the answers the user supplied during the configuration stage. Maketing has not yet supplied the values to link to the given questions for this system to be implemented.
| 34-1 |  | 0 | OWEN | Marketing notes for extended descriptions |  |  |  |  | OWEN |  |  | Need Marketing Approval for the format and the approach.
| 34-2 |  | 1 | John | DB - Call Building of Extended Description for MOD items |  |  |  |  | John | 1
| 34-3 |  | 99 |  | Reserved for Future Use
| 34-4 |  | 99 |  | Reserved for Future Use
ShopWidget | 35-0 |  | 0 |  | Atlanta Production |  |  | 12 | 0 |  | 0 | 0 | Rules for assigning Atlanta as the production facility on a MOD Order - David providing rules
| 35-1 |  | 1 | Judy | DB - Modify manufacturing facility assignment process |  | Judy | 8
| 35-2 |  | 0 | Judy | DB - Modify bottomseal/sideweld pass/fail rules to add Atlanta
| 35-3 |  | 1 | Judy | Avante - Modify Avante programs to add Atlanta as a production facility |  | Judy | 4
| 35-4 |  | 99 |  | Reserved for Future Use
| 35-5 |  | 99 |  | Reserved for Future Use
ShopWidget | 36-0 |  | 0 |  | Level 3 defaults |  |  | 0 | 0 |  | 0 | 0 | Values that are passed in to the search results routine are considered even when that category is disabled. We want to ignore disabled fields to get the correct information back in results.
| 36-1 |  | 4 | Judy | Widget Level 3 Defaults |  | Joe | [5 empty] | null out defaults if level 3 disabled
| 36-2 |  | 99 |  | Reserved for Future Use
| 36-3 |  | 99 |  | Reserved for Future Use
| 36-4 |  | 99 |  | Reserved for Future Use
SavedCarts | 37-0 |  | 0 |  | Results |  |  | 4 | 0 |  | 6 | 0
| 37-1 |  | 1 | John | Share count on results page |  |  |  |  | John | 6 |  | the count of how many user has shared the cart.
| 37-2 |  | 1 | John | DB - Record the Share Event |  | John | 4 |  |  |  |  | When the user hits share when sharing a cart we need to record in the database what was sent so we can display it from saved carts.
| 37-3 |  | 99 |  | Reserved for Future Use
| 37-4 |  | 99 |  | Reserved for Future Use
SavedCarts | 38-0 |  | 0 |  | Handling Working on Someone Else's Cart |  |  | 0 | 0 |  | 0 | 0 | Saved Carts allows you to find and "activate" someone else's cart. We need to figure out how that is going to work as far as who owns the order that gets created, and what notifications need to happen, and how.
| 38-1 |  | 0 | John | UI Changes | [7 empty] | Changes to the UI / Avante based on preferences
| 38-2 |  | 0 | Judy | Avante DB Changes
| 38-3 |  | 99 |  | Reserved for Future Use
| 38-4 |  | 99 |  | Reserved for Future Use
| 38-5 |  | 99 |  | Reserved for Future Use
39-0
| 39-1 |  | 99 |  | Reserved for Future Use
| 39-2 |  | 99 |  | Reserved for Future Use
| 39-3 |  | 99 |  | Reserved for Future Use
ShareCart | 40-0 |  | 0 |  | Redisplay Shared Cart from Saved Carts |  |  | 8 | 0 |  | 20 | 0 | We need to display the information that was shared by our customers to their colleagues and customers.
| 40-1 |  | 1 | John | UI - Create the PopUp to Display Shared Carts |  |  |  |  | John | 20
| 40-2 |  | 1 | John | DB - Return Shared Cart Information |  | John | 8
| 40-3 |  | 99 |  | Reserved for Future Use
ActiveCart | 41-0 |  | 0 |  | MOD Item Descriptions |  |  | 8 | 0 |  | 0 | 0 | We need to establish how we are going to return descriptions in the different areas of the site for MOD items since they aren't really stored anywhere.
| 41-1 |  | 1 | John | DB - Imbed the Print Plate Upload Link |  | John | 6
| 41-2 |  | 1 | John | DB - Return Built Descriptions to Web |  | John | 2
| 41-3 |  | 99 |  | Reserved for Future Use
ActiveCart | 42-0 |  | 0 |  | Freight Dropdown |  |  | 0 | 0 |  | 0 | 0 | We have to respond to the user changing this field from the cart.
| 42-1 |  | 3 |  | Reprice the Mod item and Update Quote when Freight Selected |  |  |  |  | Ed |  |  | included / not incuded drop down in the cart
| 42-2 |  | 2 |  | Change Drop Down to on CPU Selection |  |  |  |  | Ed |  |  | when they choose cpu box to dropdown goes away and logic is based on freight not included
| 42-3 |  | 99 |  | Reserved for Future Use
ActiveCart | 43-0 |  | 0 |  | Total Items |  |  | 2 | 0 |  | 0 | 0 | Currently the item count on the cart tab does not include MOD items, we need to fix this.
| 43-1 |  | 1 | John | DB - Change Cart Value Program to Include MOD items |  | John | 2
| 43-2 |  | 99 |  | Reserved for Future Use
| 43-3 |  | 99 |  | Reserved for Future Use
44-0
| 44-1 |  | 99 |  | Reserved for Future Use
| 44-2 |  | 99 |  | Reserved for Future Use
| 44-3 |  | 99 |  | Reserved for Future Use
ActiveCart | 45-0 |  | 0 |  | Quick Add |  |  | 0 | 0 |  | 0 | 0 | Handling enter and setting focus back to item number box after add button
| 45-1 |  | 3 | John | Using Quick Add - Set Focus Back to to Item Number |  |  |  |  | Ed
| 45-2 |  | 99 |  | Reserved for Future Use
| 45-3 |  | 99 |  | Reserved for Future Use
46-0
| 46-1 |  | 99 |  | Reserved for Future Use
| 46-2 |  | 99 |  | Reserved for Future Use
| 46-3 |  | 99 |  | Reserved for Future Use
ShopWidget | 47-0 |  | 0 |  | Results - show message when can't make MOD item |  |  | 2 | 0 |  | 0 | 0 | Establishing when we can make a MOD item is working correctly, but we may need to rewrite the wording.
| 47-1 |  | 1 | John | DB - Return Correct Wording for Banner Message |  | John | 2
| 47-2 |  | 99 |  | Reserved for Future Use
| 47-3 |  | 99 |  | Reserved for Future Use
ShopWidget | 48-0 |  | 0 |  | Detecting WHS descrepancy for CPU MOD items. |  |  | 0 | 0 |  | 12 | 0 | We need to display a message telling the customer this item may not be made at their nearest warehouse when it is a CPU search, This means we need to detect when that is the case.
| 48-1 |  | 1 | Judy | DB - Need to Detect that Mfg Whs is Different than Primary Zip Whs |  | Judy | ??
| 48-2 |  | 1 | John | UI - Display Discrepancey Whs Mgs in Banner |  |  |  |  | John | 8
| 48-3 |  | 1 | John | UI - Disable Accordingly Until they Make the Correct Zip Change |  |  |  |  | John | 4
| 48-4 |  | 99 |  | Reserved for Future Use
ShopWidget | 49-0 |  | 1 |  | Enter YMAC Rules for ALL categories |  |  | 0 | 0 |  | 0 | 0 | YMAC searches is based on rules that are entered into Avante (SYS9026), I need to enter the basis of these rules to start.
| 49-1 |  | 1 | JIM | Reserved for Future Use |  | JIM | 0
| 49-2 |  | 99 |  | Reserved for Future Use
| 49-3 |  | 99 |  | Reserved for Future Use
ShopWidget | 50-0 |  | 0 |  | Banner Search - Search by Customer Part# or MOD Item Nbr |  |  | 28 | 0 |  | 0 | 0 | Add ability - This is in addition to the stock item# search already in place
| 50-1 | 2013-12-11 | 1 | Judy | DB - Update RPC$SEARCHFIELD_GETDEFAULTVALUES |  | Judy | 20 |  |  |  |  | Populate the Widget with the correct values
| 50-2 |  | 1 | John | DB - Update RPC$PRODUCT ITEM_GETBYPARTNBR |  | John | 8 |  |  |  |  | Check for customer item first, then check stock then Mod
| 50-3 |  | 99 |  | Reserved for Future Use
| 50-4 |  | 99 |  | Reserved for Future Use
OrderHistory | 51-0 |  | 0 |  | Order History Summary |  |  | 0 | 0 |  | 0 | 0 | The summary page of the order history results is not done.
| 51-1 |  | 99 | John | Reserved for Future Use
| 51-2 |  | 99 |  | Reserved for Future Use
| 51-3 |  | 99 |  | Reserved for Future Use
OrderHistory | 52-0 |  | 0 |  | Remake Orders - Re-Order Page |  |  | 0 | 0 |  | 0 | 0 | Remake order logic needs to be added for CE only
| 52-1 |  | 99 | **DISCUSS | Reserved for Future Use
| 52-2 |  | 99 |  | Reserved for Future Use
| 52-3 |  | 99 |  | Reserved for Future Use
ActiveCart | 53-0 |  | 0 |  | Stock & MOD Price Overrides (Misc$) |  |  | 0 | 0 |  | 0 | 0 | Detecting the user as someone that can override prices, giving them an interface to change the prices in the cart, and save those "overrides"
| 53-1 |  | 99 |  | Reserved for Future Use
| 53-2 |  | 99 |  | Reserved for Future Use
| 53-3 |  | 99 |  | Reserved for Future Use
Checkout | 54-0 |  | 0 |  | Checkout - Summary |  |  | 0 | 0 |  | 0 | 0 | The summary page for checkout is a work in progress.
| 54-1 |  | 1 | John | UI - Complete Bundling Stage
| 54-2 |  | 1 |  | UI - CC Box DropDown - Auto Complete | [7 empty] | Only allow people in sales org contacts - give message for email addresses outside the sales org
|  |  | 1 |  | UI - Change to say "Copy Order Summary To"
|  |  | 1 |  | DB - Default CC to Sales Org Contact
|  |  | 1 |  | UI - Warning PopUp for Freeform CC | [7 empty] | warn when this person is not in the sales organization
| 54-3 |  | 99 |  | Reserved for Future Use
Checkout | 55-0 |  | 0 |  | Handling Working with Someone Else's Cart |  |  | 0 | 0 |  | 0 | 0
| 55-1 |  | 99 |  | Reserved for Future Use
| 55-2 |  | 99 |  | Reserved for Future Use
| 55-3 |  | 99 |  | Reserved for Future Use
Checkout | 56-0 |  | 0 |  | Add Order Total Panel |  |  | 0 | 0 |  | 0 | 0 | The order total panel is the section on the checkout pages where the user sees the order total and any order charges we are charging.
| 56-1 |  | 0 |  | DB - Calculate Order Total | [7 empty] | Sum Stock Items, MOD Items, Order Upcharge, and Sales Tax
| 56-2 |  | 99 |  | Reserved for Future Use
| 56-3 |  | 99 |  | Reserved for Future Use
Checkout | 57-0 |  | 0 |  | Labeling |  |  | 0 | 0 |  | 0 | 0 | Writing the labeling step of the checkout process. Including interfacing with Bartender.
| 57-1 |  | 0 |  | Handle Third Party Labels
| 57-2 |  | 99 |  | Reserved for Future Use
| 57-3 |  | 99 |  | Reserved for Future Use
| 57-4 |  | 99 |  | Reserved for Future Use
Checkout | 58-0 |  | 0 |  | Super User Setup |  |  | 0 | 0 |  | 0 | 0 | Allowing the user to choose what bill to they want to work under, and changing filtering and notifications to that end.
| 58-1 |  | 99 |  | Reserved for Future Use
| 58-2 |  | 99 |  | Reserved for Future Use
| 58-3 |  | 99 |  | Reserved for Future Use
Checkout | 59-0 |  | 0 |  | Checkout Labeling - Build Content of the Page |  |  | 0 | 0 |  | 0 | 0
| 59-1 |  | 99 |  | Reserved for Future Use
| 59-2 |  | 99 |  | Reserved for Future Use
| 59-3 |  | 99 |  | Reserved for Future Use
Checkout | 60-0 |  | 0 |  | Checkout Labeling - Build Label Image |  |  | 0 | 0 |  | 0 | 0
| 60-1 |  | 99 |  | Reserved for Future Use
| 60-2 |  | 99 |  | Reserved for Future Use
| 60-3 |  | 99 |  | Reserved for Future Use
Miscellaneous | 61-0 |  | 0 |  | Cross Browser Support |  |  | 0 | 0 |  | 0 | 0 | Testing on Multiple Platforms / Issues with IE8
| 61-1 |  | 99 |  | Reserved for Future Use
| 61-2 |  | 99 |  | Reserved for Future Use
| 61-3 |  | 99 |  | Reserved for Future Use
Miscellaneous | 62-0 |  | 0 |  | Improve Banner Message Wording |  |  | 0 | 0 |  | 0 | 0 | Already mentioned above.
| 62-1 |  | 99 |  | Reserved for Future Use
| 62-2 |  | 99 |  | Reserved for Future Use
| 62-3 |  | 99 |  | Reserved for Future Use
Miscellaneous | 63-0 |  | 0 |  | Avante Config Reports and Logic (mentioned above??) |  |  | 0 | 0 |  | 0 | 0 | Due to configuration creiteria changes and part number changes
| 63-1 |  | 99 |  | Reserved for Future Use
| 63-2 |  | 99 |  | Reserved for Future Use
| 63-3 |  | 99 |  | Reserved for Future Use
Miscellaneous | 64-0 |  | 0 |  | Quote and Ack Forms |  |  | 0 | 0 |  | 0 | 0 | No change to form layout. Continue to use for NS quote/orders & sample orders.
| 64-1 |  | 0 |  | Link From Web to Avante for Faxed Ackn
| 64-2 |  | 0 |  | Link From Avante to Web to re-send Order Ack
| 64-3 |  | 0 |  | Add checkout Shipping Upcharges | [7 empty] | Determine if we should show details or no detail - below subtotal
| 64-4 |  | 0 |  | Master Order Numbers On Optio Forms
| 64-5 | 2013-10-08 | 5 |  | Possible layout change for bundling details
| 64-6 |  | 99 |  | Reserved for Future Use
| 64-7 |  | 99 |  | Reserved for Future Use
| 64-8 |  | 99 |  | Reserved for Future Use
Miscellaneous | 65-0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 | 0
| 65-1 |  | 99 |  | Reserved for Future Use
| 65-2 |  | 99 |  | Reserved for Future Use
| 65-3 |  | 99 |  | Reserved for Future Use
Miscellaneous | 66-0 |  | 0 |  | Order Creation - Credit Hold - for Master Orders |  |  | 0 | 0 |  | 0 | 0 | Put entire master order on hold (all sub-orders) - Stock will not be allocated when put on hold
| 66-1 |  | 99 |  | Reserved for Future Use
| 66-2 |  | 99 |  | Reserved for Future Use
| 66-3 |  | 99 |  | Reserved for Future Use
Miscellaneous | 67-0 |  | 0 | Judy | Order Creation - Special Instructions / Comments |  |  | 0 | 0 |  | 0 | 0 | On the shipping and packaging step of checkout this is the "special instructions" part where the user uses their preferences to set options on the order like call for appointment, or set pallet options.
| 67-1 |  | 99 |  | Reserved for Future Use
| 67-2 |  | 99 |  | Reserved for Future Use
| 67-3 |  | 99 |  | Reserved for Future Use
Miscellaneous | 68-0 |  | 0 |  | Order Creation Upcharges |  |  | 0 | 0 |  | 0 | 0 | Capturing and passing along the correct upcharges on an order.
| 68-1 |  | 99 |  | Reserved for Future Use
| 68-2 |  | 99 |  | Reserved for Future Use
| 68-3 |  | 99 |  | Reserved for Future Use
Miscellaneous | 69-0 |  | 0 |  | Creation of c/e request(s) |  |  | 0 | 0 |  | 0 | 0 | *** this logic applies to other areas of site, not just orders
| 69-1 |  | 99 |  | Reserved for Future Use
| 69-2 |  | 99 |  | Reserved for Future Use
| 69-3 |  | 99 |  | Reserved for Future Use
Miscellaneous | 70-0 |  | 0 | Judy | Shipping Upcharges |  |  | 0 | 0 |  | 0 | 0 | Folded into the upcharges above.
| 70-1 |  | 0 |  | Avante - Invoice Form: add upcharges below subtotal | [7 empty] | Inside delivery, tailgate, liftgate and export pallets
| 70-2 |  | 99 |  | Reserved for Future Use
| 70-3 |  | 99 |  | Reserved for Future Use
| 70-4 |  | 99 |  | Reserved for Future Use
Miscellaneous | 71-0 |  | 0 |  | Production Upcharges |  |  | 0 | 0 |  | 0 | 0
| 71-1 |  | 99 |  | Reserved for Future Use
| 71-2 |  | 99 |  | Reserved for Future Use
| 71-3 |  | 99 |  | Reserved for Future Use
Miscellaneous | 72-0 |  | 0 |  | Shipping Notifications |  |  | 0 | 0 |  | 0 | 0 | Notifications for Customer Pickups & based on customer preference (call me when shipped)
| 72-1 | 2013-12-30 | 0 |  | Notify Customer When CPU is Ready
| 72-2 |  | 99 |  | Reserved for Future Use
| 72-3 |  | 99 |  | Reserved for Future Use
Miscellaneous | 73-0 |  | 0 |  | CE Alert messages for org/cust/contact |  |  | 0 | 0 |  | 0 | 0
| 73-1 |  | 99 |  | Reserved for Future Use
| 73-2 |  | 99 |  | Reserved for Future Use
| 73-3 |  | 99 |  | Reserved for Future Use
Miscellaneous | 74-0 |  | 0 |  | Master Buyer Functionality |  |  | 0 | 0 |  | 0 | 0 | Duplicate from above.
| 74-1 |  | 0 |  | Preferences | [7 empty] | Add new fields and supportive data selects, etc. for various Master Buyer functions
| 74-2 |  | 99 |  | Reserved for Future Use
| 74-3 |  | 99 |  | Reserved for Future Use
| 74-4 |  | 99 |  | Reserved for Future Use
Miscellaneous | 75-0 |  | 0 |  | Price Discrepancies |  |  | 0 | 0 |  | 0 | 0 | flagging in cart, different order acknowledgement, put order(s) on hold, auto-release for onhold orders
| 75-1 |  | 99 |  | Reserved for Future Use
| 75-2 |  | 99 |  | Reserved for Future Use
| 75-3 |  | 99 |  | Reserved for Future Use
Miscellaneous | 76-0 |  | 0 |  | Preference-related logic for defaults |  |  | 0 | 0 |  | 0 | 0 | ie, cradlepacked, no verbal p/o, no verbal order, release order in xx hours when price discrepancy
| 76-1 |  | 99 |  | Reserved for Future Use
| 76-2 |  | 99 |  | Reserved for Future Use
| 76-3 |  | 99 |  | Reserved for Future Use
Miscellaneous | 77-0 |  | 0 |  | Lock Logic - Carts, Quote Changes, etc - |  |  | 0 | 0 |  | 0 | 0 | Locking items for changes to prevent other users from modifyin at the same time.
| 77-1 |  | 1 |  | Locking Records - Carts, Quote Changes, etc
| 77-2 |  | 99 |  | Reserved for Future Use
| 77-3 |  | 99 |  | Reserved for Future Use
| 77-4 |  | 99 |  | Reserved for Future Use | [7 empty] | how will we stop multiple people from working on same cart/quote?
DataConversions | 78-0 |  | 0 |  | Conversion Programs |  |  | 4 | 0 |  | 0 | 0 | How will we migrate our data from the current setup to the future information structure of the new site.
| 78-1 |  | 0 |  | Customer comments that will become preferences
| 78-2 |  | 1 | Judy | Load master order# data for existing orders (after purging old data)
| 78-3 |  | 1 | Judy | Creating MOD items from Ashads | [7 empty] | Create MODITMMST.USR all item data and QUOTE numbers as well as CUSTPART.USR CUSTPARTXRF.USR at the bill-to level, changing key to custpart - start with bp WEB.CON VERT.CONFIG - update quote and sales order with MOD item - use work file by customer for matching mod items
| 78-4 |  | 1 | Judy | Merge/Purge Duplicate Ship-to Customers | [7 empty] | We have a number of duplicate ship-to customers - need to remove duplicates in Avante
| 78-5 | 2013-12-30 | 2 | Judy | Update ITMMST w/newest material data from Cliff's Spreadsheet |  | Wayne | 4 |  |  |  |  | Cliff has added materials to misc items - update spreadsheet & SYSTBL with new material options (ie, Steel)
| 78-6 | 2013-12-30 | 1 | Judy | Clean-up Ship Via for Ship-to and Drop Ship Customers | [7 empty] | Set all to BW - DO NOT TOUCH BILL TO RECORDS
|  |  | 1 | Judy | Reformat Marketplace Descriptions in SODET | [7 empty] | Judy changed the desriptions
| 78-7 |  | 99 |  | Reserved for Future Use
Miscellaneous | 79-0 |  | 0 |  | Performance Optimization / Server Response Issues |  |  | 0 | 0 |  | 0 | 0 | Streamlining the functions supporting the site so that it seems as fast as possible without sacrificing integrity.
| 79-1 |  | 5 |  | ShopWidget
| 79-2 |  | 5 |  | Server Response Time
| 79-3 |  | 99 |  | Reserved for Future Use
| 79-4 |  | 99 |  | Reserved for Future Use
| 79-5 |  | 99 |  | Reserved for Future Use
Miscellaneous | 80-0 |  | 0 |  | Picking Slip |  |  | 0 | 0 |  | 0 | 0 | Modify 'date heading' on warehouse picking slip (Arrive On, Ship On, Ship On or Before)
| 80-1 | 2013-12-20 | 1 | Judy | Date Box Heading to Ship On, Arrive On, or Ship On or Before
| 80-2 |  | 99 |  | Reserved for Future Use
| 80-3 |  | 99 |  | Reserved for Future Use
| 80-4 |  | 99 |  | Reserved for Future Use
ShopWidget | 81-0 | 2013-12-30 | 1 |  | Stock Selections for Centerfold Sheeting & LLD |  |  | 4 | 0 |  | 0 | 0 | Folded width is entered, RPC needs to take width x 2 for selection
| 81-1 |  | 1 | John | Update RPC$WEBPRODUCTITEM_GETBYFILTER For Cfold | [7 empty] | RPC$WEBPRODUCTITEM_GETBYFILTER must double the entered width for folded product categories.
| 81-2 | 2014-01-13 | 2 | Judy | Update RPC$WEBPRODUCTITEM_GETBYFILTER For LLD |  | Wayne | 2 |  |  |  |  | Add a stock selection for Std Hexene Blend or Octene when Material = LLD |  | Programming Spec-Web Search Results | 2014-01-13
| 81-3 |  | 99 |  | Reserved for Future Use
| 81-4 |  | 99 |  | Reserved for Future Use
ShopWidget | 82-0 | 2014-01-03 | 0 |  | New Shop Widget Product Categories |  |  | 2 | 0 |  | 0 | 0 | Add Black Conductive Bags under Poly Bags and Blk Cond Tubing under Tubing & Sleeves
| 82-1 | 2014-01-03 | 3 | Judy | Add Black Conductive Tubing and Bag Categories |  | Judy | 2 |  |  |  |  | Add to SYS9026 and disable level 2 and level 3 entry. Check stock select after Cliff adds catalog codes to ITMMST
| 82-2 | 2014-01-06 | 0 | Judy | Add Amber Zip Tops to Shop Widget Category (awaiting info from Cliff) | [7 empty] | Awaiting info from Cliff on stock Amber Ziptops
| 82-3 |  | 99 |  | Reserved for Future Use
Results | 83-0 | 2014-01-10 | 0 |  | Check for MOD Item match before showing MOD Result |  |  | 0 | 0 |  | 0 | 0 | When returning a MOD Result, check to see if there is an exact match for this item in the billto's MOD.ITMMST.USR file. If so, display result with the MOD Item# so that it can't be duplicated. What do we use for packout? Default or packout of first exact match we find? What if packout is changed in results ... look to see if that's a different MOD Item?
| 83-1 |  | 99 |  | Reserved for Future Use
| 83-2 |  | 99 |  | Reserved for Future Use
| 83-3 |  | 99 |  | Reserved for Future Use
| 84-0 | [6 empty] | 0 | 0 |  | 0 | 0
| 84-1 |  | 99 |  | Reserved for Future Use
| 84-2 |  | 99 |  | Reserved for Future Use
| 84-3 |  | 99 |  | Reserved for Future Use
| 85-0 | [6 empty] | 0 | 0 |  | 0 | 0
| 85-1 |  | 99 |  | Reserved for Future Use
| 85-2 |  | 99 |  | Reserved for Future Use
| 85-3 |  | 99 |  | Reserved for Future Use
| 86-0 | [6 empty] | 0 | 0 |  | 0 | 0
| 86-1 |  | 99 |  | Reserved for Future Use
| 86-2 |  | 99 |  | Reserved for Future Use
| 86-3 |  | 99 |  | Reserved for Future Use
| 87-0 | [6 empty] | 0 | 0 |  | 0 | 0
| 87-1 |  | 99 |  | Reserved for Future Use
| 87-2 |  | 99 |  | Reserved for Future Use
| 87-3 |  | 99 |  | Reserved for Future Use
QA Reporting | 800-0 |  |  |  | Assigned Bug Fixes |  |  | 0 | 0 |  | 0 | 0
and Bug Fixes | 800-1 | 2014-01-08 | 80 |  | Ed - Fixing Bugs |  |  |  |  | Ed |  |  |  |  | QA Reporting and Tracking | 2014-01-08
| 800-2 | 2014-01-08 | 80 |  | Francisco - Fixing Bugs |  |  |  |  | Francisco |  |  |  |  | QA Reporting and Tracking | 2014-01-08
| 800-3 | 2014-01-08 | 80 |  | Janice - Fixing Bug |  | Janice | [7 empty] | QA Reporting and Tracking | 2014-01-08
| 800-4 | 2014-01-08 | 80 |  | Joe - Fixing Bug |  | Joe | [7 empty] | QA Reporting and Tracking | 2014-01-08
| 800-5 | 2014-01-08 | 80 |  | Sal - Fixing Bug |  |  |  |  | Sal |  |  |  |  | QA Reporting and Tracking | 2014-01-08
| 800-6 | 2014-01-08 | 80 |  | Wayne - Fixing Bug |  | Wayne | [7 empty] | QA Reporting and Tracking | 2014-01-08
| 800-7 |  | 99 |  | Reserved for Future Use
| 800-8 |  | 99 |  | Reserved for Future Use
Investigate | 1999-0 |  | 0 |  | Items Requiring Further Investigation
| 1999-1 |  | 5 |  | Customer Item Number Pricing | [7 empty] | Can we save individual prices for certain parts number for a given customer (ideally would be able point to an Override price list for certain items)
| 1999-2 |  | 5 |  | Inventory Allocations | [7 empty] | Ramifications of allocating inventory when an order goes on credit hold (decided we didn't need to do this ….)
| 1999-3 |  | 5 |  | Order Number Size Change (8 or 9) 7+Suffix | [7 empty] | What needs to change on Avante when order# goes to 8 char (7+suffix) and w/o goes to 9 char
| 1999-4 |  | 5 |  | Automating CIA and COD in Ccard processing | [7 empty] | Automating CIA and COD as part of credit card process (per Dawn - if we happen to be in that area …)
| 1999-5 |  | 5 |  | UI work (smooth out screen jumping)
| 1999-6 |  | 5 |  | Product Description Standardization | [7 empty] | What should be displayed / printed on Web and Labels
| 1999-7 |  | 5 |  | Work Order Numbers | [7 empty] | Dawn was concerned that if multiple mod items on same order work order numbers would be for example 5000000A 5000000B etc
| 1999-8 | 2013-12-19 | 5 |  | Releasing B/O Pickslips only when inventory is available | [7 empty] | Look into a pre-process that sets a release flag on the backordered order. Create Pickslips would check for release flag as part of SODEL select.
| 1999-9 | 2013-12-30 | 5 | Judy | Revert AVBP EPCS0018.1 back to std version if possible | [7 empty] | AVBP missing logic from tasks 100955, 101093, and 101022. Have to set USERDATA variable for this to work with standard program. If we can't revert, must add missing logic.
| 1999-10 |  | 99 |  | Reserved for Future Use
| 1999-11 |  | 99 |  | Reserved for Future Use
Phase II | 2000-0 |  | 0 |  | Contract Pricing Structure
| 2000-1 |  | 0 |  | Program RPC
| 2000-2 |  | 0 |  | Set up contract pricing input and access in Avante | [7 empty] | For Stock and Mod Items (ONLY INTENDED FOR MOD ITEMS - CURRENTLY STAPLES AND ULINE)
| 2000-3 |  | 0 |  | NS Items on the Web
| 2000-4 |  | 0 |  | Samples on the Web
| 2000-5 |  | 99 |  | Reserved for Future Use
| 2000-6 |  | 99 |  | Reserved for Future Use
| 2000-7 |  | 99 |  | Reserved for Future Use