## Hot List
Work in process |  | Est Comp Date | Est Live Date
| Contract Pricing | 2015-06-16 | 2015-06-17 | 6546 - Joe - Started programming on Tuesday, he should be done by Monday. Judy will QA/Rework on Tuesday. Ready to roll on Wednesday 6/17. There is one program conflict with Pricing Program.
| Item Specific Work Order Comments | 2015-06-26 | 2015-06-29 | Sal (UI) - Janice (DB) - Programming should be completed by next Thursday. QA/Rework on Thursday Friday. Ready to roll Monday.
| Marketplace Pre-Opened Bags on a Roll | 2015-06-19 | 2015-06-29 | 6954 - Wayne - All programming done with exception of cost/price hookup to Excel, Excel will not be available on server until Monday after reboot, testing/rework will begin Tuesday. Two additional items have been added by Tom. Judy will write these up today and Wayne will program. These should also be ready by Tuesday for testing. Unknown potential issues with Excel.
| Marketplace Zip Tops showing LIVE CHAT for price on Anti Static Pink/Clear IMPORT result |  |  | 7849 - Wayne - ON HOLD - (need info from Tom)
| Next phase Tag Manager | 2015-06-16 | 2015-06-17 | Ed - Can be ready by next week if we are ready to have him work on them.
! | Expand widget's Marketplace capabilities
| Marketplace - Amber Zip Tops |  |  | 8298 - Wayne
| Marketplace Registered Printed Zip Tops |  |  | 6955 - If Amazing Print not implemented, requires changes to current print menu - some throwaway, some not.
| Marketplace Registered Printed Layflats |  |  | 6956 - Same issue as above.
WHAT'S NEXT
1 | Susan's Feeder List
Recently resolved
| Program widget to accept new printing capabilities |  |  | 1942, 6276 - Janice
| Tag Manager - Tracking of Orders |  |  | 8409 - Ed
| Tag Manager - Tracking User Navigation/Site Traffic |  |  | 8222 - Ed
| Changes to Order History, dynamic filtering |  |  | 8310 - Joe, DB side of ticket 8707
| Change text on shop printing for 24" plates |  |  | 8147 - Sal
See help desk report for complete list of updates to live.