## Sheet1
Use this list as a guide to decide "What's next?" as other issues are closed. Issues listed in order of priority - based on a combination of factors - work in progress at the time the list was created, issues ready to be worked on (ie, defined and not waiting for any design), and perceived impact on customers and CE. This is a snapshot; we know we are going to uncover new issues which may be more critical to resolve. Again, use this list as a guide.
| Issue | Top priorities from 2/18 | Top customer-facing issues brainstorm on – 2/18-19 | Associated tickets, status, comments, ETA, etc.
1 | My account preferences - freight etc. | X |  | 4498, 5173, 4989, 5152 IN PROCESS (Janice, Sal, Nihar)
2 | ALSO: "Bundling shouldn't override CPU with user preferences" |  |  | 5455 (new ticket by Judy)
3 | Change “reorder” to “reprice” (order history) |  | X | 5447
4 | CPU as hads come thru as ship to | X | XX | 4951 - Judy needs more info. Still happening?
5 | ALSO: "Staples/Uline CPU issues when re-ordering from order history" |  |  | 5456 - new ticket by Judy, supersedes 4951?
6 | CPU ship to corruption | X | XX | 4955, 4933 IN PROCESS; John, 2/18: "This challenging to fix."
7 | Item descriptions being overwritten |  | XX | 5045 – In process (Ed) - only have custmer reports so far, lacking details to recreate?
8 | Labeling - ability to see labels, part numbers on labels, etc. Get Bartender running again. |  | XX | 5339, 5340 –John, next up?
9 | Friday bundling logic/must ship | X |  | 5187 – hold or just get it over with?
10 | Incorrect marketplace lead times | X |  | 5170 – almost fixed.
11 | Enhance QuickAdd usability: Button |  | XX | 5397
12 | Enhance QuickAdd usability: Focus on input field |  | XX | 5398
13 | Enhance QuickAdd usability: Have Cart tab say “Quick Add” |  | XX | 5400
14 | Sharing over X items, can’t see bottom, can’t scroll, can’t get to send button |  | X | 5471 - opened as priority 2, assigned to self to recreate
15 | Pater /Technisource |  | XX | 4835. ON HOLD for next few days, on track to resolve next Fri, Tina is good with that.
16 | Browser issues – IE 9, 8, etc. |  | XX | 5331, 5239, 5127 - Ongoing; work in parallel w/other issues Enlist Jay Burke to do end to end testing to uncover issues. Code in place to capture some instances of browser-based failures.
17 | Banner search: Opacity msg with certain categories |  | XX | 4592
18 | Banner search: Discontinued items |  | XX | 5242
19 | Banner search: Search on MOD # |  | XX | 5443 (references timeline) This also takes care of the following: POs to CE that reference only MOD #s– customer puts in cart, cart or item deleted – item cannot be found w/out dimensions
20 | Banner search: Search on customer part # |  | XX | 5444 (references timeline)
21 | Fix bugs with filtering in order history. |  | X | 4932, 5090
22 | Part number visibility in general - saved items, carts, checkout, search results, order history, Godzilla etc. |  | XX | 5210 – REQUIRES DESIGN WORK.
23 | Sharing has insufficient detail - zip code, packaging details, etc. |  | XX | 4928 –NEEDS DESIGN WORK this tkt does not really capture all the issues; there may be 1-2 other tickets but I can’t find them. The design group should come up with all the details that are missing and do a mockup with detailed specs. in a consolidated ticket.
24 | Missing case/roll weights on line item basis – various screens |  | XX | 5446. NEEDS DESIGN WORK
25 | Special instructions -tweaks: allow attach docs on sm. Pkg bundles; allow free form comments (for customer -to-customer only - no shipping, CE or workorder instructions) |  | XX | 5000. DESIGN WORK NEEDED. Hopefully these are just tweaks, but it could be complicated due to how we’ve separated logic for small pkg from LTL bundles.
26 | New print plates – need costs in cart and checkout. |  | X | 5204, 4255
27 | Uline 000 comments |  |  | 5474 - priority 2; Tina feels workaround is reasonable.
28 | Apply default zip code from preferences to Active Cart, not just Shop widget |  | X | 5470 - opened as priority 2
29 | Leave me logged in |  | X | 5472 - opened as priority 2
30 | Sharing – not all contacts coming up in predictive search |  | X | 5473 - opened as priority 2, assigned to self to test - need specific examples.