## Sheet1
| Issue | Top priorities from 2/18 | Top customer-facing issues brainstorm on – 2/18-19 | Associated tickets, status, comments, ETA, etc.
1 | My account preferences - freight etc. | X |  | 4498 -90% 5173 - Resolved? (tkt is resolution pending but not assigned) 4989 - 50%? (as of 2/23) 5152 - Resolved
2 | Staples/Uline CPU issues when re-ordering from order history |  |  | 5456 - In process; may be non-issue. Meme researching.
3 | CPU ship to corruption | X | XX | 4955 - Resolved? (tkt is resolution pending but not assigned) 4933 - part of 2/25 roll? (tkt is in process, not assigned).
4 | Item descriptions being overwritten |  | XX | 5045 – In process - did not obtain details to recreate till 2/25.
5 | Labeling - ability to see labels, part numbers on labels, etc. Get Bartender running again. |  | XX | 5339 5340
6 | Friday bundling logic/must ship | X |  | 5187 – hold or just get it over with?
7 | Enhance QuickAdd usability: Button |  | XX | 5397 - 90% (please fix text on error msg - see ticket).
8 | Pater /Technisource |  | XX | 4835. In process.
9 | Browser issues – IE 9, 8, etc. |  | XX | 5331 - on hold. 5239 - resolved? I've asked Will if 2/25 updates alleviated any of these issues. 5127 - resolved? Ongoing; work in parallel w/other issues. Enlist someone to do end to end testing to uncover issues.
10 | Banner search: Opacity msg with certain categories |  | XX | 4592 - In process, status not assigned, but assigned to Sal.
11 | Banner search: Discontinued items |  | XX | 5242 - In process, not assigned.
12 | Banner search: Search on MOD # |  | XX | 5443 (references timeline) This also takes care of the following: POs to CE that reference only MOD #s– customer puts in cart, cart or item deleted – item cannot be found w/out dimensions Link to design spec added to ticket.
13 | Banner search: Search on customer part # |  | XX | 5444 (references timeline) Link to design spec added to ticket.
14 | Part number visibility in general - saved items, carts, checkout, search results, order history, Godzilla etc. |  | XX | 5210 – Link to design spec added to ticket.
15 | Fix bugs with filtering in order history. |  | X | 4932 - not assigned 5090 - in process, assigned to Janice, but status is not assigned.
16 | Missing case/roll weights on line item basis – various screens |  | XX | 5446. Design work in process.
17 | Sharing has insufficient detail - zip code, packaging details, etc. |  | XX | Owen's next design task. 4928 –this tkt does not really capture all the issues; there may be 1-2 other tickets but I can’t find them. The design group should come up with all the details that are missing and do a mockup with detailed specs. in a consolidated ticket.
18 | Special instructions -tweaks: allow attach docs on sm. Pkg bundles; allow free form comments (for customer -to-customer only - no shipping, CE or workorder instructions) |  | XX | 5000. Design work needed. Hopefully these are just tweaks, but it could be complicated due to how we’ve separated logic for small pkg from LTL bundles.
19 | New print plates – need costs in cart and checkout. Need lead time too. |  | X | 5204 - not assigned 5205 - not assigned 4255 - not assigned
20 | Uline 000 comments |  |  | 5474 - priority 2; Tina feels workaround is reasonable.
21 | Apply default zip code from preferences to Active Cart, not just Shop widget |  | X | 5470 - opened as priority 2
22 | Leave me logged in |  | X | 5472 - opened as priority 2
23 | Sharing – not all contacts coming up in predictive search |  | X | 5473 - opened as priority 2, assigned to self to test - need specific examples.
| Bundling shouldn't override CPU with user preferences |  |  | 5455 - Resolved
| Change “reorder” to “reprice” (order history) |  | X | 5447 - Resolved
| Incorrect marketplace lead times | X |  | 5170 – resolved
| Enhance QuickAdd usability: Focus on input field |  | XX | 5398 - resolved
| Enhance QuickAdd usability: Have Cart tab say “Quick Add” |  | XX | 5400 - resolved
| Sharing over X items, can’t see bottom, can’t scroll, can’t get to send button |  | X | 5471 - resolved