## Sheet1
| Issue | Associated tickets, status, comments, ETA, etc.
* | Labeling - ability to see labels, part numbers on labels, etc. Get Bartender running again. | 5339 - in process (Cathy) 5340 - in process (John)
* | Friday bundling logic/must ship | 5187 - in process (Judy) 5880 - in process (Wayne)
* | Tues/Weds 'ship to arrive on' | 5966 - In process (Judy)
* | Banner search: Search on customer part # | 5444 - In process (Janice)
* | The Business/Residential/Limited flag is not getting saved. | 4989 - in process (Janice)
* | Need to disable opaque opacity for mil below 2.5 | 4563 - In process 6128 - In process
* | Remove price breaks when price overriden | 4744 - remove from cart (done) 6123 - In process
* | Owen/Susan get red toaster messages intermittently (adding to cart/saving cart etc.) | 5331 - in process (John); hard to recreate.
WHAT'S NEXT
1 | Missing case/roll weights on line item basis – various screens | 5446. Design completed, ready to be assigned.
2 | Improve verbiage on checkout locking message | 5590 - Design complete, ready to be assigned. QUICK WIN?
3 | Need to remove gauge from configuration "script" on packslips | 5709 - Ready to be assigned.
4 | Uline 000 comments | 5474 - Judy and Cathy want to make this a P1?
5 | CPU - remove carrier drop down; non CPU, replace "My Trucker" with "Trucker" | 5676 - Ready to be assigned
6 | New print plates – need costs in cart and checkout. Need lead time too. | 5205 - In process 4255 - Design completed, ready to be assigned.
7 | Sharing, especially the cart, has insufficient detail - zip code, packaging details, etc. | 4928 - full gauge not showing in Share Item, ready to be assigned 5869 - Design in process, expected this week 5870 - Design in process, expected this week
8 | Special instructions -tweaks: allow attach docs on sm. Pkg bundles; allow free form comments (for customer -to-customer only - no shipping, CE or workorder instructions) | 5000 - Design expected week of 3/23
9 | Sharing – not all contacts coming up in predictive search | 5473 - updated w/specific examples. Has to do with contact not affiliated w/bill to
10 | Allow CE to switch between bill to's w/in web session | 5974 - requires discussion, design and assessment of level of effort.
11 | Apply default zip code from preferences to Active Cart, not just Shop widget | 5470 - ready to be assigned if items 5-7 not ready in time for next free'd up developer
12 | Leave me logged in | 5472 - opened as priority 2. May require discussion?
N/A | Browser issues – IE 9, 8, etc. | Ongoing; work in parallel w/other issues. Enlist someone to do end to end testing to uncover issues.
Recently resolved
| Give CE checkbox to suppress sales order acknowledgment | 5588
| Banner search: Search on MOD # | 5443
| Part number visibility in general - saved items, carts, checkout, search results, order history, Godzilla etc. | 5609 - 6050 -
| Customer address issues | 5606
| Item descriptions being overwritten | 5045
| Fix bugs with filtering in order history. | 4932 - 5090 -
| Banner search: Discontinued items | 5242
| Banner search: Opacity msg with certain categories | 4592 -
| Pater /Technisource | 4835
| Enhance QuickAdd usability: Button | 5397 -
| CPU ship to corruption | 4955 4933
| Staples/Uline CPU issues when re-ordering from order history | 5456 -
| Sharing over X items, can’t see bottom, can’t scroll, can’t get to send button | 5471
| Enhance QuickAdd usability: Have Cart tab say “Quick Add” | 5400
| Enhance QuickAdd usability: Focus on input field | 5398
| Incorrect marketplace lead times | 5170
| Change “reorder” to “reprice” (order history) | 5447
| Bundling shouldn't override CPU with user preferences | 5455