## Hot List
| Issue | Associated tickets, status, comments, ETA, etc.
* | Labeling - ability to see labels, part numbers on labels, etc. Get Bartender running again. | 5339 - in process (Cathy) 5340 - in process (John) 5601 - In process (John) 6163 (John)
* | Remove price breaks when price overriden | 4744 - remove from cart (done) 6123 - remove from sharing - in process (Wayne)
* | New print plates: Need plate cost in Checkout. | 5205 - (Checkout) In process (Janice)
* | Add new generic request type to enable CE to put certain orders on hold | 6371- In process (Judy)
* | Special instructions -tweaks: allow attach docs on sm. Pkg bundles; allow free form comments (for customer -to-customer only - no shipping, CE or workorder instructions) | 5000 - In process (Ed)
* | Improve verbiage on checkout locking message | 5590 - In process (Ed)
WHAT'S NEXT
1 | Get Videos to be fully functional | 6454 - Owen to seek outside help. Do not assign.
2 | Sharing, especially the cart, has insufficient detail - zip code, packaging details, etc. | 4928 - full gauge not showing in Share Item, ready to be assigned 5869 - Design in process, expected week of 4/7 5870 - Design in process, expected week of 4/7
3 | Continuation of tkt 5000; formatting of customer-to-customer comments on Packslip | 6542 - Design needs to be posted to wiki.
4 | Product-specific work order comments carrying over on as hads | 5474
5 | Order history flakey | 6495 -Bugs, ready to be assigned.
6 | Tues/Weds 'ship to arrive on' | 5966 - In process (Judy)
7 | Sharing – not all contacts coming up in predictive search | 5473 - Ready to be assigned.
8 | CPU - remove carrier drop down; non CPU, replace "My Trucker" with "Trucker" | 5676 - Ready to be assigned.
9 | Allow user to filter on Customer Part or their customers part number | Needs ticket? This was missed on tickets 6101/6098 (search on customer part number).
10 | Program widget to accept new printing capabilities | 1942 - Ready to be assigned. 6276 - Production needs print jobs to be flagged on schedule.
From Phase II list
10 | Category dropdown redesign - enable Bags category to scale better to more choices. Probably applies to other menus (eg carrier list) | 6547 - Analysis and design needed.
11 | Online print plate upload and image manipulation; real-time approval | 6551 - Awaiting deliverables from Amazing Print
12 | Pricing and other discrepancies: Automated hold/release logic | 6544 - Specs on wiki. Should be reviewed jointly to determine if there are open design questions.
13 | Form for requesting RMAs | 6545 - Design needed.
14 | Contract pricing for Staples and ULine | 6546 - Design or specifications needed.
15 | Predictive ordering | 6549 - Analysis and design needed.
16 | Google Analytics - go beyond page load-based tracking -Event tracking -E-commerce tracking -Logged-in user tracking | 6550 - Needs to be a joint IT-Marketing effort. Will be iterative; difficult to spec out precisely.
17 | Freight estimator | 6548 - Analysis and design needed.
Work that is ongoing
! | Expand widget's Marketplace capabilities | No ticket. Ongoing - needs dedicated resource?
! | Browser issues – IE 9, 8, etc. | Ongoing; work in parallel w/other issues. Enlist someone to do end to end testing to uncover issues.
Recently resolved
| Preserve backlog days discount when revising an existing quote | 6299; 4/2
| New print plates: need costs and lead time in Cart. | 4255; 4/1
| Missing case/roll weights on line item basis – various screens | 5446; 4/1
| Banner search: Search on customer part # | 5444; 3/30
| Need to disable opaque opacity for mil below 2.5 | 4563; 3/30 6128; 3/30

## Feeder List
Row # | Priority | Issue | Notes
1 | 2 | More control to override the bundling defaults. Full view of inventory during the bundling process We often have to put the order on hold to make adjustments in Avante | From Tina's "wish list." Push back?
2 | 2 | The ability to know if an order goes on “credit hold”- helpful for “must ships” | From Tina's "wish list." Push back? Notes on Wiki indicate we do not want CE to need to know or feel they have to act on this info.
3 | 2 | Be able to type in description/dimensions in the “quick add part number” box in the cart…similar to the ability in that we have on the lines in Avante and hit F3.... (this is a longshot I think) but thought we’d throw it out there anyway. | From Tina's "wish list." Push back?
4 | 2 | Allow CE to switch between bill to's w/in web session | 5974 - requires discussion, design and assessment of level of effort.
5 | 2 | Leave me logged in | 5472 - May require discussion? Less of an issue now that locking is not as frequent.
6 | 2 | Simplification of Sheeting and Film Widget Selections | 2
7 | 2 | Allow View of NS and Sample Orders
8 | 2 | Add new timestamp of Checkout by customer | Talk to CE. Another idea was to BCC order confirmations to a mailbox monitored by CE (separate from the queue)
9 | 2 | Add remaining transactions and streamline the "onramp" by making it contact-based v. bill to based. | This needs to be broken up into distinct phases or components.
10 | 2 | Create an email-viewable version of the order summary (also printable) -Link order history to the above email -Send above email from create order | Some of this came up right after launching. Needs design.
11 | 2 | Redirect customers back to the web based on link in email | Not sure what this was - shared carts and items? (Order acknowledgment is mentioned on another line.)
12 | 2 | Ability for managers to view our costs for price overrides
13 | 3 | Sample orders
14 | 3 | Allow user to delete product use, location and customer item numbers | Wait and see; possible not enough time has elapsed for this to be noticed. Keep as 3 for now.
15 | 3 | Show Open/Changeable vs. Processed Orders
16 | 3 | Advertise Brandit to non-Brandit customers where logo would otherwise appear when sharing carts/items
17 | 3 | Add Medical Grade Pallets | Reassess need. Talk to Sales, CE & purchasing.
18 | 3 | Sharing stock only cart should create a price inquiry ce request | Talk to Tina and Meme.
19 | 3 | Connecting specific “Certs Requests” after the fact to Specific Orders
20 | 3 | Narrative thread | Needs major group design effort to resume?
21 | 4 | Allow color Brandit logos
22 | 4 | Gray out non-shipping days on calendar | Probably could stand to be tweaked, but the way this is working seems adequate for now.
23 | 2-3 | Customer selection of export pallet on order will trigger email to purchasing
24 | 2-3 | Notifications to customer that order/item(s) have shipped – or cancellation
1900-01-24 | 3-4 | Display red marker flags by missing data
1900-01-25 | 3-4 | Ability to toggle UOM
27 | 3-4 | Social media integration | Requires discussion - what's the strategy overall?
28 | 3-4 | Create preference for disallowing verbal Pos | Talk to Sales, CE
29 | ? | NS item ordering | Not sure what this is
30 | ? | Various YMAC changes | Not sure what this is
31 | ? | Modify substitute logic to draw on specialized YMAC rules | Not sure what this is
32 | ? | Change prompting, defaults and validations for pink amine free | Still needed or done?
33 | ? | Add double wound sheeting
34 | ? | Zip code intelligence for anonymous user | Still desired?
35 | ? | Redesign Sharing of Unsaved item | Revisit; either a 3 or 4 or eliminate.
36 | ? | Enhance Share/Fax functionality for “no email” contacts | Not sure what this is or how desirable it still is
37 | ? | Allow CE to change date to expedite order to production | Needs discussion w/CE. Dawn has concerns about CE over-expediting.
38 | ? | Secure ability to change Bill-to information | What is this?
39 | ? | Keyboard interaction | Tickets have been entered, maybe some even closed – need to research.
40 | ? | Carts with plates must be in their own cart