## Hot List
| Issue | Associated tickets, status, comments, ETA, etc.
Work in process
* | Labeling - ability to see labels, part numbers on labels, etc. Get Bartender running again. | 5339 - in process (Cathy) 5340 - in process (John) 6163 - in process (John) 5635 - in process (John) 5924 - in process (John)
* | Remove price breaks when price overriden | 4744 - remove from cart (done) 6123 - remove from sharing - in process (Wayne)
* | Add new generic request type to enable CE to put certain orders on hold | 6371- In process (Judy)
* | Special instructions -tweaks: allow attach docs on sm. Pkg bundles; allow free form comments (for customer -to-customer only - no shipping, CE or workorder instructions) Formatting of customer-to-customer comments on packslip | 5000 - In process (Ed) 6618 - In process (Janice) 6542 - Ready to be assigned | decouple
* | Improve verbiage on checkout locking message | 5590 - In process (Sal)
Work that is ongoing
! | Expand widget's Marketplace capabilities | No ticket. Ongoing - needs dedicated resource? Should there be individual tickets for batches of work?
! | Browser issues – IE 9, 8, etc. | Ongoing; work in parallel w/other issues. Enlist someone to do end to end testing to uncover issues.
WHAT'S NEXT
1 | Spacing issues in cart + case/roll weights disappear in Checkout if you change bundling | 6518 (UI) Ready to be assigned.
2 | We allow spaces and dashes in customer part numbers at the time of saving, but search using these characters gives error. Approx. 50% of customer part numbers have dashes. | 6459 (UI/DB) - Ready to be assigned.
3 | Get Videos to be fully functional | 6454 - Owen to seek outside help. Do not assign.
4 | Sharing, especially the cart, has insufficient detail - zip code, packaging details, etc. | 5869 - Design in process, expected week of 4/6 5870 - Design in process, expected week of 4/6
5 | Product-specific work order comments carrying over on as hads | 5474 - Confirmed this is still important to fix. Ready to be assigned.
6 | Order history flakey | 6495 - Bugs, ready to be assigned.
7 | Tues/Weds 'ship to arrive on' | 5966 - Assigned but not in process.
8 | Zip code change in cart containing MOD causes all stock/MOD items to display as same MOD | 6607 - Ready to be assigned.
9 | CPU - remove carrier drop down; non CPU, replace "My Trucker" with "Trucker" | 5676 - Ready to be assigned.
10 | Program widget to accept new printing capabilities | 1942 - Ready to be assigned. 6276 - Production needs print jobs to be flagged on schedule. | verify workaround
11 | Category dropdown redesign - enable Bags category to scale better to more choices. Probably applies to other menus (eg carrier list) | 6547 - Analysis and design needed.
12 | Adding Billing Zip Code to credit card transactions | 6320
13 | Online print plate upload and image manipulation | 6551 - Awaiting deliverables from Amazing Print
14 | Pricing and other discrepancies: Automated hold/release logic | 6544 - Specs on wiki. Should be reviewed jointly to determine if there are open design questions.
15 | Form for requesting RMAs | 6545 - Design needed.
16 | Contract pricing for Staples and ULine | 6546 - Design or specifications needed.
17 | Predictive ordering | 6549 - Analysis and design needed.
18 | Google Analytics - go beyond page load-based tracking -Event tracking -E-commerce tracking -Logged-in user tracking | 6550 - Needs to be a joint IT-Marketing effort. Will be iterative; difficult to spec out precisely in one go.
Recently resolved
| New print plates: Need plate cost in Checkout (and Order History/Summary) | 5205; 4/7 6483; 4/7
| Full gauge missing from Share Item. | 4928; 4/7
| Preserve backlog days discount when revising an existing quote | 6299; 4/2
| Missing case/roll weights on line item basis – various screens | 5446; 4/1
| Banner search: Search on customer part # | 5444; 3/30
| Need to disable opaque opacity for mil below 2.5 | 4563; 3/30 6128; 3/30

## Feeder List
Row # | Priority | Issue | Notes
1 | 2 | Search by customer part number, reopened due to filtering functionality being missed (ability to filter on customer part number in saved items and order history) | 6101/6098 - Reopened
2 | 2 | Assign different MOD numbers to domestic and imported results. | 5145
3 | 2 | Place customer part number hover back in Checkout bundling | 6626 - Ready to be assigned
4 | 2 | Enable predictive searches for contact email addresses to go up against full sales org | 5473 - Ready to be assigned
5 | 2 | More control to override the bundling defaults. Full view of inventory during the bundling process We often have to put the order on hold to make adjustments in Avante | From Tina's wish list. Need to gather data on why this is necessary, and if there is a better programmatic solution then giving CE ability to do more varied overrides than currently allowed. Let Tina know about this, but have not been able to get together w/her this past week.
6 | 2 | The ability to know if an order goes on “credit hold”- helpful for “must ships” | From Tina's wish list. Notes on Wiki indicate we do not want CE to need to know or feel they have to act on this info. Spoke to Scott; discovered some improvements that can be made (need IT to weigh in on level of effort), but based on some things Scott said, really haven't eliminated the issue of needing coverage for releasing orders from certain warehouses at certain times of day. Plan to schedule meeting w/Scott, Meme and Owen.
7 | 2 | Allow CE to switch between bill to's w/in web session | 5974 - requires discussion, design and assessment of level of effort.
8 | 2 | Leave me logged in | 5472 - May require discussion? Less of an issue now that locking is not as frequent.
9 | 2 | Simplification of Sheeting and Film Widget Selections
10 | 2 | Allow View of NS and Sample Orders
11 | 2 | Add new timestamp of Checkout by customer | Talk to CE. Another idea was to BCC order confirmations to a mailbox monitored by CE (separate from the queue)
12 | 2 | Add remaining transactions and streamline the "onramp" by making it contact-based v. bill to based. | This needs to be broken up into distinct phases or components.
13 | 2 | Create an email-viewable version of the order summary (also printable) -Link order history to the above email -Send above email from create order | Some of this came up right after launching. Needs design.
14 | 2 | Redirect customers back to the web based on link in email | Not sure what this was - shared carts and items? (Order acknowledgment is mentioned on another line.)
15 | 2 | Ability for managers to view our costs for price overrides
16 | 2 | Reduce some of the obscure CE choices in special instructions - for example "bring to Jim D when ready"
17 | 2-3 | Customer selection of export pallet on order will trigger email to purchasing
18 | 2-3 | Notifications to customer that order/item(s) have shipped – or cancellation
19 | 3 | Freight estimator | 6548 - Analysis and design needed.
20 | 3 | Sample orders
21 | 3 | Allow user to delete product use, location and customer item numbers | Wait and see; possible not enough time has elapsed for this to be noticed. Keep as 3 for now.
22 | 3 | Show Open/Changeable vs. Processed Orders
23 | 3 | Advertise Brandit to non-Brandit customers where logo would otherwise appear when sharing carts/items
24 | 3 | Add Medical Grade Pallets | Reassess need. Talk to Sales, CE & purchasing.
25 | 3 | Sharing stock only cart should create a price inquiry ce request | Talk to Tina and Meme.
26 | 3 | Connecting specific “Certs Requests” after the fact to Specific Orders
27 | 3 | Narrative thread | Needs major group design effort to resume?
28 | 4 | Allow color Brandit logos
29 | 4 | Gray out non-shipping days on calendar | Probably could stand to be tweaked, but the way this is working seems adequate for now.
30 | 3-4 | Be able to type in description/dimensions in the “quick add part number” box in the cart…similar to the ability in that we have on the lines in Avante and hit F3.... (this is a longshot I think) but thought we’d throw it out there anyway. | From Tina's "wish list." Push back?
31 | 3-4 | Display red marker flags by missing data
32 | 3-4 | Ability to toggle UOM
33 | 3-4 | Social media integration | Requires discussion - what's the strategy overall?
34 | 3-4 | Create preference for disallowing verbal Pos | Talk to Sales, CE
35 | ? | NS item ordering | Not sure what this is
36 | ? | Various YMAC changes | Not sure what this is
37 | ? | Modify substitute logic to draw on specialized YMAC rules | Not sure what this is
38 | ? | Change prompting, defaults and validations for pink amine free | Still needed or done?
39 | ? | Add double wound sheeting
40 | ? | Zip code intelligence for anonymous user | Still desired?
41 | ? | Redesign Sharing of Unsaved item | Revisit; either a 3 or 4 or eliminate.
42 | ? | Enhance Share/Fax functionality for “no email” contacts | Not sure what this is or how desirable it still is
43 | ? | Allow CE to change date to expedite order to production | Needs discussion w/CE. Dawn has concerns about CE over-expediting.
44 | ? | Secure ability to change Bill-to information | What is this?
45 | ? | Keyboard interaction | Tickets have been entered, maybe some even closed – need to research.
46 | ? | Carts with plates must be in their own cart