## Hot List
Work in process
* | Bartender automatically shutting down | 7119 - Sal & John
* | Marketplace Tamper Evident Zip Tops | 6949 (DB) - Wayne
* | Program widget to accept new printing capabilities | 1942 (David, then DB programmer). Hand off from David anticipated around 5/4. 6276 - Production needs print jobs to be flagged on schedule.
* | Remove price breaks from shares when price overridden. Déjà vu all over again - when we fixed that before we broke requoting of items converted items w/deviated prices. We needed to undo the price breaks work to fix that. Now we are working to restore the price breaks removal. | Ticketed, in process - DB/UI, Sal, Wayne
* | Not all contacts coming up in predictive search | 6689 (UI) Ed - ready to test, but has to be tested on live.
* | Adding Billing Zip Code to credit card transactions | 6320 (DB) - Judy - We may already be doing this
Work that is ongoing (dedicated resource)
! | Expand widget's Marketplace capabilities
| Marketplace Zip Tops with Vent Hole | 6952
| Marketplace Zip Tops w/Hang Hole and Vent Hole | 6953
| Marketplace Pre-Opened Bags on a Roll | 6954
| Marketplace Registered Printed Zip Tops | 6955
| Marketplace Registered Printed Layflats | 6956
WHAT'S NEXT
1 | Change default for sharing to "sharing w/customer?; Yes" & add some hand-holding verbiage | 7415 - Ready to assign
2 | Product-specific work order comments carrying over on as hads | 5474 - Confirmed this is still important to fix. Ready to be assigned. Talk in person.
3 | Add 'attach docs' free form field back in for CE | 7462 - Ready to be assigned
4 | Google Analytics - go beyond page load-based tracking -Event tracking -E-commerce tracking -Logged-in user tracking | 6550 - Ready to be assigned, but requires coordination with Marketing.
5 | Assign different MOD numbers to domestic and imported results. | 5145 - Cathy says this is not trivial; requires discussion.
6 | Category dropdown redesign - enable Bags category to scale better to more choices. Probably applies to other menus (eg carrier list) | 6547 - Steve & Haley to do some design work
7 | Online print plate upload and image manipulation | 6551 - Awaiting deliverables from Amazing Print
8 | Pricing and other discrepancies: Automated hold/release logic | 6544 - Specs on wiki. Should be reviewed jointly to determine if there are open design questions.
9 | Form for requesting RMAs | 6545 - Design needed. I want to sit w/CE person to show me process.
10 | Contract pricing for Staples and ULine | 6546 - Design or specifications needed.
11 | Predictive ordering | 6549 - Analysis and design needed.
12 | Messaging | Analysis and design needed.
Recently resolved
| Order history flakey | 6495; 4/30
| CPU - remove carrier drop down; non CPU, replace "My Trucker" with "Trucker" | 5676; 4/30
| Sharing, especially the cart, has insufficient detail - zip code, packaging details, etc. | 5869; 4/30 5870; 4/30
| Place customer part number hover back in Checkout bundling | 6626; 4/30

## Feeder List
Row # | Priority | Issue | Notes
| 2 | Better language around backlog discount/upcharge | Owen working on mockups w/Haley.
2 | 2 | Source Reference on Laddawn and Brandit Lables | 7154
3 | 2 | Enable predictive searches of contacts to go against sales org | 5473 DB/UI
4 | 2 | Display customer PSP (pricing level); enable more efficient response to price deviation requests. (Came from Tina's wish list). | 7004 - Design needed.
5 | 2 | More control to override the bundling defaults. Full view of inventory during the bundling process We often have to put the order on hold to make adjustments in Avante | From Tina's wish list. Need to gather data on why this is necessary, and if there is a better programmatic solution then giving CE ability to do more varied overrides than currently allowed. Let Tina know about this, but have not been able to get together w/her this past week.
6 | 2 | The ability to know if an order goes on “credit hold”- helpful for “must ships” | From Tina's wish list. Notes on Wiki indicate we do not want CE to need to know or feel they have to act on this info. Spoke to Scott; discovered some improvements that can be made (need IT to weigh in on level of effort), but based on some things Scott said, really haven't eliminated the issue of needing coverage for releasing orders from certain warehouses at certain times of day. Plan to schedule meeting w/Scott, Meme and Owen.
7 | 2 | Leave me logged in | 5472 - May require discussion? Less of an issue now that locking is not as frequent.
8 | 2 | Simplification of Sheeting and Film Widget Selections
9 | 2 | Allow View of NS and Sample Orders
10 | 2 | Add new timestamp of Checkout by customer | Talk to CE. Another idea was to BCC order confirmations to a mailbox monitored by CE (separate from the queue)
11 | 2 | Add remaining transactions and streamline the "onramp" by making it contact-based v. bill to based. | This needs to be broken up into distinct phases or components.
12 | 2 | Allow CE to switch between bill to's w/in web session | 5974 - requires discussion, design and assessment of level of effort.
13 | 2 | Create an email-viewable version of the order summary (also printable) -Link order history to the above email -Send above email from create order | Some of this came up right after launching. Needs design. Build off of ticket 3708.
14 | 2 | Redirect customers back to the web based on link in email | Not sure what this was - shared carts and items? (Order acknowledgment is mentioned on another line.)
15 | 2 | Ability for managers to view our costs for price overrides
16 | 2 | CPU zip code indicator. In various places we show zip codes - eg pricing history, tooltips, etc. But we don't differentiate between CPU and ship to. | May need design.
17 | 2 | Tool for finding the right sized bag. | 7250. Requires design. Will Moore has created a spreadsheet. See also catalog.
18 | 2 | Reduce some of the obscure CE choices in special instructions - for example "bring to Jim D when ready"
19 | 2-3 | Customer selection of export pallet on order will trigger email to purchasing
20 | 2-3 | Notifications to customer that order/item(s) have shipped – or cancellation
21 | 2-3 | Add invoices to order history | Design needed for online version of invoice?
22 | 3 | Freight estimator | 6548 - Analysis and design needed.
23 | 3 | Sample orders
24 | 3 | Allow user to delete product use, location and customer item numbers | Wait and see; possible not enough time has elapsed for this to be noticed. Keep as 3 for now.
25 | 3 | Show Open/Changeable vs. Processed Orders
26 | 3 | Advertise Brandit to non-Brandit customers where logo would otherwise appear when sharing carts/items
27 | 3 | Add Medical Grade Pallets | Reassess need. Talk to Sales, CE & purchasing.
28 | 3 | Sharing stock only cart should create a price inquiry ce request | Talk to Tina and Meme.
29 | 3 | Connecting specific “Certs Requests” after the fact to Specific Orders
30 | 3 | Narrative thread | Needs major group design effort to resume?
31 | 4 | Allow color Brandit logos
32 | 4 | Gray out non-shipping days on calendar | Probably could stand to be tweaked, but the way this is working seems adequate for now.
33 | 3-4 | Be able to type in description/dimensions in the “quick add part number” box in the cart…similar to the ability in that we have on the lines in Avante and hit F3.... (this is a longshot I think) but thought we’d throw it out there anyway. | From Tina's "wish list." Push back?
34 | 3-4 | Display red marker flags by missing data
35 | 3-4 | Ability to toggle UOM
36 | 3-4 | Social media integration | Requires discussion - what's the strategy overall?
37 | 3-4 | Create preference for disallowing verbal Pos | Talk to Sales, CE
38 | ? | NS item ordering | Not sure what this is
39 | ? | Various YMAC changes | Not sure what this is
40 | ? | Modify substitute logic to draw on specialized YMAC rules | Not sure what this is
41 | ? | Change prompting, defaults and validations for pink amine free | Still needed or done?
42 | ? | Add double wound sheeting
43 | ? | Zip code intelligence for anonymous user | Still desired?
44 | ? | Redesign Sharing of Unsaved item | Revisit; either a 3 or 4 or eliminate.
45 | ? | Enhance Share/Fax functionality for “no email” contacts | Not sure what this is or how desirable it still is
46 | ? | Allow CE to change date to expedite order to production | Needs discussion w/CE. Dawn has concerns about CE over-expediting.
47 | ? | Secure ability to change Bill-to information | What is this?
48 | ? | Keyboard interaction | Tickets have been entered, maybe some even closed – need to research.
49 | ? | Carts with plates must be in their own cart