## Hot List
Work in process
* | Bartender automatically shutting down | 7119 - John & Sal (John off M/T/W)
* | Marketplace Tamper Evident Zip Tops | 6949 (DB) - DB work complete. Waiting on a small UI change. Judy: As this was the first ‘stock only’ category that has been changed into a Marketplace category, there was a learning curve on this one. The next ones should go much smoother.
* | Program widget to accept new printing capabilities | 1942 (DB) - Janice (David's work completed 5/11). 6276 - Production needs print jobs to be flagged on schedule.
* | Adding Billing Zip Code to credit card transactions | 6320 (DB) - Joe, resolution pending (awaiting testing before it can be deployed to live)
* | Google Analytics - go beyond page load-based tracking -Event tracking -E-commerce tracking -Logged-in user tracking | 6550 - Ed & Cliff - Awaiting deployment. Once deployed, we can consider the initial work done. We'll continue to open tickets for chunks of work.
* | Quick fix needed to address issue from 7415 (shares not defaulting to "no" for Sales/CR). | 7722 - Ed, awaiting deployment so it can be tested.
* | Please change default subject line for order confirmations to include PO# | 7729 - Ed, awaiting deployment so it can be tested.
* | Change to label description functionality (automatically deleting 2d line) | 6795 - Sal
* | Additional Share item/Share cart enhancements | 7726 - Ed
Work that is ongoing (dedicated resource)
! | Expand widget's Marketplace capabilities
| Marketplace Zip Tops with Vent Hole | 6952
| Marketplace Zip Tops w/Hang Hole and Vent Hole | 6953
| Marketplace Pre-Opened Bags on a Roll | 6954
| Marketplace Registered Printed Zip Tops | 6955
| Marketplace Registered Printed Layflats | 6956
WHAT'S NEXT
1 | Online print plate upload and image manipulation | 6551 -Ready to be assigned. Meeting to be held Thurs afternoon w/IT, Marketing, Amazing Print (5/14).
2 | Fix bug that allows you to add both a domestic and an import w/same MOD# to cart and create a pricing/availability mashup. | 7648 - Sal
3 | Provide images for MODs, expanded item descriptions | 7731 - Ready to be assigned.
4 | Display a Laddawn stock zip top if a Minigrip SKU is directly entered. | 7033 - DB –Ready to be assigned.
5 | Product-specific work order comments carrying over on as hads | 5474 - Judy, John, Tina - design expected 5/19
6 | Contract pricing for Staples and ULine | 6546 - Judy, John - design expected 5/19
7 | Category dropdown redesign - enable Bags category to scale better to more choices. Probably applies to other menus (eg carrier list) | 6547 - Design process getting underway w/Steve B.
8 | Pricing and other discrepancies: Automated hold/release logic | 6544 - Reviewed specs on 5/5; ID'd areas that need to be fleshed out and mocked up further. Hope to complete by 5/14???
9 | Form for requesting RMAs | 6545 - Sat w/Lee Carter to go through the process. Hope to have some draft specs by 5/21?
10 | Predictive ordering | 6549 - Analysis and design in process
11 | Messaging | Analysis and design in process; UI may go hand in hand w/predictive ordering above.
12 | Sample orders - from feeder list (part of line 10); determined this was one of Tina's next big efficiency improvements. | Not ticketed yet; sat w/Lee Carter 5/6 to go through the process.Hope to have some draft specs by 5/21?
Recently resolved
| Remove price breaks from shares when price overridden. Déjà vu all over again - when we fixed that before we broke requoting of items converted items w/deviated prices. We needed to undo the price breaks work to fix that. Now we are working to restore the price breaks removal. | 7319, Sal - 5/6
| Add 'attach docs' free form field back in for CE | 7462, Janice - 5/6
| Not all contacts coming up in predictive search | 6689, Ed -5/6
| Change default for sharing to "sharing w/customer?; Yes" & add some hand-holding verbiage | 7415, Ed - 5/6
See help desk report for complete list of updates to live.

## Feeder List
Row # | Priority | Issue | Notes
1 | 2 | Display a Laddawn stock zip top if a Minigrip SKU is directly entered. | 7033 - DB – YMACs when a Minigrip zip top is searched for by item number” Ready to be assigned.
2 | 2 | Provide images for MODs, expanded item descriptions | 7731 - Ready to be assigned
3 | 2 | Better language around backlog discount/upcharge | Owen working on mockups w/Haley.
4 | 2 | Incorporate bill to, ship toand contact numbers into UI as unobtrusively as possible. | Various screens TBD. Design needed.
5 | 2 | Enable predictive searches of contacts to go against sales org | 5473 DB/UI
6 | 2 | Display customer PSP (pricing level); enable more efficient response to price deviation requests. (Came from Tina's wish list). | 7004 - Design needed.
7 | 2 | More control to override the bundling defaults. Full view of inventory during the bundling process We often have to put the order on hold to make adjustments in Avante | From Tina's wish list. Need to gather data on why this is necessary, and if there is a better programmatic solution then giving CE ability to do more varied overrides than currently allowed. Let Tina know about this, but have not been able to get together w/her this past week.
8 | 2 | The ability to know if an order goes on “credit hold”- helpful for “must ships” | From Tina's wish list. Notes on Wiki indicate we do not want CE to need to know or feel they have to act on this info. Spoke to Scott; discovered some improvements that can be made (need IT to weigh in on level of effort), but based on some things Scott said, really haven't eliminated the issue of needing coverage for releasing orders from certain warehouses at certain times of day. Plan to schedule meeting w/Scott, Meme and Owen.
9 | 2 | Leave me logged in | 5472 - May require discussion? Less of an issue now that locking is not as frequent.
10 | 2 | Simplification of Sheeting and Film Widget Selections
11 | 2 | Allow View of NS and Sample Orders
12 | 2 | Add new timestamp of Checkout by customer | Talk to CE. Another idea was to BCC order confirmations to a mailbox monitored by CE (separate from the queue)
13 | 2 | Add remaining transactions and streamline the "onramp" by making it contact-based v. bill to based. | This needs to be broken up into distinct phases or components.
14 | 2 | Allow CE to switch between bill to's w/in web session | 5974 - requires discussion, design and assessment of level of effort.
15 | 2 | Create an email-viewable version of the order summary (also printable) -Link order history to the above email -Send above email from create order | Some of this came up right after launching. Needs design. Build off of ticket 3708.
16 | 2 | Redirect customers back to the web based on link in email | Not sure what this was - shared carts and items? (Order acknowledgment is mentioned on another line.)
17 | 2 | Ability for managers to view our costs for price overrides
18 | 2 | CPU zip code indicator. In various places we show zip codes - eg pricing history, tooltips, etc. But we don't differentiate between CPU and ship to. | May need design.
19 | 2 | Tool for finding the right sized bag. | 7250. Requires design. Will Moore has created a spreadsheet. See also catalog.
20 | 2 | Reduce some of the obscure CE choices in special instructions - for example "bring to Jim D when ready"
21 | 2-3 | Customer selection of export pallet on order will trigger email to purchasing
22 | 2-3 | Notifications to customer that order/item(s) have shipped – or cancellation
23 | 2-3 | Add invoices to order history | Design needed for online version of invoice?
24 | 3 | Freight estimator | 6548 - Analysis and design needed.
25 | 3 | Sample orders
26 | 3 | Allow user to delete product use, location and customer item numbers | Wait and see; possible not enough time has elapsed for this to be noticed. Keep as 3 for now.
27 | 3 | Show Open/Changeable vs. Processed Orders
28 | 3 | Advertise Brandit to non-Brandit customers where logo would otherwise appear when sharing carts/items
29 | 3 | Add Medical Grade Pallets | Reassess need. Talk to Sales, CE & purchasing.
30 | 3 | Sharing stock only cart should create a price inquiry ce request | Talk to Tina and Meme.
31 | 3 | Connecting specific “Certs Requests” after the fact to Specific Orders
32 | 3 | Narrative thread | Needs major group design effort to resume?
33 | 4 | Allow color Brandit logos
34 | 4 | Gray out non-shipping days on calendar | Probably could stand to be tweaked, but the way this is working seems adequate for now.
35 | 3-4 | Be able to type in description/dimensions in the “quick add part number” box in the cart…similar to the ability in that we have on the lines in Avante and hit F3.... (this is a longshot I think) but thought we’d throw it out there anyway. | From Tina's "wish list." Push back?
36 | 3-4 | Display red marker flags by missing data
37 | 3-4 | Ability to toggle UOM
38 | 3-4 | Social media integration | Requires discussion - what's the strategy overall?
39 | 3-4 | Create preference for disallowing verbal Pos | Talk to Sales, CE
40 | ? | NS item ordering | Not sure what this is
41 | ? | Various YMAC changes | Not sure what this is
42 | ? | Modify substitute logic to draw on specialized YMAC rules | Not sure what this is
43 | ? | Change prompting, defaults and validations for pink amine free | Still needed or done?
44 | ? | Add double wound sheeting
45 | ? | Zip code intelligence for anonymous user | Still desired?
46 | ? | Redesign Sharing of Unsaved item | Revisit; either a 3 or 4 or eliminate.
47 | ? | Enhance Share/Fax functionality for “no email” contacts | Not sure what this is or how desirable it still is
48 | ? | Allow CE to change date to expedite order to production | Needs discussion w/CE. Dawn has concerns about CE over-expediting.
49 | ? | Secure ability to change Bill-to information | What is this?
50 | ? | Keyboard interaction | Tickets have been entered, maybe some even closed – need to research.
51 | ? | Carts with plates must be in their own cart

## ManageEngine Report Framework
Tickets closed between rolls to LIVE
Generated by Susan Parker on : May 7, 2015 09:07 AM
Total records : 20
Ticket ID | Subject | Section | Resolved Time
7215 | DB - PL - CPU - remove carrier drop down; non CPU, replace "My Companys Truck" with "Trucker" | 09 CHECKOUT - SHIPPING | May 6, 2015 02:08 PM
7462 | UI - PL - Please add attach docs back to CE section of special instructions | 09 CHECKOUT - SHIPPING | May 6, 2015 12:23 PM
6618 | DB - PL - Tweaks to special instructions | 09 CHECKOUT - SHIPPING | May 6, 2015 12:08 PM
7449 | UI - Update TILES & FOOTERS Due May 4 | 21 FOOTER/HOMEPAGE CONTENT | May 6, 2015 09:47 AM
7359 | UI - MARKETING UPDATE 5/1/15 | 21 FOOTER/HOMEPAGE CONTENT | May 6, 2015 09:42 AM
6616 | DB - PB - CE NS Remake Order Quote Convert display issue | 22 AVANTE | May 4, 2015 04:54 PM
7388 | DB - ASCII File Showing How Many Quotes About to Expire for a Contact | 22 AVANTE | May 1, 2015 05:09 PM
6573 | DB - PB - EDI/XML order creation process is incorrectly setting the Must Ship Today Flag | 22 AVANTE | May 1, 2015 03:04 PM
7455 | PB - Add last login tracking to Contacts | 14 LOGIN | May 1, 2015 08:11 AM
7387 | DB - ASCII File Showing Which Lines have been Ordered 3 or more times by Same Customer | 22 AVANTE | Apr 30, 2015 12:41 PM
7154 | UI - Source Reference on Laddawn and Brandit Lables | 11 CHECKOUT - LABELING | Apr 30, 2015 09:18 AM
6345 | UI - PB - Text alignment in black opaque opacity message | 01 SHOP | Apr 30, 2015 09:10 AM
5869 | UI - PL - Add ship to zip to shared items and shared carts | 07 SHARE CART | Apr 30, 2015 09:05 AM
5870 | UI - PL - Add customer number (bill to) to lower right corner of share emails | 06 SHARE ITEM | Apr 30, 2015 09:04 AM
6626 | UI - PL - Place Hover back on the Checkout Bundling and Summary Steps | 09 CHECKOUT - SHIPPING | Apr 30, 2015 09:03 AM
6495 | UI - PL - Order history is flakey, to the point of being non-functional | 03 ORDER HISTORY | Apr 30, 2015 09:03 AM
7037 | UI - Unable to add recipient on CPU order, multi-city zip | 08 CHECKOUT - ADDRESSES | Apr 30, 2015 09:03 AM
7080 | Server Error Message in Application | 09 CHECKOUT - SHIPPING | Apr 30, 2015 09:02 AM
7221 | Cannot use 'Attach documents' in Chrome | 09 CHECKOUT - SHIPPING | Apr 30, 2015 09:01 AM
7236 | UI - Price override (unit & total) revert to list price on reorder when 'no overrun' checked | 05 ACTIVE CART | Apr 30, 2015 09:00 AM