## Hot List
Work in process
| Program widget to accept new printing capabilities | 1942, 6276 - Janice, Ready for testing.
| Google Analytics - track video plays | 7856 - Ed
| Please change default subject line for order confirmations to include PO# | 7729 - Ed, on Live (order summary piece) 7857 - Joe, in process (email subject piece)
| Additional Share item/Share cart enhancements | 7726 - Ed
| Provide images for MODs, expanded item descriptions | 7731 - Janice
| Display a Laddawn stock zip top if a Minigrip SKU is directly entered. | 7033 - Janice
| Marketplace Zip Tops with Vent Hole | 6952 - Wayne
| Marketplace Zip Tops w/Hang Hole and Vent Hole | 6953 - Wayne
! | Expand widget's Marketplace capabilities
| Marketplace Pre-Opened Bags on a Roll | 6954
| Marketplace Registered Printed Zip Tops | 6955
| Marketplace Registered Printed Layflats | 6956
WHAT'S NEXT
1 | Fix bug that allows you to add both a domestic and an import w/same MOD# to cart and create a pricing/availability mashup. | 7648 - Sal
2 | Fix bugs with Marketplace items:
a | Correct material & additive choices on marketplace items. | 2953, 4363 - Ready to be assigned.
b | Marketplace Zip Tops showing LIVE CHAT for price on Anti Static Pink/Clear IMPORT result | 7849 - Ready to be assigned
c | Change Text on Venting Nbr of Holes for Marketplace Zip Tops | 7925 - Joe, in process 7817 - Sal
3 | Change the way lists default for Laddawn operators | 7874 - Sal
4 | Dynamic filtering changes Order History | 7807 - Anticipate this being ready to assign by end of 5/19.
5 | Online print plate upload and image manipulation | 6551 -Ready to be assigned. Meeting to be held Thurs afternoon w/IT, Marketing, Amazing Print (5/14).
6 | Product-specific work order comments carrying over on as hads | 5474 - Judy, John, Tina - design expected 5/19
7 | Contract pricing for Staples and ULine | 6546 - Judy, John - design expected 5/19
8 | Changes to improve efficiency of release of credit hold must ship orders | 7954 - Ready to be assigned
9 | Category dropdown redesign - enable Bags category to scale better to more choices. Probably applies to other menus (eg carrier list) | 6547 - Design process getting underway w/Steve B.
10 | Pricing and other discrepancies: Automated hold/release logic | 6544 - Reviewed specs on 5/5; ID'd areas that need to be fleshed out and mocked up further. Hope to complete by 5/14???
11 | Form for requesting RMAs | 6545 - Sat w/Lee Carter to go through the process. Hope to have some draft specs by 5/21?
12 | Predictive ordering | 6549 - Analysis and design in process
13 | Messaging | Analysis and design in process; UI may go hand in hand w/predictive ordering above.
14 | Sample orders - from feeder list (part of line 10); determined this was one of Tina's next big efficiency improvements. | Not ticketed yet; sat w/Lee Carter 5/6 to go through the process.Hope to have some draft specs by 5/21?
Recently resolved
| Change to label description functionality (automatically deleting 2d line) + incorrect packout (/M, not /roll or cs) | 6795 - Sal, 5/18
| Adding Billing Zip Code to credit card transactions | 6320 - Joe, 5/18
| Google Analytics - foundational work | 6550 - Ed, 5/18
| Marketplace Tamper Evident Zip Tops | 6949 - Wayne, 5/18
| Quick fix needed to address issue from 7415 (shares not defaulting to "no" for Sales/CR). | 7722 - Ed, 5/19
| Bartender automatically shutting down | 7119 -Sal, John, 5/13
See help desk report for complete list of updates to live.

## Feeder List
Row # | Priority | Issue | Notes
1 | 2 | Better language around backlog discount/upcharge | Owen working on mockups w/Haley.
2 | 2 | Incorporate bill to, ship to and contact numbers into UI as unobtrusively as possible. | Various screens TBD. Design needed.
3 | 2 | Enable predictive searches of contacts to go against sales org | 5473 DB/UI
4 | 2 | Display customer PSP (pricing level); enable more efficient response to price deviation requests. (Came from Tina's wish list). | 7004 - Design needed.
5 | 2 | Add "Call for Pickup" to Special Instructions | 7887 - ready to be assigned.
6 | 2 | More control to override the bundling defaults. Full view of inventory during the bundling process We often have to put the order on hold to make adjustments in Avante | From Tina's wish list. Need to gather data on why this is necessary, and if there is a better programmatic solution then giving CE ability to do more varied overrides than currently allowed. Let Tina know about this, but have not been able to get together w/her this past week.
7 | 2 | The ability to know if an order goes on “credit hold”- helpful for “must ships” | From Tina's wish list. Notes on Wiki indicate we do not want CE to need to know or feel they have to act on this info. Spoke to Scott; discovered some improvements that can be made (need IT to weigh in on level of effort), but based on some things Scott said, really haven't eliminated the issue of needing coverage for releasing orders from certain warehouses at certain times of day. Plan to schedule meeting w/Scott, Meme and Owen.
8 | 2 | Leave me logged in | 5472 - May require discussion? Less of an issue now that locking is not as frequent.
9 | 2 | Simplification of Sheeting and Film Widget Selections | Is this really part of category menu redesign?
10 | 2 | Allow View of NS and Sample Orders
11 | 2 | Add new timestamp of Checkout by customer | Talk to CE. Another idea was to BCC order confirmations to a mailbox monitored by CE (separate from the queue)
12 | 2 | Add remaining transactions and streamline the "onramp" by making it contact-based v. bill to based. | This needs to be broken up into distinct phases or components.
13 | 2 | Allow CE to switch between bill to's w/in web session | 5974 - requires discussion, design and assessment of level of effort.
14 | 2 | Create an email-viewable version of the order summary (also printable) -Link order history to the above email -Send above email from create order | Some of this came up right after launching. Needs design. Build off of ticket 3708.
15 | 2 | Redirect customers back to the web based on link in email | Not sure what this was - shared carts and items? (Order acknowledgment is mentioned on another line.)
16 | 2 | Ability for managers to view our costs for price overrides
17 | 2 | CPU zip code indicator. In various places we show zip codes - eg pricing history, tooltips, etc. But we don't differentiate between CPU and ship to. | May need design.
18 | 2 | Tool for finding the right sized bag. | 7250. Requires design. Will Moore has created a spreadsheet. See also catalog.
19 | 2 | Reduce some of the obscure CE choices in special instructions - for example "bring to Jim D when ready"
20 | 2-3 | Customer selection of export pallet on order will trigger email to purchasing
21 | 2-3 | Notifications to customer that order/item(s) have shipped – or cancellation
22 | 2-3 | Add invoices to order history | Design needed for online version of invoice?
23 | 3 | Freight estimator | 6548 - Analysis and design needed.
24 | 3 | Sample orders
25 | 3 | Allow user to delete product use, location and customer item numbers | Wait and see; possible not enough time has elapsed for this to be noticed. Keep as 3 for now.
26 | 3 | Show Open/Changeable vs. Processed Orders
27 | 3 | Advertise Brandit to non-Brandit customers where logo would otherwise appear when sharing carts/items
28 | 3 | Add Medical Grade Pallets | Reassess need. Talk to Sales, CE & purchasing.
29 | 3 | Sharing stock only cart should create a price inquiry ce request | Talk to Tina and Meme.
30 | 3 | Connecting specific “Certs Requests” after the fact to Specific Orders
31 | 3 | Narrative thread | Needs major group design effort to resume?
32 | 4 | Allow color Brandit logos
33 | 4 | Gray out non-shipping days on calendar | Probably could stand to be tweaked, but the way this is working seems adequate for now.
34 | 3-4 | Be able to type in description/dimensions in the “quick add part number” box in the cart…similar to the ability in that we have on the lines in Avante and hit F3.... (this is a longshot I think) but thought we’d throw it out there anyway. | From Tina's "wish list." Push back?
35 | 3-4 | Display red marker flags by missing data
36 | 3-4 | Ability to toggle UOM
37 | 3-4 | Social media integration | Requires discussion - what's the strategy overall?
38 | 3-4 | Create preference for disallowing verbal Pos | Talk to Sales, CE
39 | ? | NS item ordering | Not sure what this is
40 | ? | Various YMAC changes | Not sure what this is
41 | ? | Modify substitute logic to draw on specialized YMAC rules | Not sure what this is
42 | ? | Change prompting, defaults and validations for pink amine free | Still needed or done?
43 | ? | Add double wound sheeting
44 | ? | Zip code intelligence for anonymous user | Still desired?
45 | ? | Redesign Sharing of Unsaved item | Revisit; either a 3 or 4 or eliminate.
46 | ? | Enhance Share/Fax functionality for “no email” contacts | Not sure what this is or how desirable it still is
47 | ? | Allow CE to change date to expedite order to production | Needs discussion w/CE. Dawn has concerns about CE over-expediting.
48 | ? | Secure ability to change Bill-to information | What is this?
49 | ? | Keyboard interaction | Tickets have been entered, maybe some even closed – need to research.
50 | ? | Carts with plates must be in their own cart

## ManageEngine Report Framework
Tickets closed between rolls to LIVE
Generated by Susan Parker on : May 14
Total records : 16
Ticket ID | Subject | Section | Resolved Time
7366 | DB - PB - Change Database routines to support new reprice status of 4 - Return Quote Price | 23 GLOBAL / MULTIPLE | May 7, 2015 10:34 AM
6376 | UI - Checkout process needs to be forced to https | 23 GLOBAL / MULTIPLE | May 7, 2015 10:34 AM
7415 | PL - Change default for sharing to "sharing w/customer?; Yes" | 07 SHARE CART | May 7, 2015 10:36 AM
7551 | UI - Typo in phone number on cart/print plate tooltip. | 05 ACTIVE CART | May 7, 2015 10:38 AM
7590 | UI - Changes in My Account Paperwork Preferences for an Individual location are not saving to the DB | 16 MY ACCOUNT - SHIPPING | May 7, 2015 10:39 AM
7466 | DB/UI - Customer 890042 is able to have blank CPU zip code | 01 SHOP | May 7, 2015 11:36 AM
7632 | Email Spam Filter | Not Assigned | May 7, 2015 11:56 AM
6958 | DB - Deletion of a quote in Avante should remove the quote# from web xref files | 22 AVANTE | May 8, 2015 08:18 AM
7623 | VPN Contractor Setup - Steve Borowick | Not Assigned | May 8, 2015 08:24 AM
7368 | UI - MARKETING UPDATE VIDEO 5/5/15 | 21 FOOTER/HOMEPAGE CONTENT | May 8, 2015 11:38 AM
7679 | UI - Congratulations..you've earned free freight......NOT | 07 SHARE CART | May 8, 2015 02:03 PM
7688 | Outlook permissions | Not Assigned | May 8, 2015 02:45 PM
7732 | HD - FW: Website | 07 SHARE CART | May 12, 2015 10:50 AM
7735 | WEDS MAY13 DROP INTRO from Drones | Not Assigned | May 13, 2015 03:41 PM
7799 | UI - PB - New location tags not carrying through to Checkout Addressing screen | 08 CHECKOUT - ADDRESSES | May 13, 2015 05:06 PM
6864 | DB - PB - Change FURN BAGS to FURN in the item description - it's makes the desc too long and truncates the folded option | 22 AVANTE | May 13, 2015 09:38 PM