## Hot List
Work in process |  |  | Drivers | ETA
| Program widget to accept new printing capabilities | 1942, 6276 - Janice.David should finish testing by weeks end – Janice is fixing issues as David finds them – Judy/David will retest – Tom is going to make other departments aware and order plates – we are looking at 2 weeks - **** More programming time added due to conversion program that will be needed. 8147 - Sal, text changes on screen
| Google Analytics - track video plays | 7856 - Ed
| Additional Share item/Share cart enhancements | 7726 - Ed, tested, sent back.
| Fix bug that allows you to add both a domestic and an import w/same MOD# to cart and create a pricing/availability mashup. | 7648 - Sal; done waiting to be tested.
| Changes to improve efficiency of release of credit hold must ship orders | 7954 - Joe (redirected to work on locking issues)
| Change the way lists default for Laddawn operators | 7874 - Sal, done, tested, ready to deploy
| Changes to Order History, dynamic filtering | 7807 - Sal, done, tested, sent back, ready to test again?
b | Correct material & additive choices on marketplace items. | 2953, 4363 - Wayne
! | Expand widget's Marketplace capabilities
| Marketplace Pre-Opened Bags on a Roll | 6954 - Wayne - about to start
| Marketplace Registered Printed Zip Tops | 6955 - If Amazing Print not implemented, requires changes to current print menu - some throwaway, some not.
| Marketplace Registered Printed Layflats | 6956 - Same issue as above.
WHAT'S NEXT
1 | Fix bugs with Marketplace items:
a | Marketplace Zip Tops showing LIVE CHAT for price on Anti Static Pink/Clear IMPORT result | 7849 - Wayne (need info from Tom)
Recently resolved
| Display a Laddawn stock zip top if a Minigrip SKU is directly entered. | 7033 - Joe, 5/26
| Change Text on Venting Nbr of Holes for Marketplace Zip Tops | 7925 - Joe, 5/26 - check dates 7817 - Sal, 5/26
| Marketplace Zip Tops with Vent Hole | 6952 - Wayne, 5/26
| Marketplace Zip Tops w/Hang Hole and Vent Hole | 6953 - Wayne, 5/26
| Provide images for MODs, expanded item descriptions | 7731 - Janice, 5/21
| Please change default subject line for order confirmations to include PO# | 7729 - Ed, done, 5/18 7857 - Joe, 5/22
See help desk report for complete list of updates to live.

## ManageEngine Report Framework
Tickets closed between rolls to LIVE
Generated by Susan Parker on : May 21, 2015 08:00 AM
Total records : 19
Ticket ID | Subject | Section | Resolved Time
7119 | UI - PL - Bartender - Automatically Shutting Down | 11 CHECKOUT - LABELING | May 14, 2015 10:52 AM
6807 | DB - Overrun flag not updating correctly | 22 AVANTE | May 15, 2015 03:41 PM
6803 | UI - PB - Third party freight payer name, address, zip not being required in preferences or checkout | 23 GLOBAL / MULTIPLE | May 18, 2015 10:37 AM
6795 | UI - PL - Label descriptions in Save Item pop-up | 02 SAVED ITEMS | May 18, 2015 10:37 AM
6949 | DB - PL - Marketplace Tamper Evident Zip Tops | 01 SHOP | May 18, 2015 10:38 AM
7260 | DB - Mod Item Number Assignment must see Layflat Bags and Furniture Bags as different | 01 SHOP | May 18, 2015 10:38 AM
7503 | DB - Shop validations not kicking in for VCI | 01 SHOP | May 18, 2015 10:38 AM
7622 | UI - My Account/Shipping/Pallets does not do anything when choose Apply | 16 MY ACCOUNT - SHIPPING | May 18, 2015 10:39 AM
7637 | UI - Inconsistent Locking Error messages | 23 GLOBAL / MULTIPLE | May 18, 2015 10:39 AM
7672 | DB - Rename cart is not locking the new cart name | 05 ACTIVE CART | May 18, 2015 10:40 AM
7729 | PL - Please change default subject line for order confirmations | 12 CHECKOUT - SUMMARY | May 18, 2015 10:41 AM
7009 | DB - Label flags not set properly when Bill-To/Ship-To Same on Order & PO/Label global preferences set | 22 AVANTE | May 18, 2015 10:46 AM
7818 | UI - PL - Show Import Result for Tamper Evident Zip Top (now a Marketplace Catalog Code) | 01 SHOP | May 18, 2015 10:50 AM
6550 | UI - PL - Enhanced Google Analytics tracking | 24 N/A | May 18, 2015 11:15 AM
7855 | DB - PB - Occasional quotes are using 1 Backlog Day for discounting instead of the actual backlog days for the Texas Work Center | 01 SHOP | May 18, 2015 12:06 PM
6320 | DB/UI - PL - Billing Zip Code for Credit Card Transactions | 22 AVANTE | May 18, 2015 03:18 PM
7722 | UI - PL - CR/Sales need to default to "Sharing with a customer? NO." | 06 SHARE ITEM | May 19, 2015 08:36 AM
7964 | Weblocks | 04 SAVED CARTS | May 19, 2015 02:31 PM
7979 | HD-MOD UNABLE TO ADD TO CART | 02 SAVED ITEMS | May 19, 2015 05:28 PM
8015 | DB - Atlanta is ready to start accepting printed jobs | 01 SHOP | May 20, 2015 03:46 PM