## Hot List
Work in process
| Program widget to accept new printing capabilities | 1942, 6276 - Programming and Initial QA complete. Judy and Davidk will run final test. – Spoke with Tom, he ordered plates 6/2 and spoke with departments - we will go live next week. 8147 - Sal, text changes on screen - done needs to roll with Janice's ticket
| Google Analytics - track video plays | 7856 - Ed
| Additional Share item/Share cart enhancements | 7726 - Ed, tested, sent back.
| Fix bug that allows you to add both a domestic and an import w/same MOD# to cart and create a pricing/availability mashup. | 7648 - Sal; done waiting to be tested.
| Changes to improve efficiency of release of credit hold must ship orders | 7954 - Joe (redirected to work on locking issues)
| Change the way lists default for Laddawn operators | 7874 - Sal, done, tested, ready to deploy
| Changes to Order History, dynamic filtering | 7807 - Sal, done, tested, sent back, ready to test again?
| Correct material & additive choices on marketplace items. | 2953, 4363 - Wayne
! | Expand widget's Marketplace capabilities
| Marketplace Pre-Opened Bags on a Roll | 6954 - Wayne - about to start
| Marketplace Registered Printed Zip Tops | 6955 - If Amazing Print not implemented, requires changes to current print menu - some throwaway, some not.
| Marketplace Registered Printed Layflats | 6956 - Same issue as above.
WHAT'S NEXT
1 | Marketplace Zip Tops showing LIVE CHAT for price on Anti Static Pink/Clear IMPORT result | 7849 - Wayne (need info from Tom)
Recently resolved
| Display a Laddawn stock zip top if a Minigrip SKU is directly entered. | 7033 - Joe, 5/26
| Change Text on Venting Nbr of Holes for Marketplace Zip Tops | 7925 - Joe, 5/26 - check dates 7817 - Sal, 5/26
| Marketplace Zip Tops with Vent Hole | 6952 - Wayne, 5/26
| Marketplace Zip Tops w/Hang Hole and Vent Hole | 6953 - Wayne, 5/26
| Provide images for MODs, expanded item descriptions | 7731 - Janice, 5/21
| Please change default subject line for order confirmations to include PO# | 7729 - Ed, done, 5/18 7857 - Joe, 5/22
See help desk report for complete list of updates to live.

## ManageEngine Report Framework
Tickets closed between rolls to LIVE
Generated by Susan Parker on : May 28, 2015 08:08 AM
Total records : 8
Ticket ID | Subject | Section | Resolved Time
7925 | DB - PL - Change Text on Venting Nbr of Holes for Marketplace Zip Tops | 01 SHOP | May 26, 2015 09:09 PM
7817 | UI - PL - Change Text on Venting Nbr of Holes for Marketplace Zip Tops | 01 SHOP | May 26, 2015 09:11 PM
7857 | DB - PL - Please change subject line for sales order acknowledgments | 24 N/A | May 21, 2015 01:27 PM
8071 | DB - HD - item 1764 has incorrect item description when in a cart after Centerfold Sheeting MOD Items | 05 ACTIVE CART | May 22, 2015 03:40 PM
6952 | DB - PL - Marketplace Zip Tops with Vent Hole | 01 SHOP | May 26, 2015 09:07 PM
6953 | DB - PL - Marketplace Zip Tops w/Hang Hole and Vent Hole | 01 SHOP | May 26, 2015 09:08 PM
7731 | DB - PL - No Image When Looking at Expanded Item Descriptions | 01 SHOP | May 21, 2015 02:00 PM
7881 | DB - PB - V-Boarded w/o traveller comment is missing the inches to V-Board to for Furniture Bags | 12 CHECKOUT - SUMMARY | May 27, 2015 11:36 AM