## Sheet1
Work In Process | Description | Est Comp Dt | Est Live Dt | HD Ticket | Notes
| Contract Pricing | 2015-06-16 | On Hold for Pricing | 6546 | Joe - Programming is complete. Judy - began testing yesterday but lost power today. Will finish tonight if possible or tomorrow. Final test is waiting for spreadsheet from Marketing/Sales. Cannot roll to live until this final test is done.
| Item Spcific Work Order Comments | 2015-06-26 | 2015-06-30 | 5474 and 8367 | Sal (UI) - Janice (DB) - Programming should be completed by next Monday 6/22, change from last week because some of Sals time was used for Excel Pricing and Janice took on programming Judy was going to do so she and John could focus on design for Samples. Judy on vacation 6/19 to 6/22. Judy and developers QA/Rework done by 6/26.
| Marketplace Pre-Opened Bags | 2015-06-19 | Unknown | 6954, 8469 and 8577 | Wayne - All initial widget programming is complete. One change in conflict with Joe's task. Wayne now working on 5 addtional programming tasks added from meeting the other day (freight calc, overrun disclaimer, lead times, new subscreen for new fields, color change (White, Clear/Front /Back). Excel became available on Tuesday morning, have yet to get it to work. John experienceing issues with memory and permissions. Testing /rework will begin Tuesday 6/23. As of today John reporting roadblock with excel.
| Marketplace Zip Tops showing LIVE CHAT for price on Anti Static Pink/Clear IMPORT result | On Hold | On Hold | 7849 | Wayne - ON HOLD - (need import pricing info from Tom)
| Tag Manager - track sharing | 2015-06-26 | 2015-06-30 | 8373 | Ed - Number of times click share item from results, share with custom Y or N, sharing from Cart both items and cart and complete to customer Y or N
| Tag Manager - Tracking users that login | 2015-06-26 | 2015-06-30 | 8519 | Ed - capture and account for which customers logged onto our site.
| Tag Manager - Tracking of Orders | 2015-06-18 | 2015-06-30 | 8409 | Ed - This was reopened for issues - system reporting / and cannot tell what it is tracking
| Order Tracking - Some truckers missing | 2015-06-12 | 2015-06-30 | 8418 | Ed - Trucker info for tracking delivery - not all truckers accounted for
What's Next | Expand Widget Marketplace Capabilities
| ** Amber Zip Tops |  |  | 8298 | 8298 - Wayne
| ** Register Print Zip Tops |  |  | 6955 | If Amazing Print not implemented, requires changes to current print menu - some throwaway, some not.
| ** Registered Print Layflats |  |  | 6956 | "
Susan's Feeder List
Recently Resolved