## Sheet1
Work In Process | Description | Est Comp Dt | Est Live Dt | HD Ticket | Notes
| Marketplace Zip Tops showing LIVE CHAT for price on Anti Static Pink/Clear IMPORT result | 2015-07-08 | 2015-07-10 | 7849 | Wayne - should be done with programming today. Judy will test and turn over to Marketing for testing.
| Tag Manager - track sharing | 2015-06-26 | 2015-06-30 | 8373 | Ed - Number of times click share item from results, share with custom Y or N, sharing from Cart both items and cart and complete to customer Y or N
| Tag Manager - Tracking users that login | 2015-06-26 | 2015-06-30 | 8519 | Ed - capture and account for which customers logged onto our site.
| Samples on the Web |  |  | 8751, 9179 | Ed, Janice and Joe - some programming has begun. Judy and John to finish design today.
| Amber Zip Tops | On Hold | On Hold | 8298 | Wayne
What's Next | Expand Widget Marketplace Capabilities
| ** Register Print Zip Tops |  |  | 6955 | If Amazing Print not implemented, requires changes to current print menu - some throwaway, some not.
| ** Registered Print Layflats |  |  | 6956 | "
Susan's Feeder List
Recently Resolved | Contract Pricing |  |  | 6546 | Currently for Staples and Uline
| Item Spcific Work Order Comments |  |  | 5474 and 8367
| Marketplace Pre-Opened Bags |  |  | 6954, 8469 and 8577
| Tag Manager - Tracking of Orders |  |  | 8409 | Navigations as they enter/leave the main areas of the site and quantifying the traffic. Gain understanding of how users navigate through the site. Shop and Checkout Process
| Order Tracking - Some truckers missing |  |  | 8418 | Ed - Trucker info for tracking delivery - not all truckers accounted for