## Sheet1
Work In Process | Description | Est Comp Dt | Est Live Dt | HD Ticket | Notes
| Marketplace Zip Tops showing LIVE CHAT for price on Anti Static Pink/Clear IMPORT result | On Hold | On Hold | 7849 | Wayne - Started programming 7/8 but cannot move forward. Need to discuss with Tom.
| Tag Manager - Tracking users that login | On Hold |  | 8519 | Ed - capture and account for which customers logged onto our site. Waiting for training
| Tag Manager - track sharing | On Hold |  | 8373 | Ed - Number of times click share item from results, share with custom Y or N, sharing from Cart both items and cart and complete to customer Y or N. Waiting on training.
| Samples on the Web | 2015-07-31 | 2015-08-10 | 8751, 9179 | Ed, Janice and Joe - some programming has begun. Judy and John to finish design today. Programming to be completed by 7/31. Test/Rework week of 8/3-8/7
| Auto Hold Release - Pricing and Other Discrepancies | TBD | TBD | 6544, 9196 | Sal - reviewing design to determine technical needs. Once done we will assign dates along with DB developer.
| Amber Zip Tops | On Hold | On Hold | 8298 | Wayne - Waiting for specifications from Marketing
What's Next | Expand Widget Marketplace Capabilities
| ** Register Print Zip Tops |  |  | 6955 | If Amazing Print not implemented, requires changes to current print menu - some throwaway, some not.
| ** Registered Print Layflats |  |  | 6956 | "
Susan's Feeder List
| ** Order Summary Email |  |  |  | Waiting for design handoff
| ** Shipping Notifications |  |  |  | Waiting for design handoff
| ** Promotional Discount Codes |  |  |  | Waiting for design handoff
** Other items as ready
Recently Resolved | Contract Pricing |  |  | 6546 | Currently for Staples and Uline
| Item Spcific Work Order Comments |  |  | 5474 and 8367
| Marketplace Pre-Opened Bags |  |  | 6954, 8469 and 8577
| Tag Manager - Tracking of Orders |  |  | 8409 | Navigations as they enter/leave the main areas of the site and quantifying the traffic. Gain understanding of how users navigate through the site. Shop and Checkout Process
| Order Tracking - Some truckers missing |  |  | 8418 | Ed - Trucker info for tracking delivery - not all truckers accounted for