## Sheet1
Work In Process | Description | Est Comp Dt | Est Live Dt | HD Ticket | Notes
| Marketplace Zip Tops showing LIVE CHAT for price on Anti Static Pink/Clear IMPORT result | 2015-07-14 | 2015-07-24 | 7849 | Wayne - Prgramming complete. When Tom is done testing it can roll immediately.
| Tag Manager - Tracking users that login | On Hold |  | 8519 | Ed - capture and account for which customers logged onto our site. Ed completed training and said it was very useful. Will move onto this task when Samples is done.
| Tag Manager - track sharing | On Hold |  | 8373 | Ed - Number of times click share item from results, share with custom Y or N, sharing from Cart both items and cart and complete to customer Y or N. Next after 8519
| Samples on the Web | 2015-07-31 | 2015-08-10 | 8751, 9179, 9197 | Ed, Janice and Joe - Design is complete as well as aprox 50% of programming. Programming to be completed by 7/31. Test/Rework week of 8/3-8/7
| Auto Hold Release - Pricing and Other Discrepancies | TBD | TBD | 6544, 9196 | Sal, Wayne - should be done with design today and will review with John and Judy by Friday. Programming to begin sometime next week. Still waiting on final design to determine hours and assign dates.
| Amber Zip Tops | On Hold |  | 8298 | Wayne - Waiting for specifications from Marketing
What's Next | Expand Widget Marketplace Capabilities
| ** Register Print Zip Tops |  |  | 6955 | If Amazing Print not implemented, requires changes to current print menu - some throwaway, some not.
| ** Registered Print Layflats |  |  | 6956 | "
Susan's Feeder List
| ** Order Summary Email |  |  |  | Waiting for design handoff
| ** Shipping Notifications |  |  |  | Waiting for design handoff
| ** Promotional Discount Codes |  |  |  | Waiting for design handoff
| ** Amazing Print |  |  |  | Waiting for design handoff
** Other items as ready
Recently Resolved | Due to vacations and design handoffs, we have not completed any priorty list items but have closed some bugs and help desk issues.