## Sheet1
Work In Process | Description | Est Comp Dt | Est Live Dt | HD Ticket | Notes
| Marketplace Zip Tops showing LIVE CHAT for price on Anti Static Pink/Clear IMPORT result | 2015-07-14 | 2015-07-24 | 7849 | Wayne - Prgramming complete. When Tom is done testing it can roll immediately.
| Tag Manager - Tracking users that login | On Hold |  | 8519 | Ed - capture and account for which customers logged onto our site. Ed completed training and said it was very useful. Will move onto this task when Samples is done.
| Tag Manager - track sharing | On Hold |  | 8373 | Ed - Number of times click share item from results, share with custom Y or N, sharing from Cart both items and cart and complete to customer Y or N. Next after 8519
| Samples on the Web | 2015-07-31 | 2015-08-10 | 8751, 9179, 9197, 9399, 9515, 9516 | Ed, Janice, Joe and Wayne - Programming to be completed by 7/31. Test/Rework week of 8/3-8/7
| Auto Hold Release - Pricing and Other Discrepancies | 2015-08-14 | 2015-08-24 | 6544, 9196, 9556 | Sal, Wayne - design is done. Sal is programming the UI side and Janice is programming the DB side. Initial programming completed by 8/14/15. Week of QA and rework to follow.
| Amber Zip Tops | 2015-07-31 | 2015-08-10 | 8298 | Wayne - Specs received. Wayne will program after Samples Order Creation. Will not use Excel as it will work similar to other zip tops which is already in place.
| Predictive Ordering/Messaging Analysis | 1st mtg scheduled for next week | TBD | 9557 | Joe - will be working with Susan and team to determine what information is needed and will perform necessary programming.
What's Next | Expand Widget Marketplace Capabilities
| ** Register Print Zip Tops |  |  | 6955 | If Amazing Print not implemented, requires changes to current print menu - some throwaway, some not.
| ** Registered Print Layflats |  |  | 6956 | "
Susan's Feeder List
| ** Order Summary Email |  |  |  | Waiting for design handoff
| ** Shipping Notifications |  |  |  | Waiting for design handoff
| ** Promotional Discount Codes |  |  |  | Waiting for design handoff
| ** Amazing Print |  |  |  | Waiting for design handoff
** Other items as ready
Recently Resolved | Due to vacations and design handoffs, we have not completed any priorty list items but have closed some bugs and help desk issues.