## Sheet1
Work In Process | Description | Est Comp Dt | Est Live Dt | HD Ticket | Notes
| Tag Manager - Tracking users that login | On Hold |  | 8519 | Ed - capture and account for which customers logged onto our site. Ed completed training and said it was very useful. Ed will start working on this Thursday when done with Samples. Will get a completion date from him as well.
| Tag Manager - track sharing | On Hold |  | 8373 | Ed - Number of times click share item from results, share with custom Y or N, sharing from Cart both items and cart and complete to customer Y or N. Next after 8519
| Samples on the Web | 2015-07-31 | 2015-08-17 | 8751, 9179, 9197, 9399, 9515, 9516 | Programming and QA complete. Will roll to live on Monday night per request from Tina so CE and CR could be trained and changes to specs could be implemented.
| Auto Hold Release - Pricing and Other Discrepancies | 2015-08-14 | 2015-08-31 | 6544, 9196, 9556 | Sal is programming the UI side and Janice is programming the DB side. Initial programming to be completed by 8/25/15. Week of QA and rework to follow. Programming schedule moved out as we needed to move everyone to the Samples project to get it completed.
| Amber Zip Tops | 2015-07-31 | 2015-08-19 | 8298 | Wayne - Programming complete. Wayne will turn over to Tom and Judy tomorrow to test. Can be rolled as soon as testing is done as it is all database work. Wayne will roll independently. Again this was moved out slightly because everyone was put on samples.
| Predictive Ordering/Messaging Analysis | Present Findings | 2015-08-27 | 9557 | Susan, Joe and Tom have met and begun the analysis of the data. May have something to present to Dawn and Ladd within the next couple of weeks.
| Order Summary (Acknowledgement) Email ** |  |  | 10148 | Not yet assigned. Need to review functional specs, create tech specs are estimate time required.
| Shipping Notifications ** |  |  | 10149 | Not yet assigned. Need to review functional specs, create tech specs are estimate time required.
| Online Order Summary (history) ** |  |  | 10150 | Not yet assigned. Need to review functional specs, create tech specs are estimate time required.
** Susan has requested that these 3 items be releaseed at the same time as Auto Hold Release. This make sense however it may delay delivery.
What's Next | Expand Widget Marketplace Capabilities
| ** Register Print Zip Tops |  |  | 6955 | If Amazing Print not implemented, requires changes to current print menu - some throwaway, some not.
| ** Registered Print Layflats |  |  | 6956 | "
Susan's Feeder List
| ** Promotional Discount Codes |  |  |  | Waiting for design handoff
| ** Amazing Print |  |  |  | Waiting for design handoff
** Other items as ready
Recently Resolved | All work has focused on Samples this week and therefore no other items have rolled to live.