## Sheet1
Work In Process | Description | Est Comp Dt | Est Live Dt | HD Ticket | Notes
| Tag Manager - Tracking users that login | 2015-08-24 | 2015-08-25 | 8519 | Ed - capture and account for which customers logged onto our site. Ed is currently working on this ticket and should have it done in the next few days.
| Tag Manager - track sharing | Next after 8519 |  | 8373 | Ed - Number of times click share item from results, share with custom Y or N, sharing from Cart both items and cart and complete to customer Y or N. Next after 8519
| Auto Hold Release - Pricing and Other Discrepancies | 2015-08-31 | 9/7/2015 - However may be delayed by ** changes noted below | 6544, 9196, 9556 | Sal is programming the UI side and Janice is programming the DB side. Completion of this program has been delayed as we had to move everyone to Samples. Also Susan has asked that 3 other mods roll with this that are yet to be programmed.
| Amber Zip Tops | 2015-07-31 | 2015-08-28 | 8298 | Wayne - Programming complete with exception of 1 item where he needs help from Judy. Wayne will turn over to Tom and Judy to test on Tuesday. Can be rolled as soon as testing is done as it is all database work. Wayne will roll independently. Again this was moved out slightly because everyone was put on samples.
| Predictive Ordering/Messaging Analysis |  |  | 9557 | Spoke with Joe and Tom and they will submit tickets for Joe's work as we do with the other projects we are working on with marketing (videos, tiles, tag mgr etc).
| Calculate and Return Product and Packaging Weights for Marketplace MOD items. |  |  | 6535 | Not yet assigned.
| Change MOD overrun Disclaimer |  |  | 8907 | Not yet assigned.
| Order Summary (Acknowledgement) Email ** |  |  | 10148 | Not yet assigned. Need to review functional specs, create tech specs are estimate time required.
| Shipping Notifications ** |  |  | 10149 | Not yet assigned. Need to review functional specs, create tech specs are estimate time required.
| Online Order Summary (history) ** |  |  | 10150 | Not yet assigned. Need to review functional specs, create tech specs are estimate time required.
** Susan has requested that these 3 items be releaseed at the same time as Auto Hold Release. This make sense however it may delay delivery.
What's Next | Expand Widget Marketplace Capabilities
| PL - MP Lip and Tape |  |  | 10281 | Not yet assigned.
| Register Print Zip Tops |  |  | 6955 | If Amazing Print not implemented, requires changes to current print menu - some throwaway, some not.
| Registered Print Layflats |  |  | 6956 | "
| PL - GoDaddy.com Security Reference on the New Laddawn.com |  |  | 10284 | Not yet assigned.
Susan's Feeder List
| ** Promotional Discount Codes |  |  |  | Waiting for design handoff
| ** Amazing Print |  |  |  | Waiting for design handoff
** Other items as ready
Recently Resolved
| Samples on the Web | 2015-07-31 | 2015-08-17