## Sheet1
Work In Process | Description | Est Comp Dt | Est Live Dt | HD Ticket | Notes
Ed | Tag Manager - Tracking users that login | 2015-08-24 | 2015-08-25 | 8519 | Ed - capture and account for which customers logged onto our site. Ed is currently working on this ticket and should have it done in the next few days.
Ed | Tag Manager - track sharing | Next after 8519 |  | 8373 | Ed - Number of times click share item from results, share with custom Y or N, sharing from Cart both items and cart and complete to customer Y or N. Next after 8519
Janice/Sal | Auto Hold Release - Pricing and Other Discrepancies | 2015-09-07 | 9/14/2015 - However may be delayed by ** changes noted below | 6544, 9196, 9556 | Sal is programming the UI side and Janice is programming the DB side. Completion of this program has been delayed as we had to move everyone to Samples. Also Susan has asked that 3 other mods roll with this that are yet to be programmed.
Joe | Predictive Ordering/Messaging Analysis | Next Review meeting 9/3/15 |  | 9557, 11055 | Spoke with Joe and Tom and they will submit tickets for Joe's work as we do with the other projects we are working on with marketing (videos, tiles, tag mgr etc). Joe has started the programming the first test for notifications by sending email.
Joe | Calculate and Return Product and Packaging Weights for Marketplace MOD items. | 2015-09-04 |  | 6535 | Joe working on this
Joe | Change MOD overrun Disclaimer | 2015-09-04 |  | 8907 | Joe working on this
Janice/Sal | Order Summary (Acknowledgement) Email ** | 2015-09-07 | 2015-09-14 | 10148 | Sal and Janice are adding this in to the work they are doing on the Auto Hold logic.
Janice/Sal | Online Order Summary (history) ** | 9/715 | 2015-09-14 | 10150 | Sal and Janice are adding this in to the work they are doing on the Auto Hold logic.
John | PL - GoDaddy.com Security Reference on the New Laddawn.com | 2015-09-11 | 2015-09-11 | 10284 | JP has it now, may reassign to a UI developer.
Ed | UI/HD - unable to get part numbers of labels | 2015-09-02 | 2015-09-02 | 11142 | Ed working on this now.
| DB PL - specify vent location on zip top bags | 2015-09-04 | 2015-09-04 | 10077 | Wayne working on this.
| Shipping Notifications ** |  |  | 10149 | Not yet assigned. Need to review functional specs, create tech specs are estimate time required.
What's Next | Expand Widget Marketplace Capabilities
| PL - MP Lip and Tape |  |  | 10281 | Not yet assigned - still some outstanding questions for Marketing (about new fields in the Widget).
| Register Print Zip Tops |  |  | 6955 | If Amazing Print not implemented, requires changes to current print menu - some throwaway, some not.
| Registered Print Layflats |  |  | 6956 | "
Susan's Feeder List
| ** Category Menu Design |  |  |  | Waiting for design handoff
| ** Promotional Discount Codes |  |  |  | Waiting for design handoff
| ** Amazing Print |  |  |  | Waiting for design handoff
| ** NS on the Web |  |  |  | Waiting for design handoff
** Other items as ready
Recently Resolved
| Amber Zip Tops | 2015-07-31 | 2015-08-27 | 8298 | Wayne - Programming complete with exception of 1 item where he needs help from Judy. Wayne will turn over to Tom and Judy to test on Tuesday. Can be rolled as soon as testing is done as it is all database work. Wayne will roll independently. Again this was moved out slightly because everyone was put on samples.
| Samples on the Web | 2015-07-31 | 2015-08-17