## Sheet1
Work In Process | Description | Est Comp Dt | Est Live Dt | HD Ticket | Notes
Ed | Tag Manager - Tracking users that login | 2015-08-24 |  | 8519 | Ed - capture and account for which customers logged onto our site. This is a work in progress. Ed has not worked on this for the last few weeks as he has been working on P1 bug fixes.
Ed | Tag Manager - track sharing | Next after 8519 |  | 8373 | Ed - Number of times click share item from results, share with custom Y or N, sharing from Cart both items and cart and complete to customer Y or N. Next after 8519
Janice/Sal | Auto Hold Release - Pricing and Other Discrepancies | 10.9.15 | 10.16.15 | 6544, 9196, 9556 | Sal is programming the UI side and Janice is programming the DB side. Completion of this program has been delayed as we had to move everyone to Samples. Also Susan has asked that 3 other mods roll with this that are yet to be programmed.
Janice/Sal | Order Summary (Acknowledgement) Email ** | 10.9.15 | 10.16.15 | 10148 | Sal and Janice are adding this in to the work they are doing on the Auto Hold logic.
Janice/Sal | Online Order Summary (history) ** | 10.9.15 | 10.16.15 | 10150 | Sal and Janice are adding this in to the work they are doing on the Auto Hold logic.
Joe | Change MOD overrun Disclaimer | 9.21.15 | 10.16.15 | 8907 | Joe will be working on the overrun disclaimer and also the Order Summary and Ackn changes for Auto Hold logic next.
Joe | Fax Only Order Acknowledgements | 10.9.15 | 10.16.15 | 11550 | Joe - price discrepancy work
Joe | Predictive Ordering/Messaging Analysis |  |  | 9557, 11055 | Spoke with Joe and Tom and they will submit tickets for Joe's work as we do with the other projects we are working on with marketing (videos, tiles, tag mgr. etc.). Joe has started the programming the first test for notifications by sending email.
Wayne | Calculate and Return Product and Packaging Weights for Marketplace MOD items. | 2015-09-16 | 2015-09-18 | 6535, 6409, 6725, 8177, 9129 | Wayne will be done on Thursday with several Weight related bug fixes and will be working on task associated with the Price Discrepancy project.
Wayne | Price Discrepancy Order Cancellation | 10.9.15 | 10.16.15 | 11551 | Wayne working on this beginning Thursday
John | PL - GoDaddy.com Security Reference on the New Laddawn.com |  |  | 10284 | JP has it now, may reassign to a UI developer.
Ed | UI/PL - Add "Folded" to Item Description Line | 9.16.15 | 10.16.15 | 9274, 10602 | "Folded" is already in results but nowhere else in the site.
Judy | Running Avante Lead Time and Backlog Program more Frequently | 9.18.15 | 9.18.15 | 11503 | Judy wrapping up some other work including a main milestone of Price Discrepancy then will do this work on Friday.
What's Next | Expand Widget Marketplace Capabilities
| Shipping Notifications ** |  |  | 10149 | Not yet assigned. Need to review functional specs, create tech specs are estimate time required.
| PL - MP Lip and Tape |  |  | 10281 | Not yet assigned - still some outstanding questions for Marketing (about new fields in the Widget).
| Register Print Zip Tops |  |  | 6955 | If Amazing Print not implemented, requires changes to current print menu - some throwaway, some not.
| Registered Print Layflats |  |  | 6956 | "
Susan's Feeder List
| ** Amazing Print |  |  |  | Waiting for design handoff
| ** Category Menu Design |  |  |  | Waiting for design handoff
| ** Promotional Discount Codes |  |  |  | Waiting for design handoff
| ** NS on the Web |  |  |  | Waiting for design handoff
** Other items as ready
Janice and Sal - Auto Hold
Wayne - Auto Hold, Marketplace, p1
Joe - Auto Hold, Predictive and P1 Bugs
Ed - P1 Bugs, Google Analytics
Recently Resolved
11557 | UI - PB - Unable to send quotes to NEPB customer via share cart/share item
11492 | DB - PB - "DUPLICATE" MOD numbers showing in orders in order history
10077 | DB - PL - Specified Vent Location Zip Top Bags
11589 | DB - HD/PB - REQUEST 1736979 Must ship today didn't print as such - Iowa orders not being flagged as must ship today type 2
11622 | DB - HD/PB - DUPLICATE MODS in order history
11644 | DB - Add Shipto State and Shipto Zip to the Unscheduled Custom Order Report