## Feeder List
Row # | Priority | Issue | Notes | Drivers | On agenda for Thurs | ETA for handoff
1 | 1 | Sample orders, sample bank | Not ticketed yet. | Efficiency | 2015-06-04 | 2015-06-05
2 | 1 | Pricing and other discrepancies: Automated hold/release logic | 6544 - Flow chart done. Present that along w/design elements to Ladd & Dawn 5/28 | Efficiency | 2015-06-04 | 2015-06-11
3 | 1 | Replace current print menu w/Amazing print, enable registered printing | 6551 - | Sales | 2015-06-04 | TBD
4 | 1 | Basic predictive ordering | 6549 - Get going on design 6/8 | Sales | 2015-06-11 | 2015-06-18
5 | 1 | Simple messaging | Get going on design 6/8 | Sales | 2015-06-11 | 2015-06-18
6 | 1 | Form for initiating RMAs online | 6545 - Get going on design 6/8 | Efficiency | 2015-06-11 | 2015-07-02
7 | 1 | Category dropdown redesign - enable Bags category to scale better to more choices. Probably applies to other menus (eg carrier list) | 6547 - | Sales | 2015-06-18 | 2015-07-02
8 | 1 | Convert NS quoting to "dumb" web interface | Prelim conversations held. Get going on design 6/15, work w/IT. | Efficiency | 2015-06-25 | 2015-07-02
9 | 1 | Enable sales order changes - CE only? During period TBD (order placement to print in warehouse, or…?) | Not ticketed. Bundle with other work that affects order history? | Efficiency | ? | ?
10 | 1 | Implement promotional codes |  | Sales
11 | 1 | Predictive ordering phase 2 |  | Sales
12 | 1 | Predictive ordering phase 3 |  | Sales
13 | 2 | Better language around backlog discount/upcharge | Owen working on mockups w/Haley. | Usability
14 | 2 | Incorporate bill to, ship to and contact numbers into UI as unobtrusively as possible. | Various screens TBD. Design needed. This will help CE today; it will be absolutely necessary when we move most/all transactions off Avante. | Efficiency
15 | 2 | Enable predictive searches of contacts to go against sales org | 5473 DB/UI | Usability
16 | 2 | Display customer PSP (pricing level); enable more efficient response to price deviation requests. (Came from Tina's wish list). | 7004 - Design needed. | Efficiency
17 | 2 | Add "Call for Pickup" to Special Instructions | 7887 - ready to be assigned. | Usability
18 | 2 | More control to override the bundling defaults. Full view of inventory during the bundling process We often have to put the order on hold to make adjustments in Avante | From Tina's wish list. Need to gather data on why this is necessary, and if there is a better programmatic solution then giving CE ability to do more varied overrides than currently allowed. Let Tina know about this, but have not been able to get together w/her this past week. | Efficiency
19 | 2 | Leave me logged in | 5472 - May require discussion? Less of an issue now that locking is not as frequent. | Usability
20 | 2 | Simplification of Sheeting and Film Widget Selections | Is this really part of category menu redesign? | Usability
21 | 2 | Create an email-viewable version of the order summary (also printable) -Link order history to the above email -Send above email from create order | Some of this came up right after launching. Needs design. Build off of ticket 3708. | Usability
22 | 2 | Add new timestamp of Checkout by customer | Talk to CE. Another idea was to BCC order confirmations to a mailbox monitored by CE (separate from the queue) | Efficiency
23 | 2 | Add remaining transactions and streamline the "onramp" by making it contact-based v. bill to based. | This needs to be broken up into distinct phases or components. | Efficiency
24 | 2 | Allow CE to switch between bill to's w/in web session | 5974 - requires discussion, design and assessment of level of effort. | Efficiency
25 | 2 | Redirect customers back to the web based on link in email | Not sure what this was - shared carts and items? (Order acknowledgment is mentioned on another line.) | Usability
26 | 2 | CPU zip code indicator. In various places we show zip codes - eg pricing history, tooltips, etc. But we don't differentiate between CPU and ship to. | May need design. | Usability
27 | 2 | Ability for managers to view our costs for price overrides |  | Efficiency
28 | 3 | Allow user to delete product use, location and customer item numbers | Wait and see; possible not enough time has elapsed for this to be noticed. Keep as 3 for now. | Usability
29 | 2 | Tool for finding the right sized bag. | 7250. Requires design. Will Moore has created a spreadsheet. See also catalog. | Sales
30 | 2 | Reduce some of the obscure CE choices in special instructions - for example "bring to Jim D when ready" |  | Efficiency
31 | 2-3 | Customer selection of export pallet on order will trigger email to purchasing |  | Efficiency
32 | 4 | Gray out non-shipping days on calendar | Probably could stand to be tweaked, but the way this is working seems adequate for now. | Usability
33 | 3-4 | Display red marker flags by missing data |  | Usability
34 | 3-4 | Ability to toggle UOM |  | Usability
35 | 2 | Allow View of NS and Sample Orders |  | Some/all of above
36 | 2-3 | Notifications to customer that order/item(s) have shipped – or cancellation |  | Some/all of above
37 | 3 | Advertise Brandit to non-Brandit customers where logo would otherwise appear when sharing carts/items |  | Sales
38 | 3 | Add Medical Grade Pallets | Reassess need. Talk to Sales, CE & purchasing. | Efficiency
39 | 3 | Sharing stock only cart should create a price inquiry ce request | Talk to Tina and Meme. | Efficiency
40 | 2-3 | Add invoices to order history | Design needed for online version of invoice? | Some/all of above
41 | 3 | Narrative thread | Needs major group design effort to resume? | Sales
42 | 4 | Allow color Brandit logos |  | Sales
43 | 3 | Freight estimator | 6548 - Analysis and design needed. | Some/all of above
44 | 3-4 | Be able to type in description/dimensions in the “quick add part number” box in the cart…similar to the ability in that we have on the lines in Avante and hit F3.... (this is a longshot I think) but thought we’d throw it out there anyway. | From Tina's "wish list." Push back? | Efficiency
45 | 3 | Show Open/Changeable vs. Processed Orders | This will be combined with some of the high priority stuff above like sample orders and sales order changes | Some/all of above
46 | 3 | Connecting specific “Certs Requests” after the fact to Specific Orders |  | Some/all of above
47 | 3-4 | Social media integration | Requires discussion - what's the strategy overall? | Sales
48 | 3-4 | Create preference for disallowing verbal Pos | Talk to Sales, CE | Efficiency
49 | ? | NS item ordering | Not sure what this is
50 | ? | Various YMAC changes | Not sure what this is
51 | ? | Modify substitute logic to draw on specialized YMAC rules | Not sure what this is
52 | ? | Change prompting, defaults and validations for pink amine free | Still needed or done?
53 | ? | Add double wound sheeting
54 | ? | Zip code intelligence for anonymous user | Still desired?
55 | ? | Redesign Sharing of Unsaved item | Revisit; either a 3 or 4 or eliminate.
56 | ? | Enhance Share/Fax functionality for “no email” contacts | Not sure what this is or how desirable it still is
57 | ? | Allow CE to change date to expedite order to production | Needs discussion w/CE. Dawn has concerns about CE over-expediting.
| ? | Secure ability to change Bill-to information | What is this?
| ? | Keyboard interaction | Tickets have been entered, maybe some even closed – need to research.
| ? | Carts with plates must be in their own cart

## Drivers
Data validation
Sales
Efficiency
Usability
Stability & uptime
Some/all of above
Other