## 24 Scenarios
For this test, 2 hours will equal [TBD]; 24 hours will equal [TBD]. | Laddawn customer-email | Laddawn customer-fax | NEPB customer-email | NEPB customer-fax | Pass/Fail - describe Fails
There is a price discrepancy. Verify CE drawer interface; open CE drawer, check price discrepancy box. Enter customer PO price that is less than our price. (Determine in advance if you are testing slight or significant.) | Drawer | Same | Same | Same
CE operator checks box but fails to enter PO price, then attempts to close drawer. Verify error message. Correct error, click checkout. | Drawer error | Same | Same | Same
Price discrepancy less than 6%
Customer has default preference - "I am good with this." | Preference in My Account | Same | N/A - no prefs | N/A - no prefs
Verify that price discrepancies are highlighted on Shipping & Packaging screen in checkout. Next, test 3 scenarios to verify you get the appropriate messaging when you click "save & continue" to proceed to the next screen: | Shipping & packaging | Same | Same | Same
Order entered before 11 am local warehouse time | Do not call customer msg | Same | Same | Same
Order entered after 11 am local warehouse time, without "must ship today" checked | Do not call customer msg | Same | Same | Same
Order entered after 11 am local warehouse time, with "must ship today" checked (before proceeding, pretend you called and left message) | Call customer msg | Same | Same | Same
Proceed through payment and labeling to order summary, verify price discrepancies are highlighted in order summary. Place order. Check for two simultaneous outputs: | Order summary | Same | Same | Same
1) System sends notification #1 to customer (t=0 hrs) - check to be sure message sent with high importance. | Email spec | Fax spec | Email spec (NEPB) | Fax spec (NEPB)
2) Verify new order confirmation pop-up referencing discrepancy - click Continue. Remain logged in. | Order confirmation pop-up | Same except "Sent to:" should be to a fax number. | Same | Same except "Sent to:" should be to a fax number.
After you are returned to shop widget, look in the Purple CE Requests Tab. There s/b an add’l CE Request for every individual order created for the master order. The price discrepancy request s/b completely disabled, and s/b showing that it’s on hold and routed to the generic price discrepancy operator. The user can put the order’s request on hold too if there is something else that the order needs to be held up for (ie, date expedite). Logout. | CE drawer | Same | Same | Same
Upon return to Avante, the price discrepancy requests s/b created with an OPEN status, so that it keeps the order on hold. You can view the requests using SOP9120 if you jot down the request numbers, or via SOP2001 (order display) using Options menu > C/E Request display. This will show you all requests that are attached to that order, and will then take you to SOP9120 to view each. On the main screen of order display, the order should show as on REQUEST HOLD. It may additionally show as on CREDIT hold if the customer is over their credit limit. IMPORTANT: Be sure you have closed out of the request before you proceed. | No mockup | Same | Same | Same
Customer responds within 2 hours
Customer responds online via email link. They are brought to new order summary w/approve & cancel buttons. | Order summary w/approve/cancel | N/A* | N/A - can't go online | N/A - can't go online
Price is acceptable - click "approve order" - get regular order confirmation pop-up (no reference to price discrepancy), check 4 outputs: | Pop-up as it is today | N/A | N/A | N/A
New order acknowledgment - check for all details such as special instructions, freight info, product description, etc. Be sure to also check email subject line as described in mockup. | Order ack email | N/A | N/A | N/A
Order history shows the order | Order history (as it is today) | N/A | N/A | N/A
New order summary from order history | Order summary | N/A | N/A | N/A
Go to Avante: All CE price discrepancy requests for the MASTER ORDER should have a closed status. There should be a time/date stamp in the Dates screen of the request (F9) showing when the order was approved. The F8-On Hold screen shows who approved the order (LADDAWN.COM being the customer, or CE operator code). The Hold field in the main screen of Sales Order Display should now show the order as AUTHORIZED (unless there are other Requests on hold or the order is on Credit Hold). Once authorized, the order will print in the warehouse within 1 minute if Auto Picking Slips is running. | No mockup | N/A | N/A | N/A
[END]
Price is not acceptable - click "cancel order" - get confirm cancellation pop-up (click yes), then check for 7 outputs: | Confirm cancellation | N/A | N/A | N/A
Email (or fax) cancellation acknowledgment. Be sure to also check email subject line as described in mockup. | Order ack email w/cancellation | N/A | N/A | N/A
Order history appearance - reflects cancellation - it says "Order cancelled" below the order name. | Order history w/cancellation | N/A | N/A | N/A
Order summary from order history - reflects cancellation [Note, mockup depicts only some lines which have been cancelled. When an order is cancelled this way, all lines will have been cancelled. Also, mockup has not been updated to show that quantity and extended price will be zeroed out.] | Order summary w/cancellation | N/A | N/A | N/A
Order tooltip (hover over order name) - reflects cancellation | Order name tooltip w/cancellation | N/A | N/A | N/A
Reprice (reorder pop-up) - reflects cancellation | Reprice w/cancellation | N/A | N/A | N/A
Go to Avante: All CE price discrepancy requests for the MASTER ORDER should have a closed status. There should be a time/date stamp in the Dates screen of the request (F9) showing when the order was approved. The F8-On Hold screen shows who approved the order (LADDAWN.COM being the customer, or CE operator code). The Hold field in the main screen of Sales Order Display should now show the order as AUTHORIZED (unless there are other Requests on hold or the order is on Credit Hold). Once authorized, the order will print in the warehouse within 1 minute if Auto Picking Slips is running. | No mockup | N/A | N/A | N/A
[END]
Customer responds by faxing/calling/emailing CE - pretend you have very little info to go on, like no order number. [This script does not address scenarios involving individual line cancellations, price overrides or other "sales order changes" handled in Avante.]
CE locates pending order in order history. (Are you able to easily locate it?) | Pending order link | Same | Same | Same
Click pending order link; brings you to new order summary w/approve & cancel buttons. | Order summary w/approve/cancel | Same | Same | Same
Price is acceptable - click "approve order" - get regular order confirmation pop-up (no reference to price discrepancy), check 4 outputs: | Pop-up as it is today (CE version) | Same ("Sent to:" should be to a fax number) | Same | Same ("Sent to:" should be to a fax number)
New order acknowledgment - check for all details such as special instructions, freight info, product description, etc. Be sure to also check email subject line as described in mockup. | Order ack email | Optio acknowledgments (1 for every order w/in master order) | Same as Laddawn but contains NEPB logo + no reference to ladddawn.com | Optio acknowledgments (1 for every order w/in master order)
Order history shows the order | Order history (as it is today) | Same | Same | Same
New order summary from order history | Order summary | Same | Same | Same
Go to Avante: All CE price discrepancy requests for the MASTER ORDER should have a closed status. There should be a time/date stamp in the Dates screen of the request (F9) showing when the order was approved. The F8-On Hold screen shows who approved the order (LADDAWN.COM being the customer, or CE operator code). The Hold field in the main screen of Sales Order Display should now show the order as AUTHORIZED (unless there are other Requests on hold or the order is on Credit Hold). Once authorized, the order will print in the warehouse within 1 minute if Auto Picking Slips is running.
[END]
Price is not acceptable - click "cancel order" - get confirm cancellation pop-up (click yes), then check for 7 outputs: | Confirm cancellation | Same | Same | Same
Email (or fax) cancellation acknowledgment. Be sure to also check email subject line as described in mockup. | Order ack email w/cancellation | Optio acknowledgments (1 for every order w/in master order) | Same as Laddawn but contains NEPB logo + no reference to ladddawn.com | Optio acknowledgments (1 for every order w/in master order)
Order history appearance - reflects cancellation - it says "Order cancelled" below the order name. | Order history w/cancellation | Same | Same | Same
Order summary from order history - reflects cancellation [Note, mockup depicts only some lines which have been cancelled. When an order is cancelled this way, all lines will have been cancelled. Also, mockup has not been updated to show that quantity and extended price will be zeroed out.] | Order summary w/cancellation | Same | Same | Same
Order tooltip (hover over order name) - reflects cancellation | Order name tooltip w/cancellation | Same | Same | Same
Reprice (reorder pop-up) - reflects cancellation | Reprice w/cancellation | Same | Same | Same
Go to Avante: All CE price discrepancy requests for the MASTER ORDER should have a closed status. There should be a time/date stamp in the Dates screen of the request (F9) showing when the order was approved. The F8-On Hold screen shows who approved the order (LADDAWN.COM being the customer, or CE operator code). The Hold field in the main screen of Sales Order Display should now show the order as AUTHORIZED (unless there are other Requests on hold or the order is on Credit Hold). Once authorized, the order will print in the warehouse within 1 minute if Auto Picking Slips is running.
[END]
Customer does not respond within two hours. Order is released; check for 4 outputs:
New order acknowledgment - check for all details such as special instructions, freight info, product description, etc. Be sure to also check email subject line as described in mockup. | Order ack email | Optio acknowledgments (1 for every order w/in master order) | Order ack email - same as Laddawn except has NEPB logo and no refs to Laddawn | Optio acknowledgments (1 for every order w/in master order)
Order history shows the order | Order history (as it is today)
New order summary from order history | Order summary
Go to Avante: All CE price discrepancy requests for the MASTER ORDER should have a closed status. There should be a time/date stamp in the Dates screen of the request (F9) showing when the order was approved. The F8-On Hold screen shows who approved the order (LADDAWN.COM being the customer, or CE operator code). The Hold field in the main screen of Sales Order Display should now show the order as AUTHORIZED (unless there are other Requests on hold or the order is on Credit Hold). Once authorized, the order will print in the warehouse within 1 minute if Auto Picking Slips is running. | No mockup
[END]
Customer has "no need to wait" preference | Preference in My Account | Same | N/A | N/A
Verify you get "do not call" message regardless of time of order placement and whether or not 'must ship today' is chosen. Message appears when you click "save & continue" to proceed to next screen:
Order entered before 11 am local warehouse time | Do not call customer msg | Same | N/A | N/A
Order entered after 11 am local warehouse time, without "must ship today" checked | Do not call customer msg | Same | N/A | N/A
Order entered after 11 am local warehouse time, with "must ship today" checked | Do not call customer msg | Same | N/A | N/A
Proceed through payment and labeling to order summary, verify price discrepancies are highlighted. You should also see checkbox for suppressing order acknowledgment (don't use it though). | Order summary | Same | N/A | N/A
Place order. Then verify 5 outputs - the first two are simultaneous. |  |  | N/A | N/A
Get regular order confirmation pop-up (no reference to price discrepancy notice being sent). Cllck continue and remain logged in. | Pop-up as it is today (CE version) | Same ("Sent to:" should be to a fax number)
System sends new order acknowledgment - check for all details such as special instructions, freight info, product description, etc. Be sure to also check email subject line as described in mockup. | Order ack email | Optio acknowledgments (1 for every order w/in master order) | N/A | N/A
Verify that no price discrepancy requests are created in the purple CE request drawer. | No mockup | Same | N/A | N/A
Order history shows the order | Order history (as it is today) | Same | N/A | N/A
New order summary from order history | Order summary | Same | N/A | N/A
Close request in Avante. Verify that no price discrepancy requests are in an OPEN status in Avante. | No mockup | Same | N/A | N/A
[END]
Customer has "wait for my approval" preference | Preference in My Account | Same | N/A | N/A
Verify you get message to call regardless of time of order placement and whether or not 'must ship today' is chosen. Message appears when you click "save & continue" to proceed to next screen:
Order entered before 11 am local warehouse time | Call customer msg | Same | N/A | N/A
Order entered after 11 am local warehouse time, without "must ship today" checked | Call customer msg | Same | N/A | N/A
Order entered after 11 am local warehouse time, with "must ship today" checked (pretend you called and left message) | Call customer msg | Same | N/A | N/A
Proceed through payment and labeling to order summary, verify price discrepancies are highlighted, place order. Verify two simultaneous outputs: | Order summary | Same | N/A | N/A
1) System sends notification #3a to customer (t=0 hrs) - check to be sure message sent with high importance. | Email spec | Fax spec | N/A | N/A
2) Verify new order confirmation pop-up referencing discrepancy - click Continue. Remain logged in. | Order confirmation pop-up | Same ("Sent to:" should be to a fax number) | N/A | N/A
After you are returned to shop widget, look in the Purple CE Requests Tab. There s/b an add’l CE Request for every individual order created for the master order. The price discrepancy request s/b completely disabled, and s/b showing that it’s on hold and routed to the generic price discrepancy operator. The user can put the order’s request on hold too if there is something else that the order needs to be held up for (ie, date expedite). Logout. | CE drawer | Same | N/A | N/A
Upon return to Avante, the price discrepancy requests s/b created with an OPEN status, so that it keeps the order on hold. You can view the requests using SOP9120 if you jot down the request numbers, or via SOP2001 (order display) using Options menu > C/E Request display. This will show you all requests that are attached to that order, and will then take you to SOP9120 to view each. On the main screen of order display, the order should show as on REQUEST HOLD. It may additionally show as on CREDIT hold if the customer is over their credit limit. IMPORTANT: Be sure you have closed out of the request before you proceed. | No mockup | Same | N/A | N/A
Customer responds within 24 hours
Customer responds online via email link. They are brought to new order summary w/approve & cancel buttons. | Order summary w/approve/cancel | N/A* | N/A | N/A
Price is acceptable - click "approve order" - get regular order confirmation pop-up (no reference to price discrepancy notice being sent). Click continue. Then verify 4 outputs: | Pop-up as it is today | N/A | N/A | N/A
New order acknowledgment - check for all details such as special instructions, freight info, product description, etc. Be sure to also check email subject line as described in mockup. | Order ack email | N/A | N/A | N/A
Order history shows the order | Order history (as it is today) | N/A | N/A | N/A
New order summary from order history | Order summary | N/A | N/A | N/A
Go to Avante: All CE price discrepancy requests for the MASTER ORDER should have a closed status. There should be a time/date stamp in the Dates screen of the request (F9) showing when the order was approved. The F8-On Hold screen shows who approved the order (LADDAWN.COM being the customer, or CE operator code). The Hold field in the main screen of Sales Order Display should now show the order as AUTHORIZED (unless there are other Requests on hold or the order is on Credit Hold). Once authorized, the order will print in the warehouse within 1 minute if Auto Picking Slips is running. | No mockup | N/A | N/A | N/A
[END]
Price is not acceptable - click "cancel order" - get confirm cancellation pop-up (click yes), then check for 7 outputs: | Confirm cancellation | N/A | N/A | N/A
Email (or fax) cancellation acknowledgment. Be sure to also check email subject line as described in mockup. | Order ack email w/cancellation | N/A | N/A | N/A
Order history appearance - reflects cancellation - it says "Order cancelled" below the order name. | Order history w/cancellation | N/A | N/A | N/A
Order summary from order history - reflects cancellation [Note, mockup depicts only some lines which have been cancelled. When an order is cancelled this way, all lines will have been cancelled. Also, mockup has not been updated to show that quantity and extended price will be zeroed out.] | Order summary w/cancellation | N/A | N/A | N/A
Order tooltip (hover over order name) - reflects cancellation | Order name tooltip w/cancellation | N/A | N/A | N/A
Reprice (reorder pop-up) - reflects cancellation | Reprice w/cancellation | N/A | N/A | N/A
Go to Avante: All CE price discrepancy requests for the MASTER ORDER should have a closed status. There should be a time/date stamp in the Dates screen of the request (F9) showing when the order was approved. The F8-On Hold screen shows who approved the order (LADDAWN.COM being the customer, or CE operator code). The Hold field in the main screen of Sales Order Display should now show the order as AUTHORIZED (unless there are other Requests on hold or the order is on Credit Hold). Once authorized, the order will print in the warehouse within 1 minute if Auto Picking Slips is running. | No mockup | N/A | N/A | N/A
[END]
Customer responds by faxing/calling/emailing CE - pretend you have very little info to go on, like no order number. [This script does not address scenarios involving individual line cancellations, price overrides or other "sales order changes" handled in Avante.]
CE locates pending order in order history. (Are you able to easily locate it?) | Pending order link | Same | N/A | N/A
Click pending order link; brings you to new order summary w/approve & cancel buttons. | Order summary w/approve/cancel | Same | N/A | N/A
Price is acceptable - click "approve order" - get regular order confirmation pop-up (no reference to price discrepancy notice being sent). Click continue and remain logged in. Then verify 4 outputs: | Pop-up as it is today (CE version) | Same ("Sent to:" should be to a fax number) | N/A | N/A
New order acknowledgment - check for all details such as special instructions, freight info, product description, etc. Be sure to also check email subject line as described in mockup. | Order ack email | Optio acknowledgments (1 for every order w/in master order) | N/A | N/A
Order history shows the order | Order history (as it is today) | Same | N/A | N/A
New order summary from order history | Order summary | Same | N/A | N/A
Go to Avante: All CE price discrepancy requests for the MASTER ORDER should have a closed status. There should be a time/date stamp in the Dates screen of the request (F9) showing when the order was approved. The F8-On Hold screen shows who approved the order (LADDAWN.COM being the customer, or CE operator code). The Hold field in the main screen of Sales Order Display should now show the order as AUTHORIZED (unless there are other Requests on hold or the order is on Credit Hold). Once authorized, the order will print in the warehouse within 1 minute if Auto Picking Slips is running. | No mockup | Same | N/A | N/A
[END]
Price is not acceptable - click "cancel order" - get confirm cancellation pop-up (click yes, remain logged in), then check for 7 outputs: | Confirm cancellation | Same | N/A | N/A
Email (or fax) cancellation acknowledgment. Be sure to also check email subject line as described in mockup. | Order ack email w/cancellation | Optio acknowledgments (1 for every order w/in master order)
Order history appearance - reflects cancellation - it says "Order cancelled" below the order name. | Order history w/cancellation | Same | N/A | N/A
Order summary from order history - reflects cancellation [Note, mockup depicts only some lines which have been cancelled. When an order is cancelled this way, all lines will have been cancelled. Also, mockup has not been updated to show that quantity and extended price will be zeroed out.] | Order summary w/cancellation | Same | N/A | N/A
Order tooltip (hover over order name) - reflects cancellation | Order name tooltip w/cancellation | Same | N/A | N/A
Reprice (reorder pop-up) - reflects cancellation | Reprice w/cancellation | Same | N/A | N/A
Go to Avante: All CE price discrepancy requests for the MASTER ORDER should have a closed status. There should be a time/date stamp in the Dates screen of the request (F9) showing when the order was approved. The F8-On Hold screen shows who approved the order (LADDAWN.COM being the customer, or CE operator code). The Hold field in the main screen of Sales Order Display should now show the order as AUTHORIZED (unless there are other Requests on hold or the order is on Credit Hold). Once authorized, the order will print in the warehouse within 1 minute if Auto Picking Slips is running. | No mockup | Same | N/A | N/A
[END]
Customer does not respond within 24 hours
System sends notification #3B to customer. Notification #3B is forwarded to queue. CE calls and … | Email spec | Fax spec | N/A | N/A
Customer answers when CE calls, calls back after getting message, or replies via fax or email w/in 24 hours.
CE locates pending order in order history. (Are you able to easily locate it?) | Pending order link | Same | N/A | N/A
Click pending order link; brings you to new order summary w/approve & cancel buttons. | Order summary w/approve/cancel | Same | N/A | N/A
Price is acceptable - click "approve order" - get regular order confirmation pop-up (no reference to price discrepancy notice being sent). Click continue and remain logged in. Then verify 4 outputs: | Pop-up as it is today (CE version) | Same ("Sent to:" should be to a fax number) | N/A | N/A
New order acknowledgment - check for all details such as special instructions, freight info, product description, etc. Be sure to also check email subject line as described in mockup. | Order ack email | Optio acknowledgments (1 for every order w/in master order) | N/A | N/A
Order history shows the order | Order history (as it is today) | Same | N/A | N/A
New order summary from order history | Order summary | Same | N/A | N/A
Go to Avante: All CE price discrepancy requests for the MASTER ORDER should have a closed status. There should be a time/date stamp in the Dates screen of the request (F9) showing when the order was approved. The F8-On Hold screen shows who approved the order (LADDAWN.COM being the customer, or CE operator code). The Hold field in the main screen of Sales Order Display should now show the order as AUTHORIZED (unless there are other Requests on hold or the order is on Credit Hold). Once authorized, the order will print in the warehouse within 1 minute if Auto Picking Slips is running. | No mockup | Same | N/A | N/A
[END]
Price is not acceptable - click "cancel order" - get confirm cancellation pop-up (click yes, remain logged in), then check for 7 outputs: | Confirm cancellation | Same | N/A | N/A
Email (or fax) cancellation acknowledgment. Be sure to also check email subject line as described in mockup. | Order ack email w/cancellation | Optio acknowledgments (1 for every order w/in master order) | N/A | N/A
Order history appearance - reflects cancellation - it says "Order cancelled" below the order name. | Order history w/cancellation | Same | N/A | N/A
Order summary from order history - reflects cancellation [Note, mockup depicts only some lines which have been cancelled. When an order is cancelled this way, all lines will have been cancelled. Also, mockup has not been updated to show that quantity and extended price will be zeroed out.] | Order summary w/cancellation | Same | N/A | N/A
Order tooltip (hover over order name) - reflects cancellation | Order name tooltip w/cancellation | Same | N/A | N/A
Reprice (reorder pop-up) - reflects cancellation | Reprice w/cancellation | Same | N/A | N/A
Go to Avante: All CE price discrepancy requests for the MASTER ORDER should have a closed status. There should be a time/date stamp in the Dates screen of the request (F9) showing when the order was approved. The F8-On Hold screen shows who approved the order (LADDAWN.COM being the customer, or CE operator code). The Hold field in the main screen of Sales Order Display should now show the order as AUTHORIZED (unless there are other Requests on hold or the order is on Credit Hold). Once authorized, the order will print in the warehouse within 1 minute if Auto Picking Slips is running. | No mockup | Same | N/A | N/A
[END]
Customer does not answer or return call. Instead, responds online via email link w/in 24 hours. They are brought to new order summary w/approve & cancel buttons. | Order summary w/approve/cancel | N/A* | N/A | N/A
Price is acceptable - click "approve order" - get regular order confirmation pop-up (no reference to price discrepancy notice being sent). Click continue. Then verify 4 outputs: | Pop-up as it is today | N/A | N/A | N/A
New order acknowledgment - check for all details such as special instructions, freight info, product description, etc. Be sure to also check email subject line as described in mockup. | Order ack email | N/A | N/A | N/A
Order history shows the order | Order history (as it is today) | N/A | N/A | N/A
New order summary from order history | Order summary | N/A | N/A | N/A
Go to Avante: All CE price discrepancy requests for the MASTER ORDER should have a closed status. There should be a time/date stamp in the Dates screen of the request (F9) showing when the order was approved. The F8-On Hold screen shows who approved the order (LADDAWN.COM being the customer, or CE operator code). The Hold field in the main screen of Sales Order Display should now show the order as AUTHORIZED (unless there are other Requests on hold or the order is on Credit Hold). Once authorized, the order will print in the warehouse within 1 minute if Auto Picking Slips is running. | No mockup | N/A | N/A | N/A
[END]
Price is not acceptable - click "cancel order" - get confirm cancellation pop-up (click yes), then check for 7 outputs: | Confirm cancellation | N/A | N/A | N/A
Email (or fax) cancellation acknowledgment. Be sure to also check email subject line as described in mockup. | Order ack email w/cancellation | N/A | N/A | N/A
Order history appearance - reflects cancellation - it says "Order cancelled" below the order name. | Order history w/cancellation | N/A | N/A | N/A
Order summary from order history - reflects cancellation [Note, mockup depicts only some lines which have been cancelled. When an order is cancelled this way, all lines will have been cancelled. Also, mockup has not been updated to show that quantity and extended price will be zeroed out.] | Order summary w/cancellation | N/A | N/A | N/A
Order tooltip (hover over order name) - reflects cancellation | Order name tooltip w/cancellation | N/A | N/A | N/A
Reprice (reorder pop-up) - reflects cancellation | Reprice w/cancellation | N/A | N/A | N/A
Go to Avante: All CE price discrepancy requests for the MASTER ORDER should have a closed status. There should be a time/date stamp in the Dates screen of the request (F9) showing when the order was approved. The F8-On Hold screen shows who approved the order (LADDAWN.COM being the customer, or CE operator code). The Hold field in the main screen of Sales Order Display should now show the order as AUTHORIZED (unless there are other Requests on hold or the order is on Credit Hold). Once authorized, the order will print in the warehouse within 1 minute if Auto Picking Slips is running. | No mockup | N/A | N/A | N/A
[END]
Customer does not respond within 24 hours.
System cancels order. Check for 7 outputs: | - |  | N/A | N/A
Email (or fax) cancellation acknowledgment. Be sure to also check email subject line as described in mockup. | Order ack email w/cancellation | N/A | N/A | N/A
Order history appearance - reflects cancellation - it says "Order cancelled" below the order name. | Order history w/cancellation | N/A | N/A | N/A
Order summary from order history - reflects cancellation [Note, mockup depicts only some lines which have been cancelled. When an order is cancelled this way, all lines will have been cancelled. Also, mockup has not been updated to show that quantity and extended price will be zeroed out.] | Order summary w/cancellation | N/A | N/A | N/A
Order tooltip (hover over order name) - reflects cancellation | Order name tooltip w/cancellation | N/A | N/A | N/A
Reprice (reorder pop-up) - reflects cancellation | Reprice w/cancellation | N/A | N/A | N/A
Go to Avante: All CE price discrepancy requests for the MASTER ORDER should have a closed status. There should be a time/date stamp in the Dates screen of the request (F9) showing when the order was approved. The F8-On Hold screen shows who approved the order (LADDAWN.COM being the customer, or CE operator code). The Hold field in the main screen of Sales Order Display should now show the order as AUTHORIZED (unless there are other Requests on hold or the order is on Credit Hold). Once authorized, the order will print in the warehouse within 1 minute if Auto Picking Slips is running. | No mockup | N/A | N/A | N/A
[END]
Price discrepancy greater than or equal to 6% (all handled the same - there are no preferences for handling differently)
(Repeat row 2. Skip row 3.) Proceed to checkout, through Shipping & Packaging step. Verify you get message to call regardless of time of order placement and whether or not 'must ship today' is chosen. Message appears when you click "save & continue" to proceed to next screen.
Order entered before 11 am local warehouse time | Call customer msg | Same | Same | Same
Order entered after 11 am local warehouse time, without "must ship today" checked | Call customer msg | Same | Same | Same
Order entered after 11 am local warehouse time, with "must ship today" checked (before proceeding, pretend you called and left msg) | Call customer msg | Same | Same | Same
Proceed through payment and labeling to order summary, verify price discrepancies are highlighted in order summary. Place order. Check for two simultaneous outputs: | Order summary | Same | Same | Same
1) System sends notification #2A to customer (t=0 hrs) - check to be sure message sent with high importance. | Email spec | Fax spec | Email spec (NEPB) | Fax spec (NEPB)
2) Verify new order confirmation pop-up referencing discrepancy - click Continue. Remain logged in. | Order confirmation pop-up | Same except "Sent to:" should be to a fax number. | Same | Same except "Sent to:" should be to a fax number.
After you are returned to shop widget, look in the Purple CE Requests Tab. There s/b an add’l CE Request for every individual order created for the master order. The price discrepancy request s/b completely disabled, and s/b showing that it’s on hold and routed to the generic price discrepancy operator. The user can put the order’s request on hold too if there is something else that the order needs to be held up for (ie, date expedite). Logout. | CE drawer | Same | Same | Same
Upon return to Avante, the price discrepancy requests s/b created with an OPEN status, so that it keeps the order on hold. You can view the requests using SOP9120 if you jot down the request numbers, or via SOP2001 (order display) using Options menu > C/E Request display. This will show you all requests that are attached to that order, and will then take you to SOP9120 to view each. On the main screen of order display, the order should show as on REQUEST HOLD. It may additionally show as on CREDIT hold if the customer is over their credit limit. IMPORTANT: Be sure you have closed out of the request before you proceed. | No mockup | Same | Same | Same
Customer responds within 24 hours
Customer responds online via email link. They are brought to new order summary w/approve & cancel buttons. | Order summary w/approve/cancel | N/A* | N/A | N/A
Price is acceptable - click "approve order" - get regular order confirmation pop-up (no reference to price discrepancy notice being sent). Click continue. Then verify 4 outputs: | Pop-up as it is today | N/A | N/A | N/A
New order acknowledgment - check for all details such as special instructions, freight info, product description, etc. Be sure to also check email subject line as described in mockup. | Order ack email | N/A | N/A | N/A
Order history shows the order | Order history (as it is today) | N/A | N/A | N/A
New order summary from order history | Order summary | N/A | N/A | N/A
Log in to Avante. Then… [copy from row 21 when ready] | No mockup | N/A | N/A | N/A
[END]
Price is not acceptable - click "cancel order" - get confirm cancellation pop-up (click yes), then check for 7 outputs: | Confirm cancellation | N/A | N/A | N/A
Email (or fax) cancellation acknowledgment. Be sure to also check email subject line as described in mockup. | Order ack email w/cancellation | N/A | N/A | N/A
Order history appearance - reflects cancellation - it says "Order cancelled" below the order name. | Order history w/cancellation | N/A | N/A | N/A
Order summary from order history - reflects cancellation [Note, mockup depicts only some lines which have been cancelled. When an order is cancelled this way, all lines will have been cancelled. Also, mockup has not been updated to show that quantity and extended price will be zeroed out.] | Order summary w/cancellation | N/A | N/A | N/A
Order tooltip (hover over order name) - reflects cancellation | Order name tooltip w/cancellation | N/A | N/A | N/A
Reprice (reorder pop-up) - reflects cancellation | Reprice w/cancellation | N/A | N/A | N/A
Log in to Avante. Then… [copy from row 21 when ready] | No mockup | N/A | N/A | N/A
[END]
Customer responds by faxing/calling/emailing CE - pretend you have very little info to go on, like no order number. [This script does not address scenarios involving individual line cancellations, price overrides or other "sales order changes" handled in Avante.]
CE locates pending order in order history. (Are you able to easily locate it?) | Pending order link | Same | Same | Same
Click pending order link; brings you to new order summary w/approve & cancel buttons. | Order summary w/approve/cancel | Same | Same | Same
Price is acceptable - click "approve order" - get regular order confirmation pop-up (no reference to price discrepancy notice being sent). Click continue and remain logged in. Then verify 4 outputs: | Pop-up as it is today (CE version) | Same ("Sent to:" should be to a fax number) | Same | Same ("Sent to:" should be to a fax number)
New order acknowledgment - check for all details such as special instructions, freight info, product description, etc. Be sure to also check email subject line as described in mockup. | Order ack email | Optio acknowledgments (1 for every order w/in master order) | Order ack email - same as Laddawn except has NEPB logo and no refs to Laddawn | Optio acknowledgments (1 for every order w/in master order)
Order history shows the order | Order history (as it is today) | Same | Same | Same
New order summary from order history | Order summary | Same | Same | Same
Go to Avante: All CE price discrepancy requests for the MASTER ORDER should have a closed status. There should be a time/date stamp in the Dates screen of the request (F9) showing when the order was approved. The F8-On Hold screen shows who approved the order (LADDAWN.COM being the customer, or CE operator code). The Hold field in the main screen of Sales Order Display should now show the order as AUTHORIZED (unless there are other Requests on hold or the order is on Credit Hold). Once authorized, the order will print in the warehouse within 1 minute if Auto Picking Slips is running. | No mockup | Same | Same | Same
[END]
Price is not acceptable - click "cancel order" - get confirm cancellation pop-up (click yes, remain logged in), then check for 7 outputs: | Confirm cancellation | Same | Same | Same
Email (or fax) cancellation acknowledgment. Be sure to also check email subject line as described in mockup. | Order ack email w/cancellation | Optio acknowledgments (1 for every order w/in master order) | Order cancellation email - same as Laddawn except has NEPB logo and no refs to Laddawn | Optio acknowledgments (1 for every order w/in master order)
Order history appearance - reflects cancellation - it says "Order cancelled" below the order name. | Order history w/cancellation | Same | Same | Same
Order summary from order history - reflects cancellation [Note, mockup depicts only some lines which have been cancelled. When an order is cancelled this way, all lines will have been cancelled. Also, mockup has not been updated to show that quantity and extended price will be zeroed out.] | Order summary w/cancellation | Same | Same | Same
Order tooltip (hover over order name) - reflects cancellation | Order name tooltip w/cancellation | Same | Same | Same
Reprice (reorder pop-up) - reflects cancellation | Reprice w/cancellation | Same | Same | Same
Go to Avante: All CE price discrepancy requests for the MASTER ORDER should have a closed status. There should be a time/date stamp in the Dates screen of the request (F9) showing when the order was approved. The F8-On Hold screen shows who approved the order (LADDAWN.COM being the customer, or CE operator code). The Hold field in the main screen of Sales Order Display should now show the order as AUTHORIZED (unless there are other Requests on hold or the order is on Credit Hold). Once authorized, the order will print in the warehouse within 1 minute if Auto Picking Slips is running. | No mockup | Same | Same | Same
[END]
Customer does not respond within 24 hours
System sends notification #2B to customer. Notification #2B is forwarded to queue. CE calls and … | Email spec | Fax spec | NEPB email | NEPB fax
Customer answers when CE calls, calls back after getting message, or replies via fax or email w/in 24 hours | - | - | - | -
CE locates pending order in order history. (Are you able to easily locate it?) | Pending order link | Same | Same | Same
Click pending order link; brings you to new order summary w/approve & cancel buttons. | Order summary w/approve/cancel | Same | Same | Same
Price is acceptable - click "approve order" - get regular order confirmation pop-up (no reference to price discrepancy notice being sent). Click continue and remain logged in. Then verify 4 outputs: | Pop-up as it is today (CE version) | Same ("Sent to:" should be to a fax number) | Pop-up as it is today | Same ("Sent to:" should be to a fax number)
New order acknowledgment - check for all details such as special instructions, freight info, product description, etc. Be sure to also check email subject line as described in mockup. | Order ack email | Optio acknowledgments (1 for every order w/in master order) | Order ack email - same as Laddawn except has NEPB logo and no refs to Laddawn | Optio acknowledgments (1 for every order w/in master order)
Order history shows the order | Order history (as it is today) | Same | Same | Same
New order summary from order history | Order summary | Same | Same | Same
Go to Avante: All CE price discrepancy requests for the MASTER ORDER should have a closed status. There should be a time/date stamp in the Dates screen of the request (F9) showing when the order was approved. The F8-On Hold screen shows who approved the order (LADDAWN.COM being the customer, or CE operator code). The Hold field in the main screen of Sales Order Display should now show the order as AUTHORIZED (unless there are other Requests on hold or the order is on Credit Hold). Once authorized, the order will print in the warehouse within 1 minute if Auto Picking Slips is running. | No mockup | Same | Same | Same
[END]
Price is not acceptable - click "cancel order" - get confirm cancellation pop-up (click yes, remain logged in), then check for 7 outputs: | Confirm cancellation | Same | Same | Same
Email (or fax) cancellation acknowledgment. Be sure to also check email subject line as described in mockup. | Order ack email w/cancellation | Optio acknowledgments (1 for every order w/in master order) | Order cancellation email - same as Laddawn except has NEPB logo and no refs to Laddawn | Optio acknowledgments (1 for every order w/in master order)
Order history appearance - reflects cancellation - it says "Order cancelled" below the order name. | Order history w/cancellation | Same | Same | Same
Order summary from order history - reflects cancellation [Note, mockup depicts only some lines which have been cancelled. When an order is cancelled this way, all lines will have been cancelled. Also, mockup has not been updated to show that quantity and extended price will be zeroed out.] | Order summary w/cancellation | Same | Same | Same
Order tooltip (hover over order name) - reflects cancellation | Order name tooltip w/cancellation | Same | Same | Same
Reprice (reorder pop-up) - reflects cancellation | Reprice w/cancellation | Same | Same | Same
Go to Avante: All CE price discrepancy requests for the MASTER ORDER should have a closed status. There should be a time/date stamp in the Dates screen of the request (F9) showing when the order was approved. The F8-On Hold screen shows who approved the order (LADDAWN.COM being the customer, or CE operator code). The Hold field in the main screen of Sales Order Display should now show the order as AUTHORIZED (unless there are other Requests on hold or the order is on Credit Hold). Once authorized, the order will print in the warehouse within 1 minute if Auto Picking Slips is running. | No mockup | Same | Same | Same
[END]
Customer does not answer or return call, but responds online via email link within 24 hours. They are brought to new order summary w/approve & cancel buttons. | Order summary w/approve/cancel | N/A* | N/A | N/A
Price is acceptable - click "approve order" - get regular order confirmation pop-up (no reference to price discrepancy notice being sent). Click continue. Then verify 4 outputs: | Pop-up as it is today | N/A | N/A | N/A
New order acknowledgment - check for all details such as special instructions, freight info, product description, etc. Be sure to also check email subject line as described in mockup. | Order ack email | N/A | N/A | N/A
Order history shows the order | Order history (as it is today) | N/A | N/A | N/A
New order summary from order history | Order summary | N/A | N/A | N/A
Go to Avante: All CE price discrepancy requests for the MASTER ORDER should have a closed status. There should be a time/date stamp in the Dates screen of the request (F9) showing when the order was approved. The F8-On Hold screen shows who approved the order (LADDAWN.COM being the customer, or CE operator code). The Hold field in the main screen of Sales Order Display should now show the order as AUTHORIZED (unless there are other Requests on hold or the order is on Credit Hold). Once authorized, the order will print in the warehouse within 1 minute if Auto Picking Slips is running. | No mockup | N/A | N/A | N/A
[END]
Price is not acceptable - click "cancel order" - get confirm cancellation pop-up (click yes), then check for 7 outputs: | Confirm cancellation | N/A | N/A | N/A
Email (or fax) cancellation acknowledgment. Be sure to also check email subject line as described in mockup. | Order ack email w/cancellation | N/A | N/A | N/A
Order history appearance - reflects cancellation - it says "Order cancelled" below the order name. | Order history w/cancellation | N/A | N/A | N/A
Order summary from order history - reflects cancellation [Note, mockup depicts only some lines which have been cancelled. When an order is cancelled this way, all lines will have been cancelled. Also, mockup has not been updated to show that quantity and extended price will be zeroed out.] | Order summary w/cancellation | N/A | N/A | N/A
Order tooltip (hover over order name) - reflects cancellation | Order name tooltip w/cancellation | N/A | N/A | N/A
Reprice (reorder pop-up) - reflects cancellation | Reprice w/cancellation | N/A | N/A | N/A
Go to Avante: All CE price discrepancy requests for the MASTER ORDER should have a closed status. There should be a time/date stamp in the Dates screen of the request (F9) showing when the order was approved. The F8-On Hold screen shows who approved the order (LADDAWN.COM being the customer, or CE operator code). The Hold field in the main screen of Sales Order Display should now show the order as AUTHORIZED (unless there are other Requests on hold or the order is on Credit Hold). Once authorized, the order will print in the warehouse within 1 minute if Auto Picking Slips is running. | No mockup | N/A | N/A | N/A
[END]
Customer does not respond within 24 hours.
System cancels order. Check for 7 outputs:
Email (or fax) cancellation acknowledgment. Be sure to also check email subject line as described in mockup. | Order ack email w/cancellation | Optio acknowledgments (1 for every order w/in master order) | Order cancellation email - same as Laddawn except has NEPB logo and no refs to Laddawn | Optio acknowledgments (1 for every order w/in master order)
Order history appearance - reflects cancellation - it says "Order cancelled" below the order name. | Order history w/cancellation | Same | Same | Same
Order summary from order history - reflects cancellation [Note, mockup depicts only some lines which have been cancelled. When an order is cancelled this way, all lines will have been cancelled. Also, mockup has not been updated to show that quantity and extended price will be zeroed out.] | Order summary w/cancellation | Same | Same | Same
Order tooltip (hover over order name) - reflects cancellation | Order name tooltip w/cancellation | Same | Same | Same
Reprice (reorder pop-up) - reflects cancellation | Reprice w/cancellation | Same | Same | Same
Go to Avante: All CE price discrepancy requests for the MASTER ORDER should have a closed status. There should be a time/date stamp in the Dates screen of the request (F9) showing when the order was approved. The F8-On Hold screen shows who approved the order (LADDAWN.COM being the customer, or CE operator code). The Hold field in the main screen of Sales Order Display should now show the order as AUTHORIZED (unless there are other Requests on hold or the order is on Credit Hold). Once authorized, the order will print in the warehouse within 1 minute if Auto Picking Slips is running. | No mockup | Same | Same | Same
[END]
*Fax only customers may have logins and therefore could go online to order summary via order history to manage the approval/cancellation themselves.
Note on A2: Susan Parker: INSTRUCTIONS: Each "END" line represents the end of a unique path. Test one path at a time, using one of the 4 customer types at a time, using one copy of this sheet per test. Read through the script and determine which path you're going to test. Make a copy of this sheet, then hide all the irrelevant rows so you don't get lost or have to scroll. Highlight the column representing the customer you are testing. Then be sure your test customer has the appropriate preferences set on the web (if applicable to the test) and in Avante - for email v. fax acknowledgments. When you get to the Shipping & Packaging screen in checkout during your test, it is not necessary to test all 3 of the "must ship today"/warehouse time scenarios. Just choose the scenario that best fits your current situation (in the Pass/Fail column, type "skipped" in the rows you do not test). Record all of your findings in the pass/fail column, in a separate document (best for screenshots), or a combination of the two. Do not open any tickets, but be prepared to do so.