## Sheet1
Task | Category | Responsible | Timing
Competitor Analysis | Market Research | Jeff | October
Sales Team Intel/Feedback | Market Research | Jeff, Dave | October
Pricing Strategy | Pricing and Costing | Owen, Jeff, Dave | December
SKU Selection | Product Management | Dave, Jeff | 1/11
SKU Setup | Purchasing | Diana, Jerry | 1/11
Creative Brief | Sales/Marketing | Jeff | 1/11
Product Information Architecture/UX Heirarchy | Laddawn.com | Jeff, Dave | 1/11
Customer Feedback Campaign | Market Research | Jeff, Mark | 1/14 - 1/18
Product Brief | Sales/Marketing | Jeff | 1/18
Demand Forecasting/Initial Buy/Minimums | Forecasting and Purchasing | Dave, John | 1/18
Web Template/HelpDesk Ticket | Laddawn.com | Jeff | 1/18
Results Design and Descriptions | Laddawn.com | Dave | 1/18
Development | Laddawn.com | Bill, Susan | 1/18 - 2/26
Purchase Order to Berry | Purchasing | Diana | 1/21
Dev Site Launch | Laddawn.com | Wayne | 1/28
Web Pricing | Laddawn.com | John | 1/18 - 2/26
Web Images | Laddawn.com | Chris E | 1/18 - 2/26
UX Testing | Laddawn.com | John, Jay | 2/11 - 2/26
Catalog Work - new section, summary, images, descriptions, ads | Catalog | John, Chris | 2/15
Catalog goes to print | Catalog | Chris, Suzi | 2/15
CR/CE Training | Sales/Marketing | Tina | 2/22
Sell Sheets | Sales/Marketing | Chris E | 2/26
Transfer Trucks | Purchasing | Diana | 2/4 - 2/15
Web GO LIVE | Laddawn.com | Bill | 2/26
Catalog GO LIVE | Sales/Marketing | Parke | 3/4
Email Blast 1 | Sales/Marketing | Suzi | 3/4
Email Blast 2 | Sales/Marketing | Suzi | 3/5
Blog Post | Sales/Marketing | Parke | 3/5
Call Campaign + in Call Survey | Sales/Marketing | CRP's
Survey Results Analysis | Sales/Marketing | Pankhuri
Follow Up Campaign | Sales/Marketing | CRL's
in progress
done
GO LIVE