## Sheet1
TEST EDIT | Criticality | Difficulty | Reported by | Owner(s) | Due by | Status | Comments
1. UI designs for the pop-ups of each category. | High | High | J. Piette | Owen | 2012-08-31 | Open | We may have a good idea of UI by 8/31, but anticipate "final, final" 1-2 weeks beyond that. Initial UI concepts could change during that period.
4. Enabling and disabling of options - hidden or disabled? | Med | Moderate | J. Piette | Owen | 2012-08-31 | Open | Need clarification. Isn't this part of UI (issue 1)? Can it be determined independently?
2. Text desired on the main screen when various choices are made on those pop-ups | Med | Easy | J. Piette | Owen | 2012-08-27 | Closed
3. How to handle validation errors | Med | High | J. Piette | Owen | 2012-08-27 | Closed
5. Gauge in microns | Low | Moderate | J. Piette | Susan | 2012-08-23 | Closed | UI for mils resolves this.
Test edit