## Sheet1
Overall status & highlights
Status, accomplishments and next steps by project component
1) Outstanding/ incomplete |  | 2) Documentation & design phase |  | 3) Review & validation |  | 4) Handed off for programming | Accomplishmens/changes since last week | Next steps, upcoming activity
|  |  | Shop: Special scenarios, YMAC etc. |  |  | Shop & search results (base reqs, design) | Resolved "see options" handling. In depth review with developers; some clarification around UOM and rounding. | Attach concrete dates to key workzone tasks. Talk to outside firm about front end coding.
|  |  | Special scenarios |  | Active Cart - (base reqs, design) |  | Nothing other than cleaning up images. | Need to think through the more complicated freight scenarios. Attach concrete dates to key workzone tasks. Talk to outside firm about front end coding.
|  | Checkout |  |  |  |  | Gathered data on shipping practices. Fine tuned interface for ship-to selections. Made progress on bundling scenarios. Much work remains. | Fill in remaining gaps.. Will likely be focus for next 4-6 weeks.
| Tagged Items | [5 empty] | No change. | Need to revisit what had been documented previously. Need to flesh out further. No action foreseen within next 2 weeks.
|  | Share an item, share a cart, sharing content |  |  |  |  | Significant progress on requirements & design for sharing an item, much work remains. | Document new approach and instructions for Steve for 2d design iteration.
|  | Narrative thread |  |  |  |  | No change. | Need to establish clear goals and expectations for Ed and John.
My acct/user prefs | [6 empty] | No change | To be focus of meetings with Ladd and Dawn in near future, if Sharing and Checkout do not consume all available meeting time.
Past orders | [6 empty] | No change | No action foreseen within next 2 weeks.
Predictive ordering | [6 empty] | No change | No action foreseen within next 2 weeks.
Prod. Descrip-tions | [6 empty] | No change | No action foreseen within next 2 weeks.
Discussion topics
Summer schedules and pace of work.
Checkout progress.
We have not had a status meeting or report since 6/7, but have had several requirements meetings.
Ended web component of engagement with Corey. Plan to interview firm recommended by Corey; weigh whether to pursue additional front end coding for sake of exposure to alternative approaches.
IT staff transitioning off other projects to focus on this project.